## 0. Overview
A YAT release is done in 8 steps:
				Duration	Step	Total
		1.	Regression Testing		13:30	13:30
		2.	Preparation		01:40	15:10
		3.	Final Testing		01:30	16:40
		4.	Build		00:40	17:20
		5.	Installation Testing		00:40	17:55
		6.	Packaging		00:40	17:55
		7.	Upload		01:20	19:15
		8.	Finalization		03:30	22:15

The YAT story:
					YAT	MKY	ALAZ	NUnit	netrtfwr.		LU.xml	RU.xml	.yat	.yaw		SVN		Remarks
	201x-xx-xx	:	YAT 2.0 Epsilon				1.99.80	1.0.21	3.5.18	1.0.17	0.9.19		1.5.3	1.0.0	1.5.3	1.2.1		1602
	2017-10-15	:	YAT 2.0 Delta				1.99.80	1.0.21	3.5.17	1.0.17	0.9.18		1.5.2		1.5.2	1.2.1		1602		Version of auxiliary assemblies (except NUnit which is not distributed) also incremented twice to prevent potential version conflicts at those who have tested the preliminary versions
	2017-07-04	:	YAT 2.0 Gamma 3				1.99.70	1.0.19	3.5.15	1.0.16	0.9.16		1.5.1		1.5.1	1.2.1		1408
	2016-09-30	:	YAT 2.0 Gamma 2''				1.99.52	1.0.17	3.5.14	1.0.14	0.9.15		1.5.0		1.5.0	1.2.1		1188
	2016-09-17	:	YAT 2.0 Gamma 2'				1.99.51	1.0.16	3.5.13	1.0.13	0.9.14		1.5.0		1.5.0	1.2.1		1160
	2016-09-16	:	YAT 2.0 Gamma 2				1.99.50	1.0.15	3.5.12	1.0.12	0.9.13		1.5.0		1.5.0	1.2.1		1158
	2015-06-13	:	YAT 2.0 Gamma 1''				1.99.34	1.0.13	3.5.11	1.0.10			1.4.1		1.4.1	1.2.0		799
	2015-06-07	:	YAT 2.0 Gamma 1'				1.99.33	1.0.12	3.5.10	1.0.9			1.4.0		1.4.0	1.2.0		778
	2015-06-01	:	YAT 2.0 Gamma 1				1.99.32	1.0.11	3.5.9	1.0.8			1.4.0		1.4.0	1.2.0		769
	2013-02-02	:	YAT 2.0 Beta 4 Candidate 2				1.99.30	1.0.9	3.5.7	1.0.6			1.3.1		1.3.1	1.1.1		626
	2011-12-05	:	YAT 2.0 Beta 4 Candidate 1				1.99.28	1.0.7	3.5.5	1.0.4			1.3.0		1.3.0	1.1.0		502
	2011-04-25	:	YAT 2.0 Beta 3 Candidate 4				1.99.26	1.0.5	3.5.3	1.0.2			1.2.4		1.2.9	1.0.0		419
	2010-11-28	:	YAT 2.0 Beta 3 Candidate 3				1.99.25	1.0.4	3.5.2	1.0.1			1.2.4		1.2.9	1.0.0		385
	2010-11-11	:	YAT 2.0 Beta 3 Candidate 2				1.99.24	1.0.4	3.5.2	1.0.1			1.2.4		1.2.8	1.0.0		369
	2009-09-10	:	YAT 2.0 Beta 3 Candidate 1'				1.99.23	1.0.1	3.5.0				1.2.4		1.2.7	1.0.0		251
	2009-09-08	:	YAT 2.0 Beta 3 Candidate 1				1.99.22	1.0.1	3.5.0				1.2.3		1.2.6	1.0.0		247
	2008-07-18	:	YAT 2.0 Beta 2 Candidate 4				1.99.20	1.0.0	1.2.0				1.2.3		1.2.5	1.0.0		201
	2008-04-01	:	YAT 2.0 Beta 2 Candidate 3				1.99.19					1.2.2		1.2.4	1.0.0		136
	2008-03-17	:	YAT 2.0 Beta 2 Candidate 2				1.99.18					1.2.2		1.2.3	1.0.0		122
	2008-02-11	:	YAT 2.0 Beta 2 Candidate 1				1.99.17					1.2.2		1.2.2	1.0.0		105
	2007-08-30	:	YAT 2.0 Beta 2 Preliminary				1.99.13					1.2.1		1.2.1	1.0.0		(45)
	2007-04-15	:	YAT 2.0 Beta 1				1.99.12					1.2.0		1.2.0			9
	2007-02-25	:	YAT 2.0 Alpha 3				1.99.8					1.1.2		1.1.2
	2007-02-07	:	YAT 2.0 Alpha 2				1.99.3					1.1.1		1.1.1
	2007-01-23	:	YAT 2.0 Alpha 1				1.99.0					1.1.0		1.1.0
	2003-10-31	:	XTerm232				1.0.2					1.0.1		1.0.1
	2003-10-30	:	XTerm232				1.0.1					1.0.1		1.0.1
	2003-10-14	:	XTerm232				1.0.0					1.0.0		1.0.0

## 1. Regression Testing
				Duration	Step		Total

1.				Regression Testing		00:00	13:30	00:00	13:30

	1.1.			Run coding style checks		00:30		00:30
		1.1.1.		Use StyleCop on 'Debug Test'
				> "Visual Studio > Tools > Run StyleCop (Rescan All)"

				1 expected warning:
				SA1409 : CSharp.Maintainability @ YAT.Model.Terminal.cs

				Note: Rescan just takes a few seconds, but expect quite some time for fixes

	1.2.			Run assembly checks		01:00		01:30
		1.2.1.		Ensure to select 'YAT.Test' as the 'StartUp' project

				Note: 'YAT' or 'YATConsole' don't have dependencies to the test projects, thus the test projects will not get built!

		1.2.2.		Build 'Debug Test'

		1.2.3.		Use FxCop 'MKY.Debug' on 'Debug Test'
				> Open and verify "\MKY\MKY.Debug.FxCop"

				30 expected warnings:
				CA1002 : DoNotExposeGenericLists @ 4 locations
				CA2214 : DoNotCallOverridableMethodsInConstructors @ 26 locations

		1.2.4.		Use FxCop 'NUnit.Debug' on 'Debug Test'
				> Open and verify "\NUnit\NUnit.Debug.FxCop"

		1.2.5.		Use FxCop 'YAT.Debug' on 'Debug Test'
				> Open and verify "\YAT\YAT.Debug.FxCop"

				136 expected errors/warnings:
				CA1002 : DoNotExposeGenericLists @ 52 locations
				CA2214 : DoNotCallOverridableMethodsInConstructors @ 84 locations

				Note: Rescan just takes a few seconds, but expect quite some time for fixes

	1.3.			Run automated tests		06:00		07:30
		1.3.1.		Ensure that test environment is fully ready (VSPE, loopbacks, MT-SICS,…)

		1.3.2.		Ensure to select 'YAT.Test' as the 'StartUp' project

				Note: 'YAT' or 'YATConsole' don't have dependencies to the test projects, thus the test projects will not get built!

		1.3.3.		Build 'Debug Test'

		1.3.4.		Use NUnit on 'Debug Test'
				> "Visual Studio > Tools > NUnit" (Alt+N)
				> Categories = Select and exclude all longer than a minute (but keep 1 minute because some tests just take this long)
				> "Project > Configurations > Debug" ('Debug' @ regression + 'Release' @ final)

				List of test assemblies, for manual ticking:
				> MKY.Test (0'6'')
				> MKY.IO.Ports.Test (2'10'' but see issue below)
				> MKY.IO.Serial.SerialPort.Test (0'0'')
				> MKY.IO.Serial.Socket.Test (4'00'')
				> MKY.IO.Serial.Usb.Test (0'2'')
				> MKY.IO.Usb.Test (0'5'')
				> YAT.Controller.Test (0'20'')
				> YAT.Domain.Test (4'00'')
				> YAT.Model.Test
				> Clear/Connection/FileHandling/Start/Stress (1'50'')
				> Transmission (9'30'')
				> MTSicsDevice (1'30'')
				> One/Two/Repeating (8'00'')
				> YAT.Settings.Test (0'20'')
				> YAT.View.Test (2'40'')

				Known issues:
				MKY.IO.Ports.Test.SerialPort.ConnectionTest.TestDisconnectReconnect...() fail when running in sequence with previous tests, but pass when running as single test / => For both failed tests: Close NUnit, reconfigure USB Hubs, then run first failed test again, then redo for second fail test / => Don't forget to close and reconfigure after the last test
				MKY.IO.Usb.Test.ConnectionTest is not yet implemented => Assert.Ignore() => yellow bar
				YAT.Controller.Test: Note #250 "ControllerTest modifies the current working-copy settings" / + #350 Interactive ControllerTests may fail because current application settings are used" => Simply run the failed tests again
				YAT.Model.Test.StressTest is not yet implemented => Assert.Ignore() => yellow bar
				YAT.Model.Test.Transmission.*.IPLoopbacks for 'OnSpecificIPv4/6Interface' => Assert.Ignore() => yellow bar => Install/config of "TAP-Win32 Adapter" is required
				YAT.Model.Test.Transmission.OneWay.LoopbackSelfs may fail in any case because long lines get mixed up (DirChangeLineBreak, bug #371)
				YAT.Model.Test.Transmission.OneWay.LoopbackSelfs fail at 'SingleNoEOL', 'DoubleNoEOL', 'StillEol3', 'Clear1/2' because Rx results in additional line (DirChangeLineBreak)
				YAT.Model.Test.Transmission.Repeating.LoopbackSelfs fail at '*TwoWay' because Rx results in additional line(s) (DirChangeLineBreak)
				YAT.Model.Test.Transmission.TwoWay.LoopbackSelfs fail because Rx results in additional line(s) (DirChangeLineBreak)
				YAT.Settings.Test.FileVersionsTest [03] of V1.99.5x fail (bugs #232 and #246 "Issues with [Alternate]TolerantXmlSerializer")
				YAT.View.Test.StressTest: Note #349 "StressTest uses the current local user's application settings"

				Note: If everything works fine (rarely the case…), run takes around 45 minutes, but expect quite some time for fixes

	1.4.			Run manual tests		06:00		13:30
		1.4.1.		Ensure to select 'YAT' as the 'StartUp' project

		1.4.2.		According to manual test cases in "\YAT\_Doc.Project\5 - Test\YAT – Test.ods" using 'Release' configuration but still 'Start Debugging [F5]' to handle issues

				List of test sections, for manual ticking:
				> MKY.IO.Serial.SerialPort
				> MKY.IO.Serial.Socket
				> TCP/IP
				> UDP/IP
				> MKY.IO.Serial.Usb
				> YAT.Model.Main
				> YAT.Model.Terminal
				> YAT.View.Forms.Main
				> YAT.View.Forms.Terminal
				> YAT.View.Forms.Settings
				> YAT.Log
				> YAT.Info
				(Installation not yet, will be done in 5.)

## 2. Preparation
				Duration	Step		Total

2.				Preparation		00:00	01:40	13:30	15:10

	2.1.			Set versions		00:15		13:45
		2.1.1.		Ensure that product version in ALAZ.Version is different than at last release
		2.1.2.		Ensure that product version in netrtfwriter AssemblyInfo is different than at last release
				> Versions must differ to ensure proper installation/update!
				> Additional increment makes little sense as there are no version tags in file header
		2.1.3.		Increment product version in MKY.Version
				> Versions must differ to ensure proper installation/update!
		2.1.4.		Increment product version in NUnit.Version
				> Additional increment not necessary as this assembly is not distributed
		2.1.5.		Increment product version in YAT.Version
				> Versions must differ to ensure proper installation/update!
		2.1.6.		Set product version in MKY file headers (*.* throughout \Trunk => 342 occurrences)
				> Also remove 'Development', e.g. '// MKY Version 1.0.21'
		2.1.7.		Set product version in NUnit file headers (*.* throughout \Trunk => 3 occurrences)
				> Also remove 'Development', e.g. '// NUnit Version 1.0.17'
		2.1.8.		Set product version in YAT file headers (*.* throughout \Trunk => 228 occurrences)
				> Also remove 'Development', e.g. '// YAT 2.0 Delta Version 1.99.80'
		2.1.9.		Set product version in all other file headers (*.cs throughout \Trunk)
				> Search for all previous versions, e.g. '1.99.70' and '1.99.75' and replace them as required (former settings are OK)
		2.1.10.		Set product name post fix in "YAT.Application.ApplicationEx"
		2.1.11.		Fill date and versions into 'The YAT story' in '0. Overview'
		2.1.12.		Commit changes to SVN
				> Check the property status of each file (except those of 3rd party assemblies)

	2.2.			Set installation version		00:05		13:50
		2.2.1.		Set product title in "YAT.Setup.x86"
		2.2.2.		Set product version in "YAT.Setup.x86"
		2.2.3.		Set product title in "YAT.Setup.x64"
		2.2.4.		Set product version in "YAT.Setup.x64"
		2.2.5.		Commit changes to SVN

	2.3.			Update settings defaults and schema in "YAT\!-Settings\!-Current"		00:30		14:20
		2.3.1.		Ensure to select 'YAT.Test' as the 'StartUp' project

				Note: 'YAT' or 'YATConsole' don't have dependencies to the test projects, thus the test projects will not get built!

		2.3.2.		Create files using NUnit on 'Debug Test'
				> Build "Debug Test"
				> "Visual Studio > Tools > NUnit" (Alt+N)
				> YAT.Settings.Test.SettingsFilesArchiver
				Note that explicit tests are only runable if no include/exclude filter is active!
		2.3.3.		Diff *SettingsDefault.xml
		2.3.4.		Increase hard-coded settings versions if required
		2.3.5.		Fill settings versions into '0. Overview'
		2.3.6.		If version has changed, create files again
		2.3.7.		Diff and verify *SettingsDefault.xml in detail
				> Restore the <FileType> tag to YAT (result of NUnit)
				> Manually set the <ProductVersion> tag to the YAT version (result of NUnit)
				> LocalUser: Restore the <Paths> tags to YAT (result of NUnit)
				> Terminal: Restore the <Log\Root> tags to YAT (result of NUnit)
		2.3.8.		Also diff and verify *SettingsSchema.xsd

	2.4.			Add new settings defaults and schema to settings archive		00:05		14:25
		2.4.1.		Archive the upgraded files from "\YAT\!-Settings\!-Current" to "\<New Version>"

	2.5.			Upgrade settings in settings archive "YAT\!-Settings\!-Current"		00:30		14:55
		2.5.1.		Prepare upgrade
				> Delete all "YAT Local Settings" folders in "C:\Users\<User>\AppData\Local\YAT\YAT"
				(ensure that window size is defaulted)
				> Delete all terminal and workspace files in "YAT\!-Settings\!-Current"
				(ensure that "\!-Current" will contain exact clones of the previous version)
				> Copy all terminal and workspace files of previous version to "\!-Current"
				> Connect all test devices
				(needed with some of the files)
		2.5.2.		Commit changes to SVN
		2.5.3.		Select 'YAT' as the 'StartUp' project
		2.5.4.		Perform upgrade
				> Run YAT on 'Release' but do not move or resize window
				> Open each old settings file in "YAT\!-Settings\!-Current"
				> Modify settings
				> For terminals, change 'Toolbar > Radix' to ensure that IO settings are kept
				> For workspaces, change 'Window > Always On Top' to ensure that terminal settings are kept
				> Revert change above
				> Save upgraded but unchanged settings
		2.5.5.		Diff and verify the new settings

	2.6.			Add new settings to settings archive		00:10		15:05
		2.6.1.		Archive the upgraded files in "YAT\!-Settings\<New Version>"
		2.6.2.		Add new settings to "YAT.Settings.Test.SettingsFilesProvider"
		2.6.3.		Add new settings to "YAT.Settings.Test.FileVersionsTest"

	2.7.			Rebuild and commit		00:05		15:10
		2.7.1.		Select 'YAT.Test' as the 'StartUp' project
		2.7.2.		Build 'Debug Test' (ensure no build errors)
		2.7.3.		Commit changes to SVN

## 3. Final Testing
				Duration	Step		Total

3.				Final Testing		00:00	01:30	15:10	16:40

	3.1.			Re-Run coding style checks		00:10		15:20
		3.1.1.		Use StyleCop on 'Debug Test'
				> "Visual Studio > Tools > Run StyleCop (Rescan All)"

				1 expected warning:
				SA1409 : CSharp.Maintainability @ YAT.Model.Terminal.cs

				Note: Rescan just takes a few seconds, and there should be not many findings anymore

	3.2.			Re-Run assembly checks		00:10		15:30
		3.2.1.		Ensure to select 'YAT.Test' as the 'StartUp' project

				Note: 'YAT' or 'YATConsole' don't have dependencies to the test projects, thus the test projects will not get built!

		3.2.2.		Build 'Debug Test'

		3.2.3.		Use FxCop 'MKY.Debug' on 'Debug Test'
				> Open and verify "\MKY\MKY.Debug.FxCop"

				30 expected warnings:
				CA1002 : DoNotExposeGenericLists @ 4 locations
				CA2214 : DoNotCallOverridableMethodsInConstructors @ 26 locations

		3.2.4.		Use FxCop 'NUnit.Debug' on 'Debug Test'
				> Open and verify "\NUnit\NUnit.Debug.FxCop"

		3.2.5.		Use FxCop 'YAT.Debug' on 'Debug Test'
				> Open and verify "\YAT\YAT.Debug.FxCop"

				136 expected errors/warnings:
				CA1002 : DoNotExposeGenericLists @ 52 locations
				CA2214 : DoNotCallOverridableMethodsInConstructors @ 84 locations

				Note: Rescan just takes a few seconds, and there should be not many findings anymore

	3.3.			Re-run automated tests		01:00		16:30
		3.3.1.		Ensure that test environment is fully ready (VSPE, loopbacks, MT-SICS,…)

		3.3.2.		Ensure to select 'YAT.Test' as the 'StartUp' project

				Note: 'YAT' or 'YATConsole' don't have dependencies to the test projects, thus the test projects will not get built!

		3.3.3.		Build 'Release Test'

		3.3.4.		Use NUnit on 'Release Test'
				> "Visual Studio > Tools > NUnit" (Alt+N)
				> Categories = Select and exclude all longer than a minute (but keep 1 minute because some tests just take this long)
				> "Project > Configurations > Release" (Debug @ Regression + Release @ Final)

				List of test assemblies, for manual ticking:
				> MKY.Test (0'6'')
				> MKY.IO.Ports.Test (2'10'' but see issue below)
				> MKY.IO.Serial.SerialPort.Test (0'0'')
				> MKY.IO.Serial.Socket.Test (4'00'')
				> MKY.IO.Serial.Usb.Test (0'2'')
				> MKY.IO.Usb.Test (0'5'')
				> YAT.Controller.Test (0'20'')
				> YAT.Domain.Test (4'00'')
				> YAT.Model.Test
				> Clear/Connection/FileHandling/Start/Stress (1'50'')
				> Transmission (9'30'')
				> MTSicsDevice (1'30'')
				> One/Two/Repeating (8'00'')
				> YAT.Settings.Test (0'20'')
				> YAT.View.Test (2'40'')

				Known issues:
				MKY.IO.Ports.Test.SerialPort.ConnectionTest.TestDisconnectReconnect...() fail when running in sequence with previous tests, but pass when running as single test / => For both failed tests: Close NUnit, reconfigure USB Hubs, then run first failed test again, then redo for second fail test / => Don't forget to close and reconfigure after the last test
				MKY.IO.Usb.Test.ConnectionTest is not yet implemented => Assert.Ignore() => yellow bar
				YAT.Controller.Test: Note #250 "ControllerTest modifies the current working-copy settings" / + #350 Interactive ControllerTests may fail because current application settings are used" => Simply run the failed tests again
				YAT.Model.Test.StressTest is not yet implemented => Assert.Ignore() => yellow bar
				YAT.Model.Test.Transmission.*.IPLoopbacks for 'OnSpecificIPv4/6Interface' => Assert.Ignore() => yellow bar => Install/config of "TAP-Win32 Adapter" is required
				YAT.Model.Test.Transmission.OneWay.LoopbackSelfs may fail in any case because long lines get mixed up (DirChangeLineBreak, bug #371)
				YAT.Model.Test.Transmission.OneWay.LoopbackSelfs fail at 'SingleNoEOL', 'DoubleNoEOL', 'StillEol3', 'Clear1/2' because Rx results in additional line (DirChangeLineBreak)
				YAT.Model.Test.Transmission.Repeating.LoopbackSelfs fail at '*TwoWay' because Rx results in additional line(s) (DirChangeLineBreak)
				YAT.Model.Test.Transmission.TwoWay.LoopbackSelfs fail because Rx results in additional line(s) (DirChangeLineBreak)
				YAT.Settings.Test.FileVersionsTest [03] of V1.99.5x fail (bugs #232 and #246 "Issues with [Alternate]TolerantXmlSerializer")
				YAT.View.Test.StressTest: Note #349 "StressTest uses the current local user's application settings"

				Note: If everything works fine (rarely the case…), run takes around 45 minutes, and there should be no more findings

	3.4.			Check and commit		00:10		16:40
		3.4.1.		Ensure no debug left-overs by globally searching for "Debug.Write"
				> Match case
				> No match whole word

				120 occurrences totally expected in ArgsHandler, Diagnostics, Usb, Hid,...

		3.4.2.		Ensure no debug left-overs by globally searching for "Trace.Write"
				> Match case
				> No match whole word

				239 occurrences totally expected in Diagnostics and Serializer, as well as many test assemblies

		3.4.3.		Commit changes to SVN
				> Ensure to first revert the modified settings file(s)

## 4. Build
				Duration	Step		Total

4.				Build		00:00	00:40	16:40	17:20

	4.1.			Finalize release notes		00:10		16:50
		4.1.1.		Check whether release notes are complete
		4.1.2.		Check whether limitations still apply
		4.1.3.		Update the road map if necessary
		4.1.4.		Spell check the release notes in word

	4.2.			Prepare package directory		00:10		17:00
		4.2.1.		Add a new directory to the offline archive "\YAT\Releases and Checkpoints"
		4.2.2.		Check and update year of "!-ReadMe.txt" in the release package directories
		4.2.3.		Copy the release notes to all package directories
		4.2.4.		Also copy them to the distribution root and rename to "YAT Release Notes - ReadMe.txt"
				> SourceForge requires the file to contain 'readme' in the name

				Note: The distribution packages will be packed in a further step

	4.3.			Build packages		00:20		17:20
		4.3.1.		Check "YAT.Setup.x86|x64" prerequisites for "Setup"
				> Optimize for speed
		4.3.2.		Check "YAT.Setup.x86|x64" prerequisites for "Setup with Prerequisites"
				> Optimize for size
		4.3.3.		Build > Batch Build > Clean ALL configuration for ALL target platforms
				> Reduces the risk of mistakenly taking the wrong assemblies
				> Check the intermediate folders of "\YAT\YAT\bin"
		4.3.4.		Build "x86"
				> Build "Release" configuration for "x86"
				> Build "Setup" configuration for "x86"
				> Build "Setup with Prerequisites" configuration for "x86"
		4.3.5.		Build "AnyCPU" (reason see FR#229)
				> Build "Release" configuration for "AnyCPU"
				> Build "Setup" configuration for "AnyCPU"
				> Build "Setup with Prerequisites" configuration for "AnyCPU"

## 5. Installation Testing
				Duration	Step		Total

5.				Installation Testing		00:00	00:40	17:20	17:55

	5.1.			Preparation		00:05		17:25
		5.1.1.		Close Visual Studio
				> Needed to ensure that YAT doesn't detect already running "YAT.vshost.exe" on startup
		5.1.2.		Ensure that previous Local User Settings are available
				> Use previous installed version and create one or two terminals
		5.1.3.		Ensure that current Local User Settings deleted

	5.2.			Installation		00:05		17:30
		5.2.1.		Install YAT

	5.3.			Run manual after-installation tests		00:30		17:55
		5.3.1.		Run according to manual after-installation test cases

## 6. Packaging
				Duration	Step		Total

6.				Packaging		00:00	00:30	17:55	18:25

	6.1.			Commit and tag YAT		00:15		18:10
		6.1.1.		Commit any modifications to the subversion repository
		6.1.2.		Tag/checkpoint the project
				> SVN > Repo-browser
				> Select 'trunk' in tree-view
				> Copy to...
				> New name e.g. "<...>/tags/yat-1-99-80-delta"
				> Message e.g. "YAT 2.0 Delta Version 1.99.80"
				> Unfold 'tags'
				> Check new tag
		6.1.3.		Fill SVN revision into 'The YAT story' in '0. Overview'

	6.2.			Pack YAT		00:15		18:25
		6.2.1.		Update the 6 folders in "<Offline\Releases>\Distribution"
				> Copy packages from "Setup" projects
				> Copy binaries from "YAT" project
				> Copy "YATConsole.exe" from that project
				> Copy info folders from installed "C:\Program Files\YAT"
		6.2.2.		Create the 6 according distribution files
				> "YAT-2.0_Delta_Version-1.99.80_x64_(64-bit).zip"
				> "YAT-2.0_Delta_Version-1.99.80_x64_(64-bit)_with_.NET_runtime.zip"
				> "YAT-2.0_Delta_Version-1.99.80_x86_(32-bit).zip"
				> "YAT-2.0_Delta_Version-1.99.80_x86_(32-bit)_with_.NET_runtime.zip"
				> "YAT-2.0_Delta_Version-1.99.80_x64_(64-bit)_binaries_only.zip"
				> "YAT-2.0_Delta_Version-1.99.80_x86_(32-bit)_binaries_only.zip"
		6.2.3.		Compare size of packages against last release (plausibility check)

				Note:
				Bugs #318 and #323 suggested to only distribute .msi for easier use.
				However, IE10+ by default does not allow to download (SHA1) .msi !!!
				New FR#274 “Find a way to distribute as .msi only” created

## 7. Upload
				Duration	Step		Total

7.				Upload		00:00	01:20	17:55	19:15

	7.1.			Update statistics		00:20		18:15
		7.1.1.		Update "\YAT\!-Doc.SourceForge\"

	7.2.			Prepare upload		00:10		18:25
		7.2.1.		Log in as 'y-a-terminal'
		7.2.2.		Go to 'SourceForge > YAT > Files'
		7.2.3.		Add archive folder (e.g. "Version 1.99.80 - YAT 2.0 Delta)
		7.2.4.		Move current to archive using FileZilla
				> sftp://frs.sourceforge.net | y-a-terminal | PW+OTP | 22
				> /home/pfs/project/y-a-terminal
				> Use tree view to open the intended archive folder
				> Then drag and drop files (incl. RelNotes) to that folder
				> Don't care about '+' symbol, files will get moved anyway
		7.2.5.		Exclude archived RelNotes from statistics

	7.3.			Add release		00:30		18:55
		7.3.1.		Upload distributions using the web interface
				> Manually upload for proper sequence !!!
				> Intended order: RelNotes – x86 bin – x64 bin – x86.NET – x86 – x64.NET – x64
				> Upload takes approx. 20 minutes (for ~460 MB)
		7.3.2.		Tick default platform download on normal x64 distribution
		7.3.3.		Also replace RelNotes in archive main folder
		7.3.4.		Check that both RelNotes are excluded from statistics

	7.4.			Check release and release notes		00:10		19:05
		7.4.1.		Reload YAT web page
				> It takes a moment until the uploaded files are ready for download
		7.4.2.		Download all files with Firefox
		7.4.3.		Download all files with Internet Explorer
				> Verifies digital signature issues…
		7.4.4.		Verify contents of .msi / .zip
				> At least open the ReadMe or RelNotes

	7.5.			Feature request and bug trackers		00:10		19:15
		7.5.1.		Check that items that are covered by this release have been closed

## 8. Finalization
				Duration	Step		Total

8.				Finalization		00:00	03:30	19:15	22:15

	8.1.			Submit news		00:15		19:30
		8.1.1.		Go to 'Develop > News'
		8.1.2.		Add news
				Title:
				"YAT 2.0 Gamma 1 Version 1.99.32"
				Text:
				"<Intro of release mail>"

	8.2.			Send e-mail to the YAT mailing list (Attention: Mail delay up to 60 min !!!)		00:15		19:45
		8.2.1.		Write e-mail based on earlier mailings
				> Make sure that links are updated completely, i.e. link text and link itself
				> Make sure the correct release notes are used
		8.2.2.		Check spelling
		8.2.3.		Send as "y-a-terminal@users.sourceforge.net"
		8.2.4.		Send to "y-a-terminal-users@lists.sourceforge.net"
		8.2.5.		Send encoded in Unicode
				> Thunderbird: Options > Encoding > Unicode
		8.2.6.		Send as Text+HTML
				> Thunderbird: Options > Format > Text+HTML
		8.2.7.		Save e-mail in offline archive "\Distribution"
		8.2.8.		Accept e-mail as moderator in mailman
				> May take up to 60 min until possible
				> Mail may also be delayed up to 60 min

	8.3.			Cleanup		00:15		20:00
		8.3.1.		Log out from SourceForge as 'y-a-terminal' and log in as 'maettu_this' again
		8.3.2.		Send thanks mails
				> People who are waiting for release / had dropbox access / gave feedback (YAT, MT, HFU,…)
		8.3.3.		Remove preliminiaries from dropbox
				> Also send mail to MT to do the same there
		8.3.4.		Remove people from dropbox
		8.3.5.		Commit any modifications during the release process to the subversion repository

	8.4.			Upgrade tools		01:00		20:45
		8.4.1.		Check for updates of Visual Studio and extensions
				> In case of update, install everything including extensions
		8.4.2.		Check for updates of all "\Tools\! - Tools and Versions.txt"
		8.4.3.		Also check for updates of TortoiseGIT

	8.5.			Recreate and verify working copy		00:15		20:15
		8.5.1.		Rename the existing working copy to "Trunk_<New Date>" (e.g. _2013-02-02)
		8.5.2.		Remove existing backups "Trunk_<Old Date>"
		8.5.3.		Create a new folder "Trunk"
		8.5.4.		Check the head revision out into "Trunk"
				> Make sure that only "...\code\trunk\" is checked out, not the whole repository
		8.5.5.		Open the YAT solution
		8.5.6.		Fold all projects
		8.5.7.		Set 'YAT.Test' as the active startup project
		8.5.8.		Build 'Debug Test' to ensure that all files got committed from former working copy
		8.5.9.		If VS/VSI got upgraded, build 'Setup with Prerequisites' to ensure that VSI
				> Set 'YAT' as the active startup configuration
				> Build 'Setup with Prerequisites' to ensure that VSI properly builds
		8.5.10.		Set 'YAT' as the active startup project
		8.5.11.		Set 'Debug' as the active solution configuration

	8.6.			Archive		00:15		21:00
		8.6.1.		Export the new working copy to a temporary folder (e.g. "D:\Temp\YAT")
				> Use 'SVN > Export...'
		8.6.2.		Pack the copy into a properly named zip
		8.6.3.		Move the zip to offline archive "<Version>\Working Copy"

	8.7.			Backup		01:00		22:00
		8.7.1.		Commit any modifications during the upgrade/recreate process to the subversion repository
		8.7.2.		Manually backup onto offline disk
				> Backup onto NAS is done automatically

	8.8.			Update and verify working copy (wait for a few days in case of a severe issue)		00:15		22:15
		8.8.1.		Increment product version in ALAZ.Version
		8.8.2.		Increment product version in netrtfwriter AssemblyInfo
				> All versions must be incremented to ensure proper installation/update!
		8.8.3.		Increment product version in MKY.Version
		8.8.4.		Set product version in MKY file headers throughout "<Workspace>\Trunk"
				> Add 'Development', e.g. '// MKY Development Version 1.0.14'
		8.8.5.		Increment product version in netrtfwriter\RtfWriter\Properties\AssemblyInfo.cs
		8.8.6.		Increment product version in NUnit.Version
		8.8.7.		Set product version in NUnit file headers throughout "<Workspace>\Trunk"
				> Add 'Development', e.g. '// NUnit Development Version 1.0.11'
		8.8.8.		Increment product version in YAT.Version
		8.8.9.		Set product version in YAT file headers throughout "<Workspace>\Trunk"
				> Add 'Development', e.g. '// YAT 2.0 Gamma 2 Development Version 1.99.35'
		8.8.10.		Set product name post fix in "YAT.Application.ApplicationEx"
				> Add 'Development' to clearly state that files are non-released revisions
		8.8.11.		Add a new section to the release notes
				> Copy limitations and known issues from last release
		8.8.12.		Verify that the solution still properly builds and runs