## 0. Overview
A YAT release is done in 8 steps:
				Duration	Step	Total
		1.	Regression Testing		07:00	07:00
		2.	Preparation		01:55	08:55
		3.	Final Testing		04:35	13:30
		4.	Build		00:30	14:00
		5.	Installation Testing		00:30	14:30
		6.	Packaging		00:30	14:30
		7.	Upload		00:50	15:20
		8.	Finalization		02:05	17:10

The YAT story:
					YAT	MKY	ALAZ	NUnit		LU.xml	.yat	.yaw		SVN
	2013-01-04	:	YAT 2.0 Beta 4 Candidate 2				1.99.30	1.0.9	3.5.7	1.0.6		1.3.1	1.3.1	1.1.1		?
	2011-12-05	:	YAT 2.0 Beta 4 Candidate 1				1.99.28	1.0.7	3.5.5	1.0.4		1.3.0	1.3.0	1.1.0		502
	2011-04-25	:	YAT 2.0 Beta 3 Candidate 4				1.99.26	1.0.5	3.5.3	1.0.2		1.2.4	1.2.9	1.0.0		419
	2010-11-28	:	YAT 2.0 Beta 3 Candidate 3				1.99.25	1.0.4	3.5.2	1.0.1		1.2.4	1.2.9	1.0.0		385
	2010-11-11	:	YAT 2.0 Beta 3 Candidate 2				1.99.24	1.0.4	3.5.2	1.0.1		1.2.4	1.2.8	1.0.0		369
	2009-09-10	:	YAT 2.0 Beta 3 Candidate 1				1.99.23	1.0.1	3.5.0			1.2.4	1.2.7	1.0.0		251
	2009-09-08	:	YAT 2.0 Beta 3 Candidate 1				1.99.22	1.0.1	3.5.0			1.2.3	1.2.6	1.0.0		247
	2008-07-18	:	YAT 2.0 Beta 2 Candidate 4				1.99.20	1.0.0	1.2.0			1.2.3	1.2.5	1.0.0		201
	2008-04-01	:	YAT 2.0 Beta 2 Candidate 3				1.99.19					1.2.2	1.2.4	1.0.0		136
	2008-03-17	:	YAT 2.0 Beta 2 Candidate 2				1.99.18					1.2.2	1.2.3	1.0.0		122
	2008-02-11	:	YAT 2.0 Beta 2 Candidate 1				1.99.17					1.2.2	1.2.2	1.0.0		105
	2007-08-30	:	YAT 2.0 Beta 2 Preliminary				1.99.13					1.2.1	1.2.1	1.0.0		(45)
	2007-04-15	:	YAT 2.0 Beta 1				1.99.12					1.2.0	1.2.0			9
	2007-02-25	:	YAT 2.0 Alpha 3				1.99.8					1.1.2	1.1.2
	2007-02-07	:	YAT 2.0 Alpha 2				1.99.3					1.1.1	1.1.1
	2007-01-23	:	YAT 2.0 Alpha 1				1.99.0					1.1.0	1.1.0
	2003-10-31	:	XTerm232				1.0.2					1.0.1	1.0.1
	2003-10-30	:	XTerm232				1.0.1					1.0.1	1.0.1
	2003-10-14	:	XTerm232				1.0.0					1.0.0	1.0.0

## 1. Regression Testing
				Duration	Step		Total

1.				Regression Testing		00:00	07:00	00:00	07:00

	1.1.			Run coding style checks		00:30		00:30
		1.1.1.		Use StyleCop on 'Debug Test'
				> "Visual Studio > Tools > Run StyleCop (Rescan All)"

				2 expected warnings:
				SA1203 : CSharp.Ordering @ YAT.Model.Settings.SendCommandSettings.cs
				SA1409 : CSharp.Maintainability @ YAT.Model.Terminal.cs

				Note: Rescan takes less than a minute, but expect some time for fixes

	1.2.			Run assembly checks		00:30		01:00
		1.2.1.		Use FxCop 'MKY.Debug' on 'Debug Test'
				> Open and verify "\MKY\MKY.Debug.FxCop"

				50 expected warnings:
				CA1805 : DoNotInitializeUnnecessarily @ 4 locations
				CA1811 : AvoidUncalledPrivateCode @ 4 locations
				CA2213 : DisposableFieldsShouldBeDisposed @ 16 locations
				CA2214 : DoNotCallOverridableMethodsInConstructors @ 26 locations

		1.2.2.		Use FxCop 'Nunit.Debug' on 'Debug Test'
				> Open and verify "\Nunit\NUnit.Debug.FxCop"
		1.2.3.		Use FxCop 'YAT.Debug' on 'Debug Test'
				> Open and verify "\YAT\YAT.Debug.FxCop"

				153 expected errors/warnings:
				CA1002 : DoNotExposeGenericLists @ 36 locations
				CA1044 : PropertiesShouldNotBeWriteOnly @ 17 locations
				CA1601 : DoNotUseTimersThatPreventPowerStateChanges @ 2 locations
				CA1804 : RemoveUnusedLocals @ 1 location
				CA1819 : PropertiesShouldNotReturnArrays @ 1 location
				CA2214 : DoNotCallOverridableMethodsInConstructors @ 96 locations

				Note: Rescan takes less than a minute, but expect some time for fixes

	1.3.			Run automated tests		06:00		07:00
		1.3.1.		Configure NUnit test categories
				> "Visual Studio > Tools > NUnit"
				> "Categories = Select and exclude 10'/60'/infinite/interactive"
		1.3.2.		Use NUnit on 'Debug Test'
				> "Visual Studio > Tools > NUnit"
				> "Project > Configurations > Debug"
		1.3.3.		Use NUnit on 'Release Test'
				> "Visual Studio > Tools > NUnit"
				> "Project > Configurations > Release"

				12 expected errors each:
				YAT.Model.Test.OneWayTransmissionTest::ClearCommand @ Ipv4/IPv6
				YAT.Settings.Test.FileVersionsTest::TC1/2 @ 1.99.13/17/18/19

				Note: Run takes around 10 minutes, but expect quite some time for fixes

## 2. Preparation
				Duration	Step		Total

2.				Preparation		00:00	01:55	07:00	08:55

	2.1.			Set versions		00:20		07:20
		2.1.1.		Increment product version in ALAZ.Version
		2.1.2.		Increment product version in MKY.Version
		2.1.3.		Increment product version in NUnit.Version
		2.1.4.		Increment product version in YAT.Version
		2.1.5.		Set product name post fix in "YAT.Utilities.ApplicationInfo"
				> Remove 'Development'
		2.1.6.		Set product version in MKY file headers
				> Also remove 'Development', e.g. '// MKY Version 1.0.9'
		2.1.7.		Set product version in NUnit file headers
				> Also remove 'Development', e.g. '// NUnit Version 1.0.6'
		2.1.8.		Set product version in YAT file headers
				> Also remove 'Development', e.g. '// YAT 2.0 Beta 4 Candidate 1 Version 1.99.30'
		2.1.9.		Fill date and versions into 'The YAT story' in '0. Overview'

	2.2.			Set installation version		00:05		07:25
		2.2.1.		Set product title in "YAT.Setup"
		2.2.2.		Set product version in "YAT.Setup"

	2.3.			Update settings defaults and schema in "YAT\!-Settings\!-Current"		00:30		07:55
		2.3.1.		Create files using NUnit on 'Debug Test'
				> "Visual Studio > Tools > NUnit"
				> YAT.Settings.Test.SettingsFilesArchiver
		2.3.2.		Diff and verify the files in "YAT\!-Settings\!-Current"
		2.3.3.		Fill settings versions into 'The YAT story' in '0. Overview'

	2.4.			Upgrade settings in settings archive "YAT\!-Settings\!-Current"		00:30		08:25
		2.4.1.		Upgrade settings
				> Run YAT and open old settings
				> Modify settings (use 'View > Show …' to ensure that IO settings are kept)
				> Undo changes
				> Save upgraded but unchanged settings
		2.4.2.		Diff and verify the new settings

	2.5.			Add new settings to settings archive		00:15		08:40
		2.5.1.		Archive the upgraded files in "YAT\!-Settings\<New Version>"
		2.5.2.		Add new settings to "YAT.Settings.Test.SettingsFilesProvider"
		2.5.3.		Add new settings to "YAT.Settings.Test.FileVersionsTest"

	2.6.			Rebuild and commit		00:15		08:55
		2.6.1.		Rebuild 'Debug'
		2.6.2.		Rebuild 'Debug Test'
		2.6.3.		Rebuild 'Release Test'
		2.6.4.		Commit changes to SVN

## 3. Final Testing
				Duration	Step		Total

3.				Final Testing		00:00	04:35	08:55	13:30

	3.1.			Re-Run coding style checks		00:10		09:05
		3.1.1.		Use StyleCop on 'Debug Test'
				> "Visual Studio > Tools > Run StyleCop (Rescan All)"

				2 expected warnings:
				SA1203 : CSharp.Ordering @ YAT.Model.Settings.SendCommandSettings.cs
				SA1409 : CSharp.Maintainability @ YAT.Model.Terminal.cs

				Note: Rescan takes less than a minute, and there should be no more findings

	3.2.			Re-Run assembly checks		00:10		09:15
		3.2.1.		Use FxCop 'MKY.Debug' on 'Debug Test'
				> Open and verify "\MKY\MKY.Debug.FxCop"

				50 expected warnings:
				CA1805 : DoNotInitializeUnnecessarily @ 4 locations
				CA1811 : AvoidUncalledPrivateCode @ 4 locations
				CA2213 : DisposableFieldsShouldBeDisposed @ 16 locations
				CA2214 : DoNotCallOverridableMethodsInConstructors @ 26 locations

		3.2.2.		Use FxCop 'Nunit.Debug' on 'Debug Test'
				> Open and verify "\Nunit\NUnit.Debug.FxCop"
		3.2.3.		Use FxCop 'YAT.Debug' on 'Debug Test'
				> Open and verify "\YAT\YAT.Debug.FxCop"

				153 expected errors/warnings:
				CA1002 : DoNotExposeGenericLists @ 36 locations
				CA1044 : PropertiesShouldNotBeWriteOnly @ 17 locations
				CA1601 : DoNotUseTimersThatPreventPowerStateChanges @ 2 locations
				CA1804 : RemoveUnusedLocals @ 1 location
				CA1819 : PropertiesShouldNotReturnArrays @ 1 location
				CA2214 : DoNotCallOverridableMethodsInConstructors @ 96 locations

				Note: Rescan takes less than a minute, and there should be no more findings

	3.3.			Run automated tests		00:30		09:45
		3.3.1.		Configure NUnit test categories
				> "Visual Studio > Tools > NUnit"
				> "Categories = Select and exclude 10'/60'/infinite/interactive"
		3.3.2.		Use NUnit on 'Debug Test'
				> "Visual Studio > Tools > NUnit"
				> "Project > Configurations > Debug"
		3.3.3.		Use NUnit on 'Release Test'
				> "Visual Studio > Tools > NUnit"
				> "Project > Configurations > Release"

				12 expected errors each:
				YAT.Model.Test.OneWayTransmissionTest::ClearCommand @ Ipv4/IPv6
				YAT.Settings.Test.FileVersionsTest::TC1/2 @ 1.99.13/17/18/19

				Note: Run takes around 10 minutes, and there should be no more findings

	3.4.			Disconnect all devices, restart computer, re-run automated tests		00:50		10:35
		3.4.1.		Re-run 3.3.2. above
		3.4.2.		Re-run 3.3.3. above
		3.4.3.		Reconnect devices

	3.5.			Run interactive tests		00:10		10:45
		3.5.1.		Configure NUnit test categories
				> "Visual Studio > Tools > NUnit"
				> "Categories = Select and include interactive only"
		3.5.2.		Use NUnit on 'Debug Test'
				> "Visual Studio > Tools > NUnit"
				> "Project > Configurations > Debug"
		3.5.3.		Use NUnit on 'Release Test'
				> "Visual Studio > Tools > NUnit"
				> "Project > Configurations > Release"

	3.6.			Run manual tests		02:30		13:15
		3.6.1.		According to manual test cases in "\YAT\_Doc.Project\5 - Test\YAT - Test.ods"

	3.7.			Re-run automated tests and commit		00:15		13:30
		3.7.1.		Use NUnit on 'Release Test' to ensure that modifications didn't re-introduce any bugs
		3.7.2.		Commit changes to SVN

## 4. Build
				Duration	Step		Total

4.				Build		00:00	00:30	13:30	14:00

	4.1.			Write release notes		00:00		13:30
		4.1.1.		Add them cumulatively to "\!-Doc.User\YAT Release Notes.txt"

	4.2.			Prepare package directory		00:10		13:40
		4.2.1.		Add a new directory to the offline archive "\YAT\Releases and Checkpoints"
		4.2.2.		Check and update year of "!-ReadMe.txt" in the release package directories
		4.2.3.		Add the release notes to the release package directories
		4.2.4.		Copy and rename the release notes to "YAT Release Notes - ReadMe.txt"
				> SourceForge requires the file to contain 'readme' in the name

				Note: The distribution packages will be packed in a further step

	4.3.			Re-Build YAT		00:20		14:00
		4.3.1.		Check "YAT.Setup" prerequisites for "Release"
				> Optimize for speed
		4.3.2.		Check "YAT.Setup" prerequisites for "Release with Prerequisites"
				> Optimize for size
		4.3.3.		Re-Build "Release" configuration
				> Re-build to ensure that all assemblies have the same time stamp
		4.3.4.		Build "Release with Prerequisites" configuration
				> No need to re-build since re-build has just been done

## 5. Installation Testing
				Duration	Step		Total

5.				Installation Testing		00:00	00:30	14:00	14:30

	5.1.			Installation		00:10		14:10
		5.1.1.		Close Visual Studio
				> Needed to ensure that YAT doesn't detect already running "YAT.vshost.exe" on startup
		5.1.2.		Install YAT

	5.2.			Run manual after-installation tests		00:20		14:30
		5.2.1.		Run according to manual after-installation test cases

## 6. Packaging
				Duration	Step		Total

6.				Packaging		00:00	00:35	14:30	15:05

	6.1.			Feature request and bug trackers		00:05		14:35
		6.1.1.		Check that items that are covered by this release have been closed

	6.2.			Commit and tag YAT		00:15		14:50
		6.2.1.		Commit any modifications to the subversion repository
				> Message e.g. "YAT 2.0 Beta 3 Candidate 3 Version 1.99.25"
		6.2.2.		Tag/checkpoint the project
				> SVN > Repo Browser
				> Select 'trunk'
				> Copy to...
				> New name e.g. "<...>/tags/yat-1-99-25-beta-3-candidate-3"
				> Message e.g. "YAT 2.0 Beta 3 Candidate 3 Version 1.99.25"
				> Select 'tags'
				> Check tag
		6.2.3.		Fill SVN revision into 'The YAT story' in '0. Overview'

	6.3.			Pack YAT		00:15		15:05
		6.3.1.		Update "\Distribution\Release"
		6.3.2.		Update "\Distribution\Release With Prerequisites"
		6.3.3.		Create the two according .zip files

## 7. Upload
				Duration	Step		Total

7.				Upload		00:00	00:50	14:30	15:20

	7.1.			Prepare upload to SourceForge		00:10		14:40
		7.1.1.		Log in as 'y-a-terminal'
		7.1.2.		Go to 'SourceForge > Files'
		7.1.3.		Add release folder (e.g. "Version 1.99.25 - YAT 2.0 Beta 3 Candidate 3")

				HowTo:
				<https://sourceforge.net/apps/trac/sourceforge/wiki/Release%20files%20for%20download>

	7.2.			Add release		00:30		15:10
		7.2.1.		Upload distributions using the web interface
				> 'Release' takes approx. 2 minutes (for 6 MB)
				> 'Release With Prerequisites' takes approx. 60 minutes (for 200 MB)
		7.2.2.		Tick default platform download on normal distribution
		7.2.3.		Copy and rename the release notes to "YAT Release Notes - ReadMe.txt"
				> SourceForge requires the file to contain 'readme' in the name
		7.2.4.		Upload release notes to the release folder
		7.2.5.		Upload release notes to the parent folder
		7.2.6.		Upload release notes to the main folder

	7.3.			Check release and release notes		00:10		15:20
		7.3.1.		Reload YAT web page
		7.3.2.		Download release and verify contents of .zip
		7.3.3.		Take a look at the release notes

## 8. Finalization
				Duration	Step		Total

8.				Finalization		00:00	02:05	15:20	17:10

	8.1.			Submit news		00:15		15:35
		8.1.1.		Go to 'Develop > News'
		8.1.2.		Add news
				Title:
				"YAT 2.0 Beta 4 Candidate 1 Version 1.99.28"
				Text:
				"This year the 'Samichlaus' is adding a new version of YAT to the piles of peanuts and tangerines! 'YAT 2.0 Beta 4 Candidate 1 Version 1.99.28' has just been released in time for December 6th. / This release adds quite some features to YAT, and a bunch of issues has been fixed. The most noticeable new features are related to serial COM ports as well as command line arguments in order to prepare automated and scripted use of YAT. See the release notes for details on new features, important changes, fixed bugs and known limitations. / The next release is anticipated for H1/2012 and will fix another bunch of issues and again a few new features. Slowly but steadily the number of open issues is decreasing. Once all major issues have been fixed, it will finally be time for 'YAT 2.0 Final'. The effective release time frame for 'YAT 2.0 Final' has not yet been defined and will be dependent on your feedback."

				HowTo:
				<https://sourceforge.net/apps/trac/sourceforge/wiki/News>

	8.2.			Send e-mail to the YAT mailing list		00:15		15:50
		8.2.1.		Check/update mailing list
		8.2.2.		Write e-mail based on earlier mailings
				> Make sure that links are updated completely, i.e. link text and link below
		8.2.3.		Send as "y-a-terminal@users.sourceforge.net"
		8.2.4.		Send to "y-a-terminal-users@lists.sourceforge.net"
		8.2.5.		Send as text and HTML formatted
				> It takes up to an hour until the mail is sent
		8.2.6.		Save e-mail in offline archive "\Distribution"
		8.2.7.		Accept e-mail as moderator in mailman if needed

	8.3.			Commit YAT		00:05		15:55
		8.3.1.		Commit any modifications during the release process to the subversion repository

	8.4.			Recreate YAT working copy		00:15		16:10
		8.4.1.		Rename the existing working copy to "Trunk_<New Date>" (e.g. _2011-12-05)
		8.4.2.		Remove existing backups "Trunk_<Old Date>"
		8.4.3.		Check for updates of TortoiseSVN and AnkhSVN
		8.4.4.		Create a new folder "Trunk"
		8.4.5.		Check the head revision out into "Trunk"

	8.5.			Archive YAT		00:15		16:25
		8.5.1.		Export the new working copy to offline archive "<Version>\Working Copy"
				> Use 'SVN > Export...'
		8.5.2.		Pack the copy into a properly named zip file

	8.6.			Update and verify YAT working copy		00:15		16:40
		8.6.1.		Open the YAT solution
		8.6.2.		Fold all projects
		8.6.3.		Set 'YAT' as the active startup project
		8.6.4.		Increment product version in ALAZ.Version
		8.6.5.		Increment product version in MKY.Version
		8.6.6.		Increment product version in NUnit.Version
		8.6.7.		Increment product version in YAT.Version
		8.6.8.		Set product name post fix in "YAT.Utilities.ApplicationInfo"
				> Add 'Development' to clearly state that files are non-released revisions
		8.6.9.		Set product version in MKY file headers
				> Add 'Development', e.g. '// MKY Development Version 1.0.7'
		8.6.10.		Set product version in NUnit file headers
				> Add 'Development', e.g. '// NUnit Development Version 1.0.4'
		8.6.11.		Set product version in YAT file headers
				> Add 'Development', e.g. '// YAT 2.0 Beta 4 Candidate 1 Development Version 1.99.28'
		8.6.12.		Add a new section to the release notes
		8.6.13.		Verify that the solution still properly builds and runs
		8.6.14.		Commit modifications to the subversion repository

	8.7.			Update statistics		00:15		16:55
		8.7.1.		Update "\YAT\!-Doc.SourceForge\"

	8.8.			Backup PC		00:30		17:10
		8.8.1.		Offline archive
		8.8.2.		Sandboxes