## 0. Overview
A YAT release is done in 6 steps:
				Duration	Step	Total
		1.	Preparation		01:25	01:25
		2.	Software Testing		05:10	06:35
		3.	Packaging		01:25	08:00
		4.	Installation Testing		01:25	09:25
		5.	Upload		01:25	10:50
		6.	Finalization		01:25	12:15

The YAT story:
					YAT	MKY	ALAZ	NUnit
	2011-12-05	:	YAT 2.0 Beta 4 Candidate 1				1.99.28	1.0.7	3.5.5	1.0.4
	2011-04-25	:	YAT 2.0 Beta 3 Candidate 4				1.99.26	1.0.5	3.5.3	1.0.2
	2010-11-28	:	YAT 2.0 Beta 3 Candidate 3				1.99.25	1.0.4	3.5.2	1.0.1
	2010-11-11	:	YAT 2.0 Beta 3 Candidate 2				1.99.24	1.0.4	3.5.2	1.0.1
	2009-09-10	:	YAT 2.0 Beta 3 Candidate 1				1.99.23	1.0.1	3.5.0
	2009-09-08	:	YAT 2.0 Beta 3 Candidate 1				1.99.22	1.0.1	3.5.0
	2008-07-18	:	YAT 2.0 Beta 2 Candidate 4				1.99.20	1.0.0	1.2.0
	2008-04-01	:	YAT 2.0 Beta 2 Candidate 3				1.99.19
	2008-03-17	:	YAT 2.0 Beta 2 Candidate 2				1.99.18
	2008-02-11	:	YAT 2.0 Beta 2 Candidate 1				1.99.17
	2007-08-30	:	YAT 2.0 Beta 2 Preliminary				1.99.13
	2007-04-15	:	YAT 2.0 Beta 1				1.99.12
	2007-02-25	:	YAT 2.0 Alpha 3				1.99.8
	2007-02-07	:	YAT 2.0 Alpha 2				1.99.3
	2007-01-23	:	YAT 2.0 Alpha 1				1.99.0
	2003-10-31	:	XTerm232				1.0.2
	2003-10-30	:	XTerm232				1.0.1
	2003-10-14	:	XTerm232				1.0.0

## 1. Preparation
				Duration	Step		Total

1.				Preparation		00:00	01:25	00:00	01:25

	1.1.			Set versions		00:20		00:20
		1.1.1.		Increment product version in ALAZ.Version
		1.1.2.		Increment product version in MKY.Version
		1.1.3.		Increment product version in NUnit.Version
		1.1.4.		Increment product version in YAT.Version
		1.1.5.		Set product name post fix in "YAT.Utilities.ApplicationInfo"
		1.1.6.		Set product version in MKY file headers
				> Remove 'Development', e.g. '// MKY Version 1.0.7'
		1.1.7.		Set product version in NUnit file headers
				> Remove 'Development', e.g. '// NUnit Version 1.0.4'
		1.1.8.		Set product version in YAT file headers
				> Remove 'Development', e.g. '// YAT 2.0 Beta 4 Candidate 1 Version 1.99.28'
		1.1.9.		Fill date and versions into 'The YAT story' in '0. Overview'

	1.2.			Set installation version		00:05		00:25
		1.2.1.		Set product title in "YAT.Setup"
		1.2.2.		Set product version in "YAT.Setup"

	1.3.			Add new settings to settings archive		00:15		00:40
		1.3.1.		Clone settings set to "YAT\!-Settings\<New Version>"
		1.3.2.		Add new settings to "YAT.Settings.Test.SettingsFilesProvider"
		1.3.3.		Add new settings to "YAT.Settings.Test.FileVersionsTest"

	1.4.			Rebuild		00:15		00:55
		1.4.1.		Rebuild 'Debug'
		1.4.2.		Rebuild 'Debug Test'
		1.4.3.		Rebuild 'Release Test'

	1.5.			Upgrade settings in settings archive		00:30		01:25
		1.5.1.		Commit changes to SVN to prepare diff
		1.5.2.		Upgrade settings
				> Run YAT and open old settings
				> Modify settings (use 'View > Show …' to ensure that IO settings are kept)
				> Undo changes
				> Save upgraded but unchanged settings
		1.5.3.		Diff and verify the new settings
		1.5.4.		Commit changes to SVN

## 2. Software Testing
				Duration	Step		Total

2.				Software Testing		00:00	05:10	01:25	06:35

	2.1.			Run coding style checks		00:30		01:55
		2.1.1.		Use StyleCop on 'Debug'
				> "Visual Studio > Tools > Run StyleCop (Rescan All)"
		2.1.2.		Use StyleCop on 'Debug Test'
				> "Visual Studio > Tools > Run StyleCop (Rescan All)"

				Note: Rescan takes less than a minute, but expect some time to fix errors/warnings/messages

	2.2.			Run assembly checks		00:30		02:25
		2.2.1.		Use FxCop 'MKY.Debug' on 'Debug Test'
				> Open and verify "\MKY\MKY.Debug.FxCop"
		2.2.2.		Use FxCop 'YAT.Debug' on 'Debug Test'
				> Open and verify "\YAT\YAT.Debug.FxCop"

				Note: Rescan takes less than a minute, but expect some time to fix errors/warnings/messages

	2.3.			Run automated tests		02:00		04:25
		2.3.1.		Configure NUnit test categories
				> "Visual Studio > Tools > NUnit"
				> "Categories = Exclude 1'/10'/60'/infinite/endurance/interactive/stress"
		2.3.2.		Use NUnit on 'Debug Test'
				> "Visual Studio > Tools > NUnit"
				> "Project > Configurations > Debug"
		2.3.3.		Use NUnit on 'Release Test'
				> "Visual Studio > Tools > NUnit"
				> "Project > Configurations > Release"

				Note: Run takes around 10 minutes, but expect quite some time for fixes

	2.4.			Disconnect all devices, restart laptop, re-run automated tests		00:30		04:55
		2.4.1.		Re-run 2.3.1. above
		2.4.2.		Re-run 2.3.2. above
		2.4.3.		Re-run 2.3.3. above
		2.4.4.		Reconnect devices

	2.5.			Run interactive tests		00:10		05:05
		2.5.1.		Configure NUnit test categories
				> "Visual Studio > Tools > NUnit"
				> "Categories = Include interactive only"
		2.5.2.		Use NUnit on 'Debug Test'
				> "Visual Studio > Tools > NUnit"
				> "Project > Configurations > Debug"
		2.5.3.		Use NUnit on 'Release Test'
				> "Visual Studio > Tools > NUnit"
				> "Project > Configurations > Release"

	2.6.			Run manual tests		01:30		06:35
		2.6.1.		According to manual test cases in "\YAT\_Doc.Project\5 - Test\YAT - Test.ods"

## 3. Packaging
				Duration	Step		Total

3.				Packaging		00:00	01:25	06:35	08:00

	3.1.			Set versions		00:20		06:55
		3.1.1.		Increment product version in ALAZ.Version
		3.1.2.		Increment product version in MKY.Version
		3.1.3.		Increment product version in NUnit.Version
		3.1.4.		Increment product version in YAT.Version
		3.1.5.		Set product name post fix in "YAT.Utilities.ApplicationInfo"
		3.1.6.		Set product version in MKY file headers
				> Remove 'Development', e.g. '// MKY Version 1.0.7'
		3.1.7.		Set product version in NUnit file headers
				> Remove 'Development', e.g. '// NUnit Version 1.0.4'
		3.1.8.		Set product version in YAT file headers
				> Remove 'Development', e.g. '// YAT 2.0 Beta 4 Candidate 1 Version 1.99.28'
		3.1.9.		Fill date and versions into 'The YAT story' in '0. Overview'

	3.2.			Set installation version		00:05		07:00
		3.2.1.		Set product title in "YAT.Setup"
		3.2.2.		Set product version in "YAT.Setup"

	3.3.			Add new settings to settings archive		00:15		07:15
		3.3.1.		Clone settings set to "YAT\!-Settings\<New Version>"
		3.3.2.		Add new settings to "YAT.Settings.Test.SettingsFilesProvider"
		3.3.3.		Add new settings to "YAT.Settings.Test.FileVersionsTest"

	3.4.			Rebuild		00:15		07:30
		3.4.1.		Rebuild 'Debug'
		3.4.2.		Rebuild 'Debug Test'
		3.4.3.		Rebuild 'Release Test'

	3.5.			Upgrade settings in settings archive		00:30		08:00
		3.5.1.		Commit changes to SVN to prepare diff
		3.5.2.		Upgrade settings
				> Run YAT and open old settings
				> Modify settings (use 'View > Show …' to ensure that IO settings are kept)
				> Undo changes
				> Save upgraded but unchanged settings
		3.5.3.		Diff and verify the new settings
		3.5.4.		Commit changes to SVN

## 4. Installation Testing
				Duration	Step		Total

4.				Installation Testing		00:00	01:25	08:00	09:25

	4.1.			Set versions		00:20		08:20
		4.1.1.		Increment product version in ALAZ.Version
		4.1.2.		Increment product version in MKY.Version
		4.1.3.		Increment product version in NUnit.Version
		4.1.4.		Increment product version in YAT.Version
		4.1.5.		Set product name post fix in "YAT.Utilities.ApplicationInfo"
		4.1.6.		Set product version in MKY file headers
				> Remove 'Development', e.g. '// MKY Version 1.0.7'
		4.1.7.		Set product version in NUnit file headers
				> Remove 'Development', e.g. '// NUnit Version 1.0.4'
		4.1.8.		Set product version in YAT file headers
				> Remove 'Development', e.g. '// YAT 2.0 Beta 4 Candidate 1 Version 1.99.28'
		4.1.9.		Fill date and versions into 'The YAT story' in '0. Overview'

	4.2.			Set installation version		00:05		08:25
		4.2.1.		Set product title in "YAT.Setup"
		4.2.2.		Set product version in "YAT.Setup"

	4.3.			Add new settings to settings archive		00:15		08:40
		4.3.1.		Clone settings set to "YAT\!-Settings\<New Version>"
		4.3.2.		Add new settings to "YAT.Settings.Test.SettingsFilesProvider"
		4.3.3.		Add new settings to "YAT.Settings.Test.FileVersionsTest"

	4.4.			Rebuild		00:15		08:55
		4.4.1.		Rebuild 'Debug'
		4.4.2.		Rebuild 'Debug Test'
		4.4.3.		Rebuild 'Release Test'

	4.5.			Upgrade settings in settings archive		00:30		09:25
		4.5.1.		Commit changes to SVN to prepare diff
		4.5.2.		Upgrade settings
				> Run YAT and open old settings
				> Modify settings (use 'View > Show …' to ensure that IO settings are kept)
				> Undo changes
				> Save upgraded but unchanged settings
		4.5.3.		Diff and verify the new settings
		4.5.4.		Commit changes to SVN

## 5. Upload
				Duration	Step		Total

5.				Upload		00:00	01:25	09:25	10:50

	5.1.			Set versions		00:20		09:45
		5.1.1.		Increment product version in ALAZ.Version
		5.1.2.		Increment product version in MKY.Version
		5.1.3.		Increment product version in NUnit.Version
		5.1.4.		Increment product version in YAT.Version
		5.1.5.		Set product name post fix in "YAT.Utilities.ApplicationInfo"
		5.1.6.		Set product version in MKY file headers
				> Remove 'Development', e.g. '// MKY Version 1.0.7'
		5.1.7.		Set product version in NUnit file headers
				> Remove 'Development', e.g. '// NUnit Version 1.0.4'
		5.1.8.		Set product version in YAT file headers
				> Remove 'Development', e.g. '// YAT 2.0 Beta 4 Candidate 1 Version 1.99.28'
		5.1.9.		Fill date and versions into 'The YAT story' in '0. Overview'

	5.2.			Set installation version		00:05		09:50
		5.2.1.		Set product title in "YAT.Setup"
		5.2.2.		Set product version in "YAT.Setup"

	5.3.			Add new settings to settings archive		00:15		10:05
		5.3.1.		Clone settings set to "YAT\!-Settings\<New Version>"
		5.3.2.		Add new settings to "YAT.Settings.Test.SettingsFilesProvider"
		5.3.3.		Add new settings to "YAT.Settings.Test.FileVersionsTest"

	5.4.			Rebuild		00:15		10:20
		5.4.1.		Rebuild 'Debug'
		5.4.2.		Rebuild 'Debug Test'
		5.4.3.		Rebuild 'Release Test'

	5.5.			Upgrade settings in settings archive		00:30		10:50
		5.5.1.		Commit changes to SVN to prepare diff
		5.5.2.		Upgrade settings
				> Run YAT and open old settings
				> Modify settings (use 'View > Show …' to ensure that IO settings are kept)
				> Undo changes
				> Save upgraded but unchanged settings
		5.5.3.		Diff and verify the new settings
		5.5.4.		Commit changes to SVN

## 6. Finalization
				Duration	Step		Total

6.				Finalization		00:00	01:25	10:50	12:15

	6.1.			Set versions		00:20		11:10
		6.1.1.		Increment product version in ALAZ.Version
		6.1.2.		Increment product version in MKY.Version
		6.1.3.		Increment product version in NUnit.Version
		6.1.4.		Increment product version in YAT.Version
		6.1.5.		Set product name post fix in "YAT.Utilities.ApplicationInfo"
		6.1.6.		Set product version in MKY file headers
				> Remove 'Development', e.g. '// MKY Version 1.0.7'
		6.1.7.		Set product version in NUnit file headers
				> Remove 'Development', e.g. '// NUnit Version 1.0.4'
		6.1.8.		Set product version in YAT file headers
				> Remove 'Development', e.g. '// YAT 2.0 Beta 4 Candidate 1 Version 1.99.28'
		6.1.9.		Fill date and versions into 'The YAT story' in '0. Overview'

	6.2.			Set installation version		00:05		11:15
		6.2.1.		Set product title in "YAT.Setup"
		6.2.2.		Set product version in "YAT.Setup"

	6.3.			Add new settings to settings archive		00:15		11:30
		6.3.1.		Clone settings set to "YAT\!-Settings\<New Version>"
		6.3.2.		Add new settings to "YAT.Settings.Test.SettingsFilesProvider"
		6.3.3.		Add new settings to "YAT.Settings.Test.FileVersionsTest"

	6.4.			Rebuild		00:15		11:45
		6.4.1.		Rebuild 'Debug'
		6.4.2.		Rebuild 'Debug Test'
		6.4.3.		Rebuild 'Release Test'

	6.5.			Upgrade settings in settings archive		00:30		12:15
		6.5.1.		Commit changes to SVN to prepare diff
		6.5.2.		Upgrade settings
				> Run YAT and open old settings
				> Modify settings (use 'View > Show …' to ensure that IO settings are kept)
				> Undo changes
				> Save upgraded but unchanged settings
		6.5.3.		Diff and verify the new settings
		6.5.4.		Commit changes to SVN