## MKY.IO.Serial.SerialPort
#	Functionality	Test	Stimulus	Expected	Remarks

			Note that the following tests must be performed on an interface fully supporting buffering.
			Ideally use VSPE, or FTDI ports which are known to have best feature support.
			e.g. Microsoft and Prolific do not properly support buffering.

	Rates	Rates with default settings	Create a new terminal on serial COM port
			Create a second terminal looped back to the first
			Show rates on both terminals
			Send some data back and forth	Rates must properly behave
			Send "\!-SendFiles\Stress-1-Normal.txt"	Byte rate must be at least 500/s (i.e. 9600 baud - 25% - some overhead) / All bytes must be received
			Set both terminals to 115200 baud		Use presets, then these are tested right as well
			Send "\!-SendFiles\Stress-2-Large.txt"	Byte rate must be at least 3000/s (i.e. 115200 baud - 25% - lots of overhead) / All bytes must be received	Note that receiving may not be updated while sending file / See bug #305 "Break doesn't break file sending" for details

		Rates with full buffering	In advanced settings of both terminals, disable... / ...'Output no more than baud rate...' / ...'Output chunks of max...'
			Restore both terminals to 9600 baud		Use presets, then these are tested right as well
			Send some data back and forth	Rates must properly behave
			Send "\!-SendFiles\Stress-2-Large.txt"	With VSPE, byte rate will be something like 4000/s :-) / All bytes must be received
			Again set both terminals to 115200 baud		Use presets, then these are tested right as well
			Send "\!-SendFiles\Stress-2-Large.txt"	With VSPE, byte rate will be something like 14000/s :-)) / All bytes must be received

			Note that the following tests must be performed on an interface fully supporting advanced serial COM port features.
			Ideally use internal ports, or FTDI ports which are known to have best feature support.
			VSPE e.g. doesn't support XOn/XOff software flow control.

	RFR/CTS	Closed – Manual RFR/CTS	Create a new terminal on serial COM port with 'Manual Hardware' flow control without opening it	RFR/CTS/DTR/DSR/DCD states are shown but disabled
			Show flow control count	Flow control count is shown, all set to 0
		Open – Manual RFR/CTS	Start/open terminal	RFR/DTR are on and editable, CTS is shown and off
			Disable and re-enable RFR and DTR	Flow control count is incremented
			Reset flow control count	Flow control count reset to 0
		Closed – RFR/CTS	Create a second terminal looped back to the first with 'Hardware' flow control without opening it	RFR/CTS/DTR/DSR/DCD states are shown but disabled
		Open – RFR/CTS	Start/open terminal	RFR/DTR are on, DTR is editable, CTS is shown and on
				CTS/DSR/DCD of first terminal are on
			Disable and re-enable RFR and DTR of first terminal	CTS and DSR/DCD turn off and on / Flow control count is incremented
			Reset flow control count	Flow control count reset to 0
		Send while CTS is on	Send some data from second to first terminal	Data is sent and received
		Send while CTS is off	Toggle RFR of first terminal	CTS of second terminal is off
			Send some data from second to first terminal	Data is sent but retained
			Toggle RFR of first terminal	CTS of first terminal is on / Data is received

	XOn/XOff	Closed – None	Create a new terminal on serial COM port with 'None' flow control without opening it	IXS and OXS states are hidden
		Open – None	Start/open terminal	IXS and OXS states are hidden
		Open – Manual XOn/XOff	Set terminal to 'Manual Software' flow control	IXS and OXS states are shown, IXS is editable, IXS is on, OXS is assumed to be on / <XON> is sent by terminal
			Show flow control count	Flow control count is shown, all set to 0 / Except for IXS XOn which is incremented each time the terminal is opened
		Open – XOn/XOff	Create a second terminal looped back to the first
			Set terminal to 'Software' flow control
			Start/open terminal	<XON> is received by first terminal
				OXS count is incremented
		Send while XOn	Send some data from second to first terminal	Data is sent and received
		Send while XOff	Toggle IXS of first terminal	<XOFF> is received by second terminal but won't be shown
			Send some data from second to first terminal	Data is accepted
			Send some more data from second to first terminal until warning is output	Warning is output once / Data is accepted but partly retained (i.e. will not yet be shown)
			Send some more data from second to first terminal	Data is accepted but retained (i.e. will not yet be shown)
			Toggle IXS of first terminal	<XON> is received by second terminal but won't be shown / Retained data is sent and received
			Toggle IXS of first terminal	<XOFF> is received by second terminal but won't be shown
			Send a lot of data from second to first terminal	Data is accepted but retained / Warning is output once again	Ensure that a lot of data can be retained
			Toggle IXS of first terminal	<XON> is received by second terminal but won't be shown / Retained data is sent and received
		Hide XOn/XOff	Enable 'Hide XOn/XOff' in advanced settings of first terminal	<XON> and <XOFF> indications disappear
		Show XOn/XOff	Disable 'Hide XOn/XOff' in advanced settings of first terminal	<XON> and <XOFF> indications reappear

	Combined	Combine both above	Use 'Manual Combined' and 'Combined' flow control

	Output Break State	Indicate OBS/IBS	Create a new terminal on serial COM port
			Terminal > Settings... > Advanced Settings... / > Indicate break states / > Output break can be modified	IBS and OBS indicated / IBS is disabled (i.e. greyed), OBS is enabled

			Create a second terminal looped back to the first
			Terminal > Settings... > Advanced Settings... / > Indicate break states / > Output break can be modified	IBS and OBS indicated / IBS is disabled (i.e. greyed), OBS is enabled

		Set OBS manually	Set OBS of first terminal by clicking on symbol	First terminal: OBS turns red and terminal gets disconnected
				Second terminal: IBS turns red but terminal stays connected

		Reset OBS manually	Reset OBS of first terminal by clicking on symbol	First terminal: OBS turns green and terminal gets connected again / Second terminal: IBS stays red
			Send some data from first to second terminal	Data is sent and received / Second terminal: IBS turns green

		Modify OBS settings	First terminal: / Terminal > Settings... > Advanced Settings... / > No send while in OBS = No

		Set OBS manually	Set OBS of first terminal by clicking on symbol	First terminal: OBS turns red and terminal gets disconnected / Second terminal: IBS turns red but terminal stays connected
			Send some data from first to second terminal	Data is retained and an error message is shown

		Reset OBS manually	Reset OBS of first terminal by clicking on symbol	First terminal: OBS turns green and terminal gets connected again / Second terminal: IBS stays red
			Send some data from first to second terminal	Data is sent and received / Second terminal: IBS turns green

		\!(OutputBreakOn)	Define a command \!(OutputBreakOn)\!(NoEOL)
		\!(OutputBreakOff)	Define a command \!(OutputBreakOff)\!(NoEOL)
			Define a command with some data

			Send some data from first to second terminal	Data is sent and received
			Set OBS of first terminal by calling the according command	First terminal: OBS turns red and terminal gets disconnected / Second terminal: IBS turns red but terminal stays connected
			Reset OBS of first terminal by calling the according command	First terminal: OBS turns green and terminal gets connected again / Second terminal: IBS stays red
			Send some data from first to second terminal	Data is sent and received / No error messages appear / Second terminal: IBS turns green

ToDo			"YAT – BreakStateTest.jpg" still of any purpose?

ToDo		Suspend/Resume	Open terminal on internal COM		Requires computer with internal COM (e.g. docking station @ MT)
		of internal COM	Send some data back and forth	Data is sent and received
			Suspend computer
			Resume computer
			Send some data back and forth	Data is sent and received, no exceptions

	Disconnect/Reconnect	Microsoft driver	Go to the system device manager / Locate the RB EVB (e.g. on COM43) and verify the driver	Driver is e.g. ToriLogic/Thesycon 1.21.0.0 of 2016-07-21	This is an additional test to the automatic performed tests / Required because the automatic test doesn't use the Microsoft driver
			Change to Microsoft driver by 'Update > Manual > List > Serial USB Device'	Driver now is e.g. Microsoft 10.0.10586.306 of 2016-06-21
			Create a new terminal on RB EVB serial COM port	Terminal opened
			Send something	Sending possible, successfully receiving
			Disconnect USB cable on RB EVB	Terminal still indicated as "Open" since alive ticker doesn't work with Microsoft driver / No exceptions
			Manually close the port	No exceptions
			Reconnect USB cable to RB EVB
			Manually open the port again
			Send something	Sending possible, successfully receiving
			Disconnect USB cable on RB EVB	Terminal still indicated as "Open" since alive ticker doesn't work with Microsoft driver / No exceptions
			Reconnect USB cable to RB EVB	Terminal reopened
			Send something again	Sending possible again, successfully receiving	Unfortunately, this case cannot be handled as port stays open the whole time / => ObjectDisposedException will happen and YAT needs to be restarted
			Send something	Sending possible, successfully receiving
			Disconnect USB cable on RB EVB	Terminal still indicated as "Open" since alive ticker doesn't work with Microsoft driver / No exceptions
			Send something	Sending not possible, terminal gets closed, is waiting for reconnect	Unfortunately, this case cannot be reliably handled / => ObjectDisposedException may happen and YAT needs to be restarted
			Reconnect USB cable to RB EVB	Terminal reopened
			Send something again	Sending possible again, successfully receiving	Only new data is sent, previous data got cleared
			Exit YAT	No exceptions
			Go back to the system device manager
			Restore to ToriLogic/Thesycon driver by 'Update > Manual > List > Serial USB Device'	Driver is again e.g. ToriLogic/Thesycon 1.21.0.0 of 2016-07-21

## MKY.IO.Serial.Socket
#	Functionality	Test	Stimulus	Expected	Remarks

	Open	Continuous while opening	Create a new terminal using AutoSocket
			Start continuous mode on device		SIR on RB ExBal Win32 / (ECHO 2 doesn't work as disconnect resets it)
			Close port while SIR is received	No exceptions
			Open port while SIR is received	Data is received, no exceptions
			Exit YAT	No exceptions
			Start YAT while SIR is received	Data is received, no exceptions
			Stop continuous mode on device		C

	TCP/IP Client	Auto-Reconnect	Create and open TCP/IP Server
			Create and open TCP/IP Client without auto-reconnect	Both terminals interconnected
			Close server	Client gets disconnected
			Open server again	Client stays disconnected
			Open client	Both terminals are interconnected
			Reconfigure the client to be auto-reconnectable
			Close server	Client gets disconnected
			Open server again	Client gets reconnected
			Close server again	Client gets disconnected
			Open server again	Client gets reconnected

	TCP/IP Server	Listening	Close client	Server gets listening
			Open client	Server gets reconnected
			Close client again	Server gets listening
			Open client again	Server gets reconnected

			Close both terminals

	Rates	Tx/Rx byte/line rates	Create a new terminal using AutoSocket
			Create a second terminal looped back to the first
			Show rates on both terminals
			Send some data back and forth	Rates must properly behave
			Send "\!-SendFiles\Stress-3-EvenLarger.txt"	Byte rate must be ~15000/s / Line rate must be ~200/s / All bytes must be received

	TCP/IP AutoSocket	Remoteconnect	[On YAT DevelopmentComputer] / Create a new terminal using TCP/IP AutoSocket / > Remote Host = YAT TestComputer	Terminal can be opened	YAT DevelopmentComputer is 192.168.188.34
			[On YAT TestComputer] / Create a new terminal using TCP/IP AutoSocket / > Remote Host = YAT DevelopmentComputer	Both terminals interconnected	YAT TestComputer is 192.168.188.32
			Send some data back and forth	Data can be exchanged

			Close both terminals

	TCP/IP Cilent/Server	Remoteconnect	[On YAT TestComputer] / Create a TCP/IP Server	Terminal can be opened
			[On YAT DevelopmentComputer] / Create a new terminal using TCP/IP Client / > Remote Host = YAT TestComputer	Both terminals interconnected	YAT TestComputer is 192.168.188.32
			Send some data back and forth	Data can be exchanged

			[On YAT DevelopmentComputer] / Create a TCP/IP Server
			[On YAT TestComputer] / Create a TCP/IP Client / > Remote Host = YAT DevelopmentComputer	Both terminals interconnected	YAT DevelopmentComputer is 192.168.188.34
			Send some data back and forth	Data can be exchanged

			Close all terminals

	UDP/IP PairSocket	Interconnect	Create two terminals using UDP/IP PairSocket / > 1st terminal ports = 10000 / 10001 / > 2nd terminal ports = 10001 / 10000	Both terminals opened
			Send some data back and forth	Data can be exchanged
			Close all terminals

		Remoteconnect	[On YAT DevelopmentComputer] / Create a new terminal using UDP/IP PairSocket / > Remote Host = YAT TestComputer / > Local UDP Port = 10000	Terminal can be opened	YAT TestComputer is 192.168.188.32
			[On YAT TestComputer] / Create a new terminal using UDP/IP PairSocket / > Remote Host = YAT DevelopmentComputer / > Local UDP Port = 10000	Both terminals interconnected	YAT DevelopmentComputer is 192.168.188.34
			Send some data back and forth	Data can be exchanged

			Close both terminals

	UDP/IP Client/Server	Interconnect	Create a terminal using UDP/IP Client / > Remote port = 10000
			Create a terminal using UDP/IP Server / > Local port = 10000
			Send some data back and forth	Data can be exchanged	Client must send data first

		Multiconnect	Create another terminal using UDP/IP Client / > Remote port = 10000	Port sharing allowed
			Send some data back and forth	Data can be exchanged	Server sends to most recently active client
			Send some data back and forth from the previous client	Data can be exchanged	Server sends to most recently active client

			Close all terminals

		Remoteconnect	[On YAT TestLaptop] / Create a UDP Server / > Local port = 10000	Terminal can be opened
			[On YAT DevelopmentComputer] / Create a new terminal using UDP/IP Client / > Remote host = YAT TestLaptop / > Remote port = 10000		Client must send data first

			Close both terminals

## MKY.IO.Serial.Usb
#	Functionality	Test	Stimulus	Expected	Remarks

	Enumeration		Connect test devices
			Start YAT and select USB Ser/HID	Devices are shown in device list

	Start/Stop	Single device	Send something to the device	Device responses	Use YAT.8 ExLight
			Terminal caption and I/O status	Full device info – Connected – Open / Green
			Stop terminal	Full device info – Closed / Grey
			Start terminal	Full device info – Connected – Open / Green
			Repeat Stop/Start
			Send something to the device	Device responses
			Close YAT while terminal is open	Terminal closes, YAT exits
			Start YAT again	Full device info – Connected – Open / Green
			Send something to the device	Device responses
			Stop terminal	Full device info – Closed – Grey
			Start terminal	Full device info – Connected – Open / Green
			Send something to the device	Device responses

	Connect/Disconnect	Single device	Disconnect device while terminal is open	Full device info – Disconnected – Waiting / Red	YAT.8 ExLight is connected to Out 1 of Hub 1
			Reconnect device	Full device info – Connected – Open / Green
			Send something to the device	Device responses
			Repeat Disconnect/Connect
			Send something to the device	Device responses
			Reset device
			Send something to the device	Device responses
			Disconnect device while terminal is open	Full device info – Disconnected – Waiting / Red
			Stop terminal	Full device info – Closed / Grey
			Reconnect device	Full device info – Closed / Grey
			Start terminal	Full device info – Connected – Open / Green
			Send something to the device	Device responses
			Close YAT while terminal is open	Terminal closes, YAT exits
			Disconnect device while YAT is closed
			Start YAT again	Full device info – Disconnected – Waiting / Red
			Reconnect device	Full device info – Connected – Open / Green
			Send something to the device	Device responses
			Repeat Disconnect/Connect
			Send something to the device	Device responses
			Stop terminal	Short device info – Closed – Grey
			Disconnect device while terminal is stopped
			Start terminal	Full device info – Disconnected – Waiting / Red
			Reconnect device	Full device info – Connected – Open / Green
			Send something to the device	Device responses

	XOn/XOff	Manual XOn/XOff	Set terminal to 'Manual Software' flow control	IXS and OXS states are shown, IXS is editable, IXS is on, OXS is assumed to be on
			Show flow control count	Flow control count is shown, all set to 0 / Except for IXS XOn which is incremented each time the terminal is opened
		Send while XOn	Request some data from the device	Data is sent and received
		Send while XOff	Toggle IXS	<XOFF> is sent
			Request some data from the device	Data is sent but no response is received
			Toggle IXS	<XON> is sent
				Retained data is received
		Hide XOn/XOff	Enable 'Hide XOn/XOff' in advanced settings of first terminal	<XON> and <XOFF> indications disappear
		Show XOn/XOff	Disable 'Hide XOn/XOff' in advanced settings of first terminal	<XON> and <XOFF> indications reappear

	Report ID	Correct ID	Create a new terminal to one of the MT boards using defaults (i.e. report ID = 0)	Connected – Open – Green
		Display settings	Terminal Settings... > Advanced Settings... > Include non-payload data
			Request some data from the device	Data is sent and received
		Wrong ID	Open terminal settings and change report ID = 1	Connected – Open – Green
			Request some data from the device	Data is sent but nothing is received
		Correct ID again	Open terminal settings and restore report ID = 0	Connected – Open – Green
			Request some data from the device	Data is sent and received again

		\!(ReportId(<ID>))	Prepend \!(ReportId(1)) and request data again	Data is sent but nothing is received	\!(ReportId(1))
			Prepend \!(ReportId(0)) and request data again	Data is sent and received again
			Prepend \!(ReportId(1)) and request data again	Data is sent but nothing is received
			Prepend \!(ReportId()) and request data again	Data is sent and received again

		Display settings	Terminal Settings... > Advanced Settings... > Exclude non-payload data again
			Request some data from the device	Data is sent and received

		Preset 'Plain'	Change preset to 'Plain'
			Request some data from the device	Data is sent and received / Response includes terminating zero and filler bytes

		\!(ReportId(<ID>))	Prepend \!(ReportId(1)) and request data again	Data is sent but nothing is received
			Prepend \!(ReportId(0)) and request data again	Data is sent and received again

	TI Loopback	COM loopback	Create a new terminal to TI board #1 using the COM51 application UART @ 28.8 k	Connected – Open – Green
		USB Ser/HID	Create a new terminal to TI board #1	Connected – Open – Green
			Send some data back and forth	USB > COM works fine, COM > USB may result in <CR>/<LF> issues

		Display settings	Terminal Settings... > Advanced Settings... > Include non-payload data
			Send some data back and forth	USB > COM works fine, COM > USB may result in <CR>/<LF> issues

		\!(ReportId(<ID>))	Prepend \!(ReportId(0x01)) and request data again	Error message "Falscher Parameter"	\!(ReportId(0x01))
			Reset device
			Prepend \!(ReportId(0x3F)) and request data again	Data is sent and received again
			Prepend \!(ReportId(0x01)) and request data again	Error message "Falscher Parameter"
			Reset device
			Prepend \!(ReportId()) and request data again	Data is sent and received again

## YAT.Model.Main
#	Functionality	Test	Stimulus	Expected	Remarks

	File handling	Files on temporary storage	Create and start 2 AutoSockets which are interconnected to each other
			Save workspace and terminals onto a memory stick	Workspace and terminals are saved
			Remove memory stick	Nothing happens
			Send some data back and forth	Data sent and received
			Exit YAT	YAT issues error messages / Exit is cancelled / No exceptions
			Reconnect memory stick
			Exit YAT	YAT exits without any warning or error message

		Close on removed files on implicitly changed settings	Subsequent start	Workspace must still contain 2 terminals
			Remove memory stick	Nothing happens
			Send some data back and forth	Data sent and received
			Exit YAT	YAT exits without any warning or error message

		Save on removed files on implicitly changed settings	Reconnect memory stick
			Subsequent start	Workspace must still contain 2 terminals
			Remove memory stick	Nothing happens
			Send some data back and forth	Data sent and received
			Save terminal	A proper error message and the 'Save As...' dialog is shown	User intended save is always to be done
			No	Nothing happens
			Exit YAT	YAT exits without any warning or error message

		Save on removed files on explicitly changed settings	Reconnect memory stick
			Subsequent start	Workspace must still contain 2 terminals
			Remove memory stick	Nothing happens
			Modify some explicit settings	Asterisk is shown
			Save terminal	A proper error message and the 'Save As...' dialog is shown	User intended save is always to be done
			No	Nothing happens, asterisk is still shown
			Reconnect memory stick
			Save terminal	Saved without any warning or error message / Asterisk no longer shown
			Exit YAT	YAT exits without any warning or error message

		Close on removed files on explicitly changed settings	Subsequent start	Workspace must still contain 2 terminals
			Remove memory stick	Nothing happens
			Modify some explicit settings	Asterisk is shown
			Exit YAT	A proper error message and the 'Save As...' dialog is shown	Explicit settings are to be saved on exit
			Cancel	Nothing happens, asterisk is still shown
			Exit YAT	A proper error message and the 'Save As...' dialog is shown	Explicit settings are to be saved on exit
			No	YAT exits without any warning or error message

## YAT.Model.Terminal
#	Functionality	Test	Stimulus	Expected	Remarks

	Automatic response	Initialization	Create and start 2 AutoSockets which are interconnected to each other	Automatic response combo boxes are not visible / Menu > Send > Automatic Response is not checked
			Send some data back and forth	Data sent and received
			Create some predefined command		Later used as triggers and responses
			Send some data back and forth	Data sent and received

		Configuration	Show automatic response in tool bar	Automatic response combo boxes are not visible / Menu > Send > Automatic Response is not checked
			Select trigger = [Any Line]
			Select response = [Send Text]
		Trigger	Send some data back and forth	Data sent and received / Automatic response is triggered for each received line

			Select response = [Predefined Command 1]	Data sent and received / Automatic response is triggered for each received line
			Select response = [Predefined Command 2]	Data sent and received / Automatic response is triggered for each received line
			Select response = Some dedicated command	Data sent and received / Automatic response is triggered for each received line

			Select trigger = [Predefined Command 1]	Data sent and received / Automatic response is triggered for the given command

		Persistance	Exit YAT
			Start YAT again	Automatic response settings are still active
			Send some data back and forth	Data sent and received / Automatic response is triggered for each received line

## YAT.View.Forms.Main
#	Functionality	Test	Stimulus	Expected	Remarks

	Startup position		Start YAT	YAT is started within visible screen
			Create a terminal		Required to keep workspace
			Move YAT to a different location, if available to a different screen		Note that the whole application must be located at one screen, / i.e. positions across screens are moved to the primary screen
			Resize YAT
			Exit YAT		Position and size are stored in workspace
			Start YAT again	YAT is started with correct location and size

	Layout setting		Create another terminal	Terminals are created and automatically tiled vertically
			Resize YAT	Terminals are kept tiled
			Exit YAT	Layout is stored in workspace
			Start YAT again	Layout is restored
			Resize YAT	Terminals are still kept tiled
			Resize one of the terminals	Layout is reset to 'Manual'
			Resize YAT	Terminals are no longer resized
			Exit YAT	Layout is stored in workspace
			Start YAT again	Layout is restored
			Layout terminals again automatically (Ctrl+Alt+A)	Terminals get tiled again
			Resize YAT	Terminals are kept tiled

	Always on top		Ctrl+Alt+T to enable 'Always On Top'
			Change to some other application	YAT stays on top
			Change back to YAT
			Ctrl+Alt+T to disable 'Always On Top'
			Change to some other application	YAT no longer on top
			Change back to YAT
			Exit YAT

	No Ports		Disable all internal serial COM ports / Disconnect all USB/RS-232 adapters / Disable all virtual ports such as VSPE
			Start YAT	Warning that there are no serial COM ports / Everything else must work fine

## YAT.View.Forms.Terminal
#	Functionality	Test	Stimulus	Expected	Remarks

	Send Text		Create and start 2 AutoSockets which are interconnected to each other
		Edit	Fill-in some command
			<Enter>	Command gets sent / Cursor stays at end of text box
			Modify the command
			<Enter>	Command gets sent / Cursor stays at end of text box
			<Enter>	Command gets sent / Cursor stays at end of text box	Ensure that subsequent <Enter> work
			2 x <Alt-Tab> to switch to some other application and back to YAT	Command gets completely selected
			<Enter>	Command gets sent / Cursor stays at end of text box
			Modify the command
			<Enter>	Command gets sent / Cursor stays at end of text box
			2 x <Alt-Tab> to switch to some other application and back to YAT	Command gets completely selected
			Modify the command
			<Enter>	Command gets sent / Cursor stays at end of text box
			<Ctrl+Enter>	Command gets sent without EOL / Cursor stays at end of text box
			<Enter>	Command gets sent / Cursor stays at end of text box
		Edit while closed	Stop the terminal	Cursor stays at end of text box
			Modify the command
			Start the terminal again
			<Enter>	Command gets sent / Cursor stays at end of text box
		F-Shortcuts	<F3>	Command gets sent / Cursor and selection stays as is
			<Alt+F3>	Command gets sent without EOL / Cursor and selection stays as is
			<F3>	Command gets sent / Cursor and selection stays as is
		Ctrl-Shortcuts	<Ctrl+A>	Command gets completely selected
			<Ctrl+C>	Command gets copied onto clipboard
		Multi Line	Select "..."	'Multi Line Command' box opens / Former command is visible
			Fill-in some multi line command
			<Ctrl+Enter>	'Multi Line Command' box closes / 'Send Command' shows the command
			<Enter>	Command gets sent / Cursor stays at 'Send Command (F3)'
			2 x <Shift+Tab> to move cursor back to the text field
			<Enter>	Command gets sent / Cursor stays at end of text box
			<Ctrl+A>	Command gets completely selected
			Modify the command
			<Enter>	Command gets sent / Cursor stays at end of text box
			<Arrow-Down> and <Arrow-Up>	Command changes among recents
			<Enter>	Command gets sent / Cursor stays at end of text box
		Keep Command	<Ctrl+Shift+K> to disable this option
			<Enter>	Command gets erased after send
			Fill-in some new command
			<Enter>	Command gets erased after send
			<Ctrl+Shift+K> to restore this option
			Fill-in some new command
			<Enter>	Command gets sent / Cursor stays at end of text box
		Send Immediately	<Ctrl+Shift+I> to enable this option	Command gets reset / Button changes to "Send EOL (F3)"
			Enable 'Show EOL'		Required to track line breaks below
			Enter some characters	Characters are sent immediately
			<Enter>	EOL is sent / Line break is done
			<Enter>	EOL is sent / Line break is done
			Enter some characters	Characters are sent immediately
			<F3>	EOL is sent / Line break is done
			<F3>	EOL is sent / Line break is done
			Enter some characters	Characters are sent immediately
			<Backspace>	<BS> is sent
			Enter some characters	Characters are sent immediately	Ensure that characters are still sent properly
			<Enter>	EOL is sent / Line break is done
			Press "Send EOL (F3)"	EOL is sent / Line break is done
			Press "Send EOL (F3)"	EOL is sent / Line break is done	Ensure that <Enter a command...> doesn't lead to an error message
			<Ctrl+Shift+I> to restore this option
			<Enter>	EOL is sent	Ensure that command is properly reset
			Fill-in some command
			<Enter>	Command gets sent / Cursor stays at end of text box
		Recent	<Arrow-Down> and <Arrow-Up>	Command changes among recents	Ensure that items are sorted correctly (most recent at top)
			<Enter>	Command gets sent / Cursor stays at end of text box
			Open recent drop-down	No control characters in drop-down	Control characters would be displayed as bullet and result in an XML serialization error when serializing the recents into the .yat file

	Predefined Commands		Keep the 2 AutoSockets which are interconnected to each other
			Define a predefined command without a dedicated description
			Define a predefined command with a dedicated description
			Define a predefined multi line command without a dedicated description
			Define a predefined multi line command with a dedicated description
			Send the predefined commands back and forth	Commands get sent
		F-Shortcuts	<Shift+Fx>	Command gets sent
		Recent	<Arrow-Down> and <Arrow-Up>	Command changes among recents	Ensure that items are sorted correctly (most recent at top)
			<Enter>	Command gets sent / Cursor stays at end of text box
		Changed Recent	<Arrow-Down> and <Arrow-Up>	Command changes among recents
			<Shift+Fx>	Command gets sent / "Send Text" still contain changed recent
			<Enter>	Changed recent command gets sent / Cursor stays at end of text box
			<Shift+Fx>	Command gets sent
		Copy Predefind	<Ctrl+Shift+P> to enable this option
			<Shift+Fx>	Command gets copied after send	Ensure that command is sent from the active terminal!
			If cursor is not yet in "Send Command" / <Alt+C> to set cursor into "Send Command"
			Modify the command
			<Enter>	Command gets sent / Cursor stays at end of text box
			<Shift+Fx>	Command gets copied after send / Cursor stays at end of text box
			<Enter>	EOL is sent / Line break is done
			<Ctrl+Shift+P> to restore this option
		Recent	<Arrow-Down> and <Arrow-Up>	Command changes among recents	Ensure that items are sorted correctly (most recent at top)
			<Enter>	Command gets sent / Cursor stays at end of text box

	Send File		Enable 'Byte/Line Count'
			Send "\!-SendFiles\Stress-3-EvenLarger.txt"	GUI properly reponds
			Break sending	Breaks within reasonable time	Not yet possible, requires fixing bug #305 "Break doesn't break file sending"
			Send "\!-SendFiles\Stress-2-Large.txt"	Break has been resumed / GUI still properly responds
			<F4>	File is sent again
			<F4>	File is sent again
			Repeat the steps "Predefined" above	Same as for text terminal

		Stress	Send "\!-SendFiles\Stress-5-LongLine.txt"	Works without issues / Line exceed warning is output at the end of the line
			Send "\!-SendFiles\Stress-6-EnormousLine.txt"	Works without issues / Line exceed warning is output at the end of the line	Not yet possible, requires fixing bug #340 "Enormous lines cannot be sent"
			Clear the monitors

	Text Line Breaks	Empty Lines	Keep the 2 AutoSockets which are interconnected to each other
			A\!(EOL)B\!(EOL)\!(EOL)C	A / B / C
			Enable 'Show EOL'	Same as above but with <CR><LF>
			Disable 'Show EOL'	Same as above without <CR><LF>

	Binary Terminal		Change both to 'Binary' terminals
			Repeat the some of the steps above to ensure that binary works as well
			Switch radix	All radices work well	Ensure that 'String' and 'Char' also works for binary terminals

	Binary Line Breaks		Keep the 2 AutoSockets which are interconnected to each other
			Set both terminals to binary and enable binary line breaks
			Send some commands back and forth	Line breaks work according to the settings	Cannot be tested automatically because of limitations to read back the formatted text output

## YAT.View.Forms.Settings
#	Functionality	Test	Stimulus	Expected	Remarks

	Settings Dialogs	Terminal Settings	Create a 'Text' terminal

			Open the terminal settings	All fine
			Modify some settings	All fine	Explorative testing
			Open the 'Text' settings	All fine
			Modify some settings	All fine	Explorative testing
			Close the 'Text' settings	All fine
			Open the 'Advanced' settings	All fine
			Modify some settings	All fine	Explorative testing
			Close the 'Advanced' settings	All fine
			Close the terminal settings	All fine

			Open the terminal settings again	All fine
			Change to 'Binary'	All fine
			Modify some settings	All fine	Explorative testing
			Open the 'Binary' settings	All fine
			Modify some settings	All fine	Explorative testing
			Close the 'Binary' settings	All fine
			Open the 'Advanced' settings	All fine
			Modify some settings	All fine	Explorative testing
			Close the 'Advanced' settings	All fine
			Close the terminal settings	All fine

		Log Settings	Open the log settings	All fine
			Modify some settings	All fine	Explorative testing
			Close the log settings	All fine

		Format Settings	Open the format settings	All fine
			Modify some settings	All fine	Explorative testing
			Close the format settings	All fine

		Preferences	Open the preferences	All fine
			Modify some settings	All fine	Explorative testing
			Close the format settings	All fine

## YAT.Log
#	Functionality	Test	Stimulus	Expected	Remarks

	Log		Create and start 2 AutoSockets which are interconnected to each other
			"Open log folder in file browser..."

		Initial = Neat text	Log > On	File is created	BiDir @ Neat => .log
			Send some data back and forth
			Open file in text editor	File contains transmitted lines
			Send some data back and forth
			Log > Off
			Change to text editor	File gets refreshed / File contains transmitted lines
			Close editor

		Neat RTF	Log > Settings
			Change to .rtf
			Log > On	File is created	BiDir @ Neat => .rtf
			Send some data back and forth
			Log > Off
			Open file in Office Word	File contains transmitted lines

		Changing settings	Log > On	New file is created	New time stamp

		Neat XML	Log > Settings
			Change to .xml	File is created	BiDir @ Neat => .xml
			Send some data back and forth
			Open file in text editor	File contains transmitted lines
			Send some data back and forth
			Change to text editor	File gets refreshed / File contains transmitted lines

		Raw text	Log > Settings
			Disable neat log
			Enable all raw logs	Files are created	All @ Raw => .dat
			Send some data back and forth
			Open files in hex editor	Files contain transmitted data / Files contain no Unicode BOM

		Raw XML	Log > Settings
			Change to .xml	Files are created	All @ Raw => .xml
			Send some data back and forth
			Open files in text editor	Files contain transmitted data
			Send some data back and forth
			Change to text editor	Files get refreshed / Files contain transmitted data

## YAT.Info
#	Functionality	Test	Stimulus	Expected	Remarks

		Release Notes	"Help > Release Notes"	Check version and year/date

		About	"Help > About"	Check version and year

		Unhandled Exceptions	"Help > About" > Click slightly above the right end of the 1st line	Unhandled exception is thrown and handled / Console indicates unhandled exception / Exception details can be shown
				Exception contains inner exception (level1)
				Exception can be copied onto clipboard
			Request "Exit"	YAT exits, no exceptions
			"Help > About" > Click 1st line again	Unhandled exception is thrown and handled / Console indicates unhandled exception / Exception details can be shown
				Exception contains inner exception (level1)
				Exception can be copied onto clipboard
			Request "Restart"	YAT restarts, no exceptions
			"Help > About" > Click 1st line again	Unhandled exception is thrown and handled / Console indicates unhandled exception / Exception details can be shown	Becomes async after restart (for whatever reason)
				Exception contains inner exception (level1)
				Exception can be copied onto clipboard
			[Retry]	No exceptions
			"Help > About" > Click 1st line again	Unhandled exception is thrown and handled / Console indicates unhandled exception / Exception details can be shown	Still async
				Exception contains inner exception (level1)
				Exception can be copied onto clipboard
				No exceptions
			[Ignore]	No exceptions
			"Help > About" > Click 1st line again	Exception is being ignored
			Exit YAT	YAT exits, no exceptions	Required to fully reset exception handling

			"Help > About" > Click slightly above the right end of the 2nd line	Same as above

			"Help > About" > Click slightly above the right end of the 3rd line	Same as above, without [Retry] and [Ignore]	Debugger will show the exception => [Continue]

## Installation
#	Functionality	Test	Stimulus	Expected	Remarks

	File system	Files	Open "C:\Program Files\YAT"	3rd party infos / ALAZ / MKY / RtfWriter / YAT assemblies / Release Notes / YAT.exe / YATConsole.exe / No NUnit, no test projects
				Timestamp of all executables must be build time

	System	Installed Software	Open "System > Software"	YAT is shown once only	Old versions are replaced automatically
				YAT is shown with the correct version

	Local User Settings	Prepare	Ensure that previous Local User Settings are available		This is a quick-fix to feature request #178 "Add test cases for local user settings"

	System	Start	Open "Start > Programs"	YAT must be shown

	YAT	Initial start	Start "Start > Programs > YAT > YAT"	YAT must start with last settings
		Terminals	Create 2 interconnected serial COM port terminals	Terminals must get created
			Send some data back and forth	Data must be sent back and forth
			Define a few predefined commands	Commands must be usable to send data back and forth
			Ensure that there are some command recents	Commands must be usable to send data back and forth
			Ensure that there are some file recents	Files must be usable to send data back and forth
		Exit	Exit	Workspace including terminals must be auto-saved
		Subsequent start	Start "Start > Programs > YAT > YAT"	Workspace including terminals must be restored
			Send some data back and forth	Data must be sent back and forth
			Use previously predefined commands	Commands must be usable to send data back and forth
			Use command recents	Commands must be usable to send data back and forth
			Use file recents	Files must be usable to send data back and forth
		Workspace	"File > Workspace > Close"	Workspace must be closed without exceptions

		.yat	Create 2 interconnected TCP/IP AutoSocket terminals	Terminals must get interconnected
			Save terminals manually (Save As...)	Files must get created
			"File > Workspace > Close Workspace"	Workspace must be closed without exceptions
			"File > Open"
			Open first terminal again	First terminal must be opened
			"File > Recent"	Second terminal must be opened
		.yaw	Save workspace manually (Save As...)	File must get created
			Exit
		.yaw/.yat cmd line	Double-click the workspace .yaw	YAT and terminals must be opened
			Double-click one of the terminal .yat	YAT and terminal must be opened

		YAT.exe	Verify that console based start works
			Verify that help is shown in message box
			Verify that errors are handled and help is output

		YATConsole.exe	Verify that console based start works
			Verify that help is shown in console
			Verify that errors are handled and help is output

		Main	Welcome	Check version
		Release Notes	"Help > Release Notes"	Check version and year/date
		About	"Help > About"	Check version and year

	Concurrent Instances in case of AutoSave	Precondition	LocalUserSettings.General.AutoOpenWorkspace = true		This test initially was implemented as YAT.Model.Test.FileHandlingTest.TestConcurrentInstancesInCaseOfAutoSave() and...
			LocalUserSettings.General.AutoSaveWorkspace = true		...YAT.Model.Test.FileHandlingTest.TestSequenceOfUseCases_6_through_9_()::UC9 with a third main.
			LocalUserSettings.AutoWorkspace.FilePath = ""		However, these tests cannot be done automatically due to limitations of running really concurrent instances out of a single NUnit test script.

		Step 1 :: Initial start and exit	Initial start
			Create new terminal	Auto workspace with 1 auto terminal
			Define a few predefined commands

		Step 2 :: Subsequent and concurrent start with nested exit	Subsequent start (instance #1)	Instance #1: / Workspace still contains 1 terminal / Terminal still contains predefined commands
			Concurrent start (instance #2)	Instance #2: / New terminal can be created
			Exit instance #2
			Exit instance #1

		Step 3 :: Subsequent start and exit	Subsequent start	Workspace still contains 1 terminal / Terminal still contains predefined commands
			Exit

		Step 4 :: Subsequent and concurrent start with sequential exit	Subsequent start (instance #1)	Instance #1: / Workspace still contains 1 terminal / Terminal still contains predefined commands
			Concurrent start (instance #2)	Instance #2: / New terminal can be created
			Exit instance #1
			Exit instance #2

		Step 5 :: Subsequent start and exit	Subsequent start	Workspace still contains 1 terminal / Terminal still contains predefined commands
			Exit