## 0. Overview
A YAT release is done in 6 steps:
				Duration	Step	Total
		1.	Preparation		01:25	01:25
		2.	Software Testing
		3.	Packaging
		4.	Installation Testing
		5.	Upload
		6.	Finalization

The YAT story:
					YAT	MKY	ALAZ	NUnit
	2011-12-04	:	YAT 2.0 Beta 4 Candidate 1				1.99.28	1.0.7	3.5.5	1.0.4
	2011-04-25	:	YAT 2.0 Beta 3 Candidate 4				1.99.26	1.0.5	3.5.3	1.0.2
	2010-11-28	:	YAT 2.0 Beta 3 Candidate 3				1.99.25	1.0.4	3.5.2	1.0.1
	2010-11-11	:	YAT 2.0 Beta 3 Candidate 2				1.99.24	1.0.4	3.5.2	1.0.1
	2009-09-10	:	YAT 2.0 Beta 3 Candidate 1				1.99.23	1.0.1	3.5.0
	2009-09-08	:	YAT 2.0 Beta 3 Candidate 1				1.99.22	1.0.1	3.5.0
	2008-07-18	:	YAT 2.0 Beta 2 Candidate 4				1.99.20	1.0.0	1.2.0
	2008-04-01	:	YAT 2.0 Beta 2 Candidate 3				1.99.19
	2008-03-17	:	YAT 2.0 Beta 2 Candidate 2				1.99.18
	2008-02-11	:	YAT 2.0 Beta 2 Candidate 1				1.99.17
	2007-08-30	:	YAT 2.0 Beta 2 Preliminary				1.99.13
	2007-04-15	:	YAT 2.0 Beta 1				1.99.12
	2007-02-25	:	YAT 2.0 Alpha 3				1.99.8
	2007-02-07	:	YAT 2.0 Alpha 2				1.99.3
	2007-01-23	:	YAT 2.0 Alpha 1				1.99.0
	2003-10-31	:	XTerm232				1.0.2
	2003-10-30	:	XTerm232				1.0.1
	2003-10-14	:	XTerm232				1.0.0

## 1. Preparation
				Duration	Step		Total

1.				Preparation		00:00	01:25	00:00	01:25

	1.1.			Set versions		00:20		00:20
		1.1.1.		Increment product version in ALAZ.Version
		1.1.2.		Increment product version in MKY.Version
		1.1.3.		Increment product version in NUnit.Version
		1.1.4.		Increment product version in YAT.Version
		1.1.5.		Set product name post fix in "YAT.Utilities.ApplicationInfo"
		1.1.6.		Set product version in MKY file headers
				> Remove 'Development', e.g. '// MKY Version 1.0.7'
		1.1.7.		Set product version in NUnit file headers
				> Remove 'Development', e.g. '// NUnit Version 1.0.4'
		1.1.8.		Set product version in YAT file headers
				> Remove 'Development', e.g. '// YAT 2.0 Beta 4 Candidate 1 Version 1.99.28'
		1.1.9.		Fill date and versions into 'The YAT story' in '0. Overview'

	1.2.			Set installation version		00:05		00:25
		1.2.1.		Set product title in "YAT.Setup"
		1.2.2.		Set product version in "YAT.Setup"

	1.3.			Add new settings to settings archive		00:15		00:40
		1.3.1.		Clone settings set to "YAT\!-Settings\<New Version>"
		1.3.2.		Add new settings to "YAT.Settings.Test.SettingsFilesProvider"
		1.3.3.		Add new settings to "YAT.Settings.Test.FileVersionsTest"

	1.4.			Rebuild		00:15		00:55
		1.4.1.		Rebuild 'Debug'
		1.4.2.		Rebuild 'Debug Test'
		1.4.3.		Rebuild 'Release Test'

	1.5.			Upgrade settings in settings archive		00:30		01:25
		1.5.1.		Commit changes to SVN to prepare diff
		1.5.2.		Upgrade settings
				> Run YAT and open old settings
				> Modify settings, undo changes, save upgraded but unchanged settings
				> Save upgraded but unchanged settings
		1.5.3.		Diff and verify the new settings