## 0. Overview
A YAT release is done in 8 steps:
				Duration	Step	Total
		1.	Regression Testing		11:30	11:30
		2.	Preparation		01:45	13:15
		3.	Final Testing		01:30	14:45
		4.	Build		00:40	15:25
		5.	Installation Testing		00:40	16:05
		6.	Packaging		00:40	16:05
		7.	Upload		01:00	17:05
		8.	Finalization		02:10	18:55

The YAT story:
					YAT	MKY	ALAZ	NUnit	netrtfwr.		LU.xml	.yat	.yaw		SVN
	2016-09-30	:	YAT 2.0 Gamma 2''				1.99.52	1.0.17	3.5.14	1.0.14	0.9.15		1.5.0	1.5.0	1.2.1		1188
	2016-09-17	:	YAT 2.0 Gamma 2'				1.99.51	1.0.16	3.5.13	1.0.13	0.9.14		1.5.0	1.5.0	1.2.1		1160
	2016-09-16	:	YAT 2.0 Gamma 2				1.99.50	1.0.15	3.5.12	1.0.12	0.9.13		1.5.0	1.5.0	1.2.1		1158
	2015-06-13	:	YAT 2.0 Gamma 1''				1.99.34	1.0.13	3.5.11	1.0.10			1.4.1	1.4.1	1.2.0		799
	2015-06-07	:	YAT 2.0 Gamma 1'				1.99.33	1.0.12	3.5.10	1.0.9			1.4.0	1.4.0	1.2.0		778
	2015-06-01	:	YAT 2.0 Gamma 1				1.99.32	1.0.11	3.5.9	1.0.8			1.4.0	1.4.0	1.2.0		769
	2013-02-02	:	YAT 2.0 Beta 4 Candidate 2				1.99.30	1.0.9	3.5.7	1.0.6			1.3.1	1.3.1	1.1.1		626
	2011-12-05	:	YAT 2.0 Beta 4 Candidate 1				1.99.28	1.0.7	3.5.5	1.0.4			1.3.0	1.3.0	1.1.0		502
	2011-04-25	:	YAT 2.0 Beta 3 Candidate 4				1.99.26	1.0.5	3.5.3	1.0.2			1.2.4	1.2.9	1.0.0		419
	2010-11-28	:	YAT 2.0 Beta 3 Candidate 3				1.99.25	1.0.4	3.5.2	1.0.1			1.2.4	1.2.9	1.0.0		385
	2010-11-11	:	YAT 2.0 Beta 3 Candidate 2				1.99.24	1.0.4	3.5.2	1.0.1			1.2.4	1.2.8	1.0.0		369
	2009-09-10	:	YAT 2.0 Beta 3 Candidate 1'				1.99.23	1.0.1	3.5.0				1.2.4	1.2.7	1.0.0		251
	2009-09-08	:	YAT 2.0 Beta 3 Candidate 1				1.99.22	1.0.1	3.5.0				1.2.3	1.2.6	1.0.0		247
	2008-07-18	:	YAT 2.0 Beta 2 Candidate 4				1.99.20	1.0.0	1.2.0				1.2.3	1.2.5	1.0.0		201
	2008-04-01	:	YAT 2.0 Beta 2 Candidate 3				1.99.19					1.2.2	1.2.4	1.0.0		136
	2008-03-17	:	YAT 2.0 Beta 2 Candidate 2				1.99.18					1.2.2	1.2.3	1.0.0		122
	2008-02-11	:	YAT 2.0 Beta 2 Candidate 1				1.99.17					1.2.2	1.2.2	1.0.0		105
	2007-08-30	:	YAT 2.0 Beta 2 Preliminary				1.99.13					1.2.1	1.2.1	1.0.0		(45)
	2007-04-15	:	YAT 2.0 Beta 1				1.99.12					1.2.0	1.2.0			9
	2007-02-25	:	YAT 2.0 Alpha 3				1.99.8					1.1.2	1.1.2
	2007-02-07	:	YAT 2.0 Alpha 2				1.99.3					1.1.1	1.1.1
	2007-01-23	:	YAT 2.0 Alpha 1				1.99.0					1.1.0	1.1.0
	2003-10-31	:	XTerm232				1.0.2					1.0.1	1.0.1
	2003-10-30	:	XTerm232				1.0.1					1.0.1	1.0.1
	2003-10-14	:	XTerm232				1.0.0					1.0.0	1.0.0

## 1. Regression Testing
				Duration	Step		Total

1.				Regression Testing		00:00	11:30	00:00	11:30

	1.1.			Run coding style checks		01:00		01:00
		1.1.1.		Use StyleCop on 'Debug Test'
				> "Visual Studio > Tools > Run StyleCop (Rescan All)"

				1 expected warning:
				SA1409 : CSharp.Maintainability @ YAT.Model.Terminal.cs

				Note: Rescan just takes a few seconds, but expect quite some time for fixes

	1.2.			Run assembly checks		02:00		03:00
		1.2.1.		Build 'Debug Test'

		1.2.2.		Use FxCop 'MKY.Debug' on 'Debug Test'
				> Open and verify "\MKY\MKY.Debug.FxCop"

				26 expected warnings:
				CA2214 : DoNotCallOverridableMethodsInConstructors @ 26 locations

		1.2.3.		Use FxCop 'NUnit.Debug' on 'Debug Test'
				> Open and verify "\NUnit\NUnit.Debug.FxCop"

		1.2.4.		Use FxCop 'YAT.Debug' on 'Debug Test'
				> Open and verify "\YAT\YAT.Debug.FxCop"

				135 expected errors/warnings:
				CA1002 : DoNotExposeGenericLists @ 52 locations
				CA2214 : DoNotCallOverridableMethodsInConstructors @ 83 locations

				Note: Rescan just takes a few seconds, but expect quite some time for fixes

	1.3.			Run automated tests		06:00		09:00
		1.3.1.		Ensure to select 'YAT.Test' as the 'StartUp' project

				Note: 'YAT' or 'YATConsole' don't have dependencies to the test projects, thus they will not get built!

		1.3.2.		Build 'Debug Test'

		1.3.3.		Use NUnit on 'Debug Test'
				> "Visual Studio > Tools > NUnit" (Alt+N)
				> Categories = Select and exclude all longer than a minute
				> "Project > Configurations > Debug" ('Debug' @ regression + 'Release' @ final)

				Expected errors/warnings:
				MKY.IO.Ports.Test.SerialPort.ConnectionTest.TestDisconnectReconnect...() fail when running in sequence with previous tests, pass when running as single test
				MKY.IO.Usb.Test.ConnectionTest is not yet implemented => Assert.Ignore() => yellow bar
				YAT.Controller.Test: Note #250 "ControllerTest modifies the current working-copy settings" + #350 Interactive ControllerTests may fail because current application settings are used" => Simply run the tests again
				YAT.Model.Test.ConnectionTest.TestDisconnectReconnectSerialPort fails when running in sequence with previous tests, passes when running as single test
				YAT.Model.Test.FileHandlingTest fails because of the issue described in FR#272 => Dispose() must temporarily be commented-out (for running the test) in Model.Main#1181/Workspace#1143/Terminal#2010
				YAT.Model.Test.StressTest is not yet implemented => Assert.Ignore() => yellow bar
				YAT.Model.Test.Transmission.*.IPLoopbacks fail for 'OnSpecificIPv4/6Interface', install/config of "TAP-Win32 Adapter" is required
				YAT.Model.Test.Transmission.MTSicsDeviceTest fail for COM and USB due to received XOn/XOff characters, handling/subtraction of them is required
				YAT.Model.Test.Transmission.OneWay.LoopbackSelfs fail at 'SingleNoEOL', 'DoubleNoEOL', 'StillEol3', 'Clear1/2' because Tx results in a line (DirChangeLineBreak)
				YAT.Model.Test.Transmission.Repeating.LoopbackSelfs fail at '*TwoWay' because Tx results in line(s) (DirChangeLineBreak)
				YAT.Model.Test.Transmission.TwoWay.LoopbackSelfs fail because Tx results in line(s) (DirChangeLineBreak)
				YAT.Settings.Test.FileVersionsTest [01|02] of V1.99.13/17/18/19 fail (bugs #232 and #246 "Issues with [Alternate]TolerantXmlSerializer")
				YAT.Settings.Test.FileVersionsTest [03|07] before V1.99.50 fail (bugs #232 and #246 "Issues with [Alternate]TolerantXmlSerializer")
				YAT.View.Test.StressTest: Note #349 "StressTest uses the current application settings"

				Note: If everything works fine (rarely the case…), run takes around 60 minutes, but expect quite some time for fixes

	1.4.			Run manual tests		02:30		11:30
		1.4.1.		According to manual test cases in "\YAT\_Doc.Project\5 - Test\YAT – Test.ods" using 'Release' configuration

## 2. Preparation
				Duration	Step		Total

2.				Preparation		00:00	01:45	11:30	13:15

	2.1.			Set versions		00:15		11:45
		2.1.1.		Ensure that product version in ALAZ.Version is different than at last release
		2.1.2.		Ensure that product version in netrtfwriter AssemblyInfo is different than at last release
				> Versions must differ to ensure proper installation/update!
				> Additional increment makes little sense as there are no version tags in file header
		2.1.3.		Increment product version in MKY.Version
		2.1.4.		Increment product version in NUnit.Version
		2.1.5.		Increment product version in YAT.Version
				> Versions must differ to ensure proper installation/update!
		2.1.6.		Set product version in MKY file headers (*.cs)
				> Also remove 'Development', e.g. '// MKY Version 1.0.12'
		2.1.7.		Set product version in NUnit file headers (*.cs)
				> Also remove 'Development', e.g. '// NUnit Version 1.0.9'
		2.1.8.		Set product version in YAT file headers (*.cs)
				> Also remove 'Development', e.g. '// YAT 2.0 Gamma 1 Version 1.99.33'
		2.1.9.		Set product name post fix in "YAT.Application.ApplicationEx"
				> Remove 'Development'
		2.1.10.		Fill date and versions into 'The YAT story' in '0. Overview'

	2.2.			Set installation version		00:05		11:50
		2.2.1.		Set product title in "YAT.Setup.x86"
		2.2.2.		Set product version in "YAT.Setup.x86"
		2.2.3.		Set product title in "YAT.Setup.x64"
		2.2.4.		Set product version in "YAT.Setup.x64"

	2.3.			Commit		00:05		11:55
		2.3.1.		Commit changes to SVN
				> Check the property status of each file
				> Ensure not to commit modified settings file(s)

	2.4.			Update settings defaults and schema in "YAT\!-Settings\!-Current"		00:30		12:25
		2.4.1.		Update settings versions if required
		2.4.2.		Fill settings versions into '0. Overview'
		2.4.3.		Create files using NUnit on 'Debug Test'
				> Build "Debug Test"
				> "Visual Studio > Tools > NUnit" (Alt+N)
				> YAT.Settings.Test.SettingsFilesArchiver
				(Note that explicit tests are only runable if no include/exclude filter is active)
		2.4.4.		Diff and verify the files in "YAT\!-Settings\!-Current"
				> Restore the <FileType> tag to YAT (result of NUnit)
				> Manually set the <ProductVersion> tag to the YAT version (result of NUnit)
		2.4.5.		Diff and verify the files in "YAT\!-Settings\!-Current" against the *SettingsDefault.xml
				> Update default values if they have changed

	2.5.			Add new settings defaults and schema to settings archive		00:05		12:30
		2.5.1.		Archive the upgraded files in "YAT\!-Settings\<New Version>"

	2.6.			Upgrade settings in settings archive "YAT\!-Settings\!-Current"		00:30		13:00
		2.6.1.		Upgrade settings
				> Delete all "YAT Local Settings" or copy default settings there (ensure that window size is defaulted)
				> Ensure that "YAT\!-Settings\!-Current" contains exact clones of the previous version
				> Run YAT and open old settings
				> Modify settings
				> For terminals, change 'Toolbar > Radix' to ensure that IO settings are kept
				> For workspaces, change 'Window > Always On Top' to ensure that terminal settings are kept
				> Undo changes
				> Save upgraded but unchanged settings
		2.6.2.		Diff and verify the new settings

	2.7.			Add new settings to settings archive		00:10		13:10
		2.7.1.		Archive the upgraded files in "YAT\!-Settings\<New Version>"
		2.7.2.		Add new settings to "YAT.Settings.Test.SettingsFilesProvider"
		2.7.3.		Add new settings to "YAT.Settings.Test.FileVersionsTest"

	2.8.			Rebuild and commit		00:05		13:15
		2.8.1.		Build 'Debug Test' (ensure no build errors)
		2.8.2.		Commit changes to SVN

## 3. Final Testing
				Duration	Step		Total

3.				Final Testing		00:00	01:30	13:15	14:45

	3.1.			Re-Run coding style checks		00:10		13:25
		3.1.1.		Use StyleCop on 'Debug Test'
				> "Visual Studio > Tools > Run StyleCop (Rescan All)"

				1 expected warning:
				SA1409 : CSharp.Maintainability @ YAT.Model.Terminal.cs

				Note: Rescan just takes a few seconds, and there should be no more findings

	3.2.			Re-Run assembly checks		00:10		13:35
		3.2.1.		Build 'Debug Test'

		3.2.2.		Use FxCop 'MKY.Debug' on 'Debug Test'
				> Open and verify "\MKY\MKY.Debug.FxCop"

				26 expected warnings:
				CA2214 : DoNotCallOverridableMethodsInConstructors @ 26 locations

		3.2.3.		Use FxCop 'NUnit.Debug' on 'Debug Test'
				> Open and verify "\NUnit\NUnit.Debug.FxCop"

		3.2.4.		Use FxCop 'YAT.Debug' on 'Debug Test'
				> Open and verify "\YAT\YAT.Debug.FxCop"

				135 expected errors/warnings:
				CA1002 : DoNotExposeGenericLists @ 52 locations
				CA2214 : DoNotCallOverridableMethodsInConstructors @ 83 locations

				Note: Rescan just takes a few seconds, and there should be no more findings

	3.3.			Re-run automated tests		01:00		14:35
		3.3.1.		Ensure to select 'YAT.Test' as the 'StartUp' project

				Note: 'YAT' or 'YATConsole' don't have dependencies to the test projects, thus they will not get built!

		3.3.2.		Build 'Release Test'

		3.3.3.		Use NUnit on 'Release Test'
				> "Visual Studio > Tools > NUnit" (Alt+N)
				> Categories = Select and exclude all longer than a minute
				> "Project > Configurations > Release" (Debug @ Regression + Release @ Final)

				Expected errors/warnings:
				MKY.IO.Ports.Test.SerialPort.ConnectionTest.TestDisconnectReconnect...() fail when running in sequence with previous tests, pass when running as single test
				MKY.IO.Usb.Test.ConnectionTest is not yet implemented => Assert.Ignore() => yellow bar
				YAT.Controller.Test: Note #250 "ControllerTest modifies the current working-copy settings" + #350 Interactive ControllerTests may fail because current application settings are used" => Simply run the tests again
				YAT.Model.Test.ConnectionTest.TestDisconnectReconnectSerialPort fails when running in sequence with previous tests, passes when running as single test
				YAT.Model.Test.FileHandlingTest fails because of the issue described in FR#272 => Dispose() must temporarily be commented-out (for running the test) in Model.Main#1181/Workspace#1143/Terminal#2010
				YAT.Model.Test.StressTest is not yet implemented => Assert.Ignore() => yellow bar
				YAT.Model.Test.Transmission.*.IPLoopbacks fail for 'OnSpecificIPv4/6Interface', install/config of "TAP-Win32 Adapter" is required
				YAT.Model.Test.Transmission.MTSicsDeviceTest fail for COM and USB due to received XOn/XOff characters, handling/subtraction of them is required
				YAT.Model.Test.Transmission.OneWay.LoopbackSelfs fail at 'SingleNoEOL', 'DoubleNoEOL', 'StillEol3', 'Clear1/2' because Tx results in a line (DirChangeLineBreak)
				YAT.Model.Test.Transmission.Repeating.LoopbackSelfs fail at '*TwoWay' because Tx results in line(s) (DirChangeLineBreak)
				YAT.Model.Test.Transmission.TwoWay.LoopbackSelfs fail because Tx results in line(s) (DirChangeLineBreak)
				YAT.Settings.Test.FileVersionsTest [01|02] of V1.99.13/17/18/19 fail (bugs #232 and #246 "Issues with [Alternate]TolerantXmlSerializer")
				YAT.Settings.Test.FileVersionsTest [03|07] before V1.99.50 fail (bugs #232 and #246 "Issues with [Alternate]TolerantXmlSerializer")
				YAT.View.Test.StressTest: Note #349 "StressTest uses the current application settings"

				Note: If everything works fine (rarely the case…), run takes around 60 minutes, and there should be no more findings

	3.4.			Check and commit		00:10		14:45
		3.4.1.		Ensure no debug left-overs by globally searching for "Debug.Write"
				> Match case
				> No match whole word

				100 occurrences totally expected in ArgsHandler, Diagnostics, Usb, Hid,...

		3.4.2.		Ensure no debug left-overs by globally searching for "Trace.Write"
				> Match case
				> No match whole word

				272 occurrences totally expected in Diagnostics and Serializer, as well as many 'Test' assemblies

		3.4.3.		Commit changes to SVN
				> Ensure not to commit modified settings file(s)

## 4. Build
				Duration	Step		Total

4.				Build		00:00	00:40	14:45	15:25

	4.1.			Finalize release notes		00:10		14:55
		4.1.1.		Add them cumulatively to "\!-Doc.User\YAT Release Notes.txt"
		4.1.2.		Check whether release notes are complete
		4.1.3.		Check whether limitations still apply
		4.1.4.		Update the road map if necessary

	4.2.			Prepare package directory		00:10		15:05
		4.2.1.		Add a new directory to the offline archive "\YAT\Releases and Checkpoints"
		4.2.2.		Check and update year of "!-ReadMe.txt" in the release package directories
		4.2.3.		Copy the release notes to all package directories
		4.2.4.		Also copy them to the distribution root and rename to "YAT Release Notes - ReadMe.txt"
				> SourceForge requires the file to contain 'readme' in the name

				Note: The distribution packages will be packed in a further step

	4.3.			Build packages		00:20		15:25
		4.3.1.		Check "YAT.Setup.x86|x64" prerequisites for "Setup"
				> Optimize for speed
		4.3.2.		Check "YAT.Setup.x86|x64" prerequisites for "Setup with Prerequisites"
				> Optimize for size
		4.3.3.		Build > Batch Build > Clean ALL configuration for ALL target platforms
				> Reduces the risk of mistakenly taking the wrong assemblies
				> Check the intermediate folders of "\YAT\YAT\bin"
		4.3.4.		Build "x86"
				> Build "Release" configuration for "x86"
				> Build "Setup" configuration for "x86"
				> Build "Setup with Prerequisites" configuration for "x86"
		4.3.5.		Build "AnyCPU" (reason see FR#229)
				> Build "Release" configuration for "AnyCPU"
				> Build "Setup" configuration for "AnyCPU"
				> Build "Setup with Prerequisites" configuration for "AnyCPU"

## 5. Installation Testing
				Duration	Step		Total

5.				Installation Testing		00:00	00:40	15:25	16:05

	5.1.			Installation		00:10		15:35
		5.1.1.		Close Visual Studio
				> Needed to ensure that YAT doesn't detect already running "YAT.vshost.exe" on startup
		5.1.2.		Install YAT

	5.2.			Run manual after-installation tests		00:30		16:05
		5.2.1.		Run according to manual after-installation test cases

## 6. Packaging
				Duration	Step		Total

6.				Packaging		00:00	00:30	16:05	16:35

	6.1.			Commit and tag YAT		00:15		16:20
		6.1.1.		Commit any modifications to the subversion repository
				> Message e.g. "YAT 2.0 Gamma 1 Version 1.99.32"
		6.1.2.		Fill SVN revision into 'The YAT story' in '0. Overview'
		6.1.3.		Tag/checkpoint the project
				> SVN > Repo-browser
				> Select 'trunk' in tree-view
				> Copy to...
				> New name e.g. "<...>/tags/yat-1-99-32-gamma-1"
				> Message e.g. "YAT 2.0 Gamma 1 Version 1.99.32"
				> Unfold 'tags'
				> Check new tag

	6.2.			Pack YAT		00:15		16:35
		6.2.1.		Update the 4 folders in "<Offline\Releases>\Distribution"
		6.2.2.		Create the 4 according distribution files
				> "YAT-2.0_Gamma-1_Version-1.99.32_x64_(64-bit).zip"
				> "YAT-2.0_Gamma-1_Version-1.99.32_x64_(64-bit)_with_.NET_runtime.zip"
				> "YAT-2.0_Gamma-1_Version-1.99.32_x86_(32-bit).zip"
				> "YAT-2.0_Gamma-1_Version-1.99.32_x86_(32-bit)_with_.NET_runtime.zip"

				Note:
				Bugs #318 and #323 suggested to only distribute .msi for easier use.
				However, IE10+ by default does not allow to download (SHA1) .msi !!!
				New FR#274 “Find a way to distribute as .msi only” created

## 7. Upload
				Duration	Step		Total

7.				Upload		00:00	01:00	16:05	17:05

	7.1.			Prepare upload to SourceForge		00:10		16:15
		7.1.1.		Log in as 'y-a-terminal'
		7.1.2.		Go to 'SourceForge > YAT > Files > YAT 2.0'
		7.1.3.		Add release folder (e.g. "Version 1.99.32 - YAT 2.0 Gamma 1")

				HowTo:
				<https://sourceforge.net/apps/trac/sourceforge/wiki/Release%20files%20for%20download>

	7.2.			Add release		00:30		16:45
		7.2.1.		Upload distributions using the web interface
				> Intended order: RelNotes – x86.NET – x86 – x64.NET – x64
				> Manually upload for proper sequence !!!
				> Upload takes approx. 20 minutes (for ~450 MB)
		7.2.2.		Tick default platform download on normal x64 distribution
		7.2.3.		Also upload release notes to the parent folder
		7.2.4.		Also upload release notes to the root folder

	7.3.			Check release and release notes		00:10		16:55
		7.3.1.		Reload YAT web page
				> It takes a moment until the uploaded files are ready for download
		7.3.2.		Download all files with Firefox
		7.3.3.		Verify contents of .msi / .zip
				> At least open the ReadMe or RelNotes
		7.3.4.		Download all files with Internet Explorer
				> Verifies digital signature issues…

	7.4.			Feature request and bug trackers		00:10		17:05
		7.4.1.		Check that items that are covered by this release have been closed

## 8. Finalization
				Duration	Step		Total

8.				Finalization		00:00	02:10	17:05	18:55

	8.1.			Submit news		00:15		17:20
		8.1.1.		Go to 'Develop > News'
		8.1.2.		Add news
				Title:
				"YAT 2.0 Gamma 1 Version 1.99.32"
				Text:
				"<Intro of release mail>"

				HowTo:
				<https://sourceforge.net/apps/trac/sourceforge/wiki/News>

	8.2.			Send e-mail to the YAT mailing list (Attention: Mail delay up to 60 min !!!)		00:15		17:35
		8.2.1.		Check/update mailing list
		8.2.2.		Write e-mail based on earlier mailings
				> Make sure that links are updated completely, i.e. link text and link below
				> Make sure the correct release notes are used
		8.2.3.		Check spelling
		8.2.4.		Send as "y-a-terminal@users.sourceforge.net"
		8.2.5.		Send to "y-a-terminal-users@lists.sourceforge.net"
		8.2.6.		Send encoded in Unicode
				> Thunderbird: Options > Encoding > Unicode
		8.2.7.		Send as Text+HTML
				> Thunderbird: Options > Format > Text+HTML
		8.2.8.		Save e-mail in offline archive "\Distribution"
		8.2.9.		(Accept e-mail as moderator in mailman if needed)
				> Has not been necessary for recent releases

	8.3.			Commit		00:05		17:40
		8.3.1.		Commit any modifications during the release process to the subversion repository
		8.3.2.		Log out as 'y-a-terminal'

	8.4.			Recreate and verify working copy		00:15		17:55
		8.4.1.		Rename the existing working copy to "Trunk_<New Date>" (e.g. _2013-02-02)
		8.4.2.		Remove existing backups "Trunk_<Old Date>"
		8.4.3.		Check for updates of TortoiseSVN and AnkhSVN
		8.4.4.		Create a new folder "Trunk"
		8.4.5.		Check the head revision out into "Trunk"
				> Make sure that only "...\code\trunk\" is checked out, not the whole repository
		8.4.6.		Open the YAT solution
		8.4.7.		Fold all projects
		8.4.8.		Set 'YAT' as the active startup project
		8.4.9.		Build "Debug Test" and "Release Test" to ensure that all files are committed

	8.5.			Archive		00:15		18:10
		8.5.1.		Export the new working copy to offline archive "<Version>\Working Copy"
				> Use 'SVN > Export...'
		8.5.2.		Pack the copy into a properly named zip file

	8.6.			Update and verify working copy (wait for a few days in case of a severe issue)		00:15		18:25
		8.6.1.		Increment product version in ALAZ.Version
		8.6.2.		Increment product version in netrtfwriter AssemblyInfo
				> All versions must be incremented to ensure proper installation/update!
		8.6.3.		Increment product version in MKY.Version
		8.6.4.		Set product version in MKY file headers
				> Add 'Development', e.g. '// MKY Development Version 1.0.14'
		8.6.5.		Increment product version in netrtfwriter\RtfWriter\Properties\AssemblyInfo.cs
		8.6.6.		Increment product version in NUnit.Version
		8.6.7.		Set product version in NUnit file headers
				> Add 'Development', e.g. '// NUnit Development Version 1.0.11'
		8.6.8.		Increment product version in YAT.Version
		8.6.9.		Set product version in YAT file headers
				> Add 'Development', e.g. '// YAT 2.0 Gamma 2 Development Version 1.99.35'
		8.6.10.		Set product name post fix in "YAT.Application.ApplicationEx"
				> Add 'Development' to clearly state that files are non-released revisions
		8.6.11.		Add a new section to the release notes
				> Copy limitations and known issues from last release
		8.6.12.		Verify that the solution still properly builds and runs

	8.7.			Update statistics		00:15		18:40
		8.7.1.		Update "\YAT\!-Doc.SourceForge\"

	8.8.			Commit		00:05		18:45
		8.8.1.		Commit modifications to the subversion repository

	8.9.			Backup PC		00:30		18:55
		8.9.1.		Offline archive
		8.9.2.		Sandboxes