## MKY.IO.Ports
#	Functionality	Test	Stimulus	Expected	Remarks

	Break State				Using RS-232 hardware, see "YAT - BreakStateTest.jpg"

## YAT.Gui.Forms.Main
#	Functionality	Test	Stimulus	Expected	Remarks

	Startup position		Start YAT
			Place YAT onto primary screen
			Exit
			Start YAT again	YAT starts on primary screen

			Start YAT
			Place YAT onto secondary screen
			Exit
			Start YAT again	YAT starts on secondary screen

			Start YAT
			Place YAT onto secondary screen
			Exit
			Remove secondary screen
			Start YAT again	YAT must start on primary screen

## YAT.Gui.Forms.Terminal
#	Functionality	Test	Stimulus	Expected	Remarks

	Copy-paste	Single line	Send a line
			Copy a sent line and paste it into the "Send Command" text box	Command is available for send
			Send the line again	Command is sent exactly the same as before
		Multiple lines	Copy multiple lines and paste them into a text editor	All characters of all lines are pasted into the text file
		Formatted lines	Copy multiple lines and paste them into a word processer	All characters of all lines are properly formatted

	Send command	Keys	Enter a valid command
			Hit 'Enter'	Command is sent
			Leave text box with tab and forward to "Send Command"
			Hit 'Enter' again	Command is sent
			Use shortcut 'F3' to send	Command is sent
		Validation	Enter an invalid command
			Hit 'Enter'	MsgBox including error message with error character
			Hit 'Enter' again	MsgBox including error message with error character
			Leave text box with tab	MsgBox including error message with error character
			Leave text box with tab again	MsgBox including error message with error character

	Predefined	Single line command	Create a command	Button gets activated
			Send the command
			Send the command by shortcut
		Tab order	Tab must forward from left to right
		Keys	Enter a valid command
			Hit 'Enter'	Dialog is quit and command is available
			Send the command	Command is sent
		Validation	Enter an invalid command
			Hit 'Enter'	MsgBox including error message with error character
			Hit 'Enter' again	MsgBox including error message with error character
			Leave text box with tab	MsgBox including error message with error character
			Leave text box with tab again	MsgBox including error message with error character

## Installation
#	Functionality	Test	Stimulus	Expected	Remarks

	File system	Files	Open "C:\Program Files\YAT"	DejaVu Info / MKY / YAT / Release Notes / No test projects
				Timestamp of all files must be build time

	System	Installed Software	Open "System > Software"	YAT is shown once only	Old versions are replaced automatically
				YAT is shown with the correct version

	System	Start	Open "Start > Programs"	YAT must be shown

	YAT	Initial start	Start "Start > Programs > YAT > YAT"	YAT must start with latest settings
		Terminals	Create 2 interconnected serial COM port terminals	Terminals must get created
			Send some data back and forth	Data must be sent back and forth
			Define a few predefined commands	Commands must be usable to send data back and forth
			Ensure that there are some command recents	Commands must be usable to send data back and forth
			Ensure that there are some file recents	Files must be usable to send data back and forth
		Exit	Exit	Workspace including terminals must be auto-saved
		Subsequent start	Start "Start > Programs > YAT > YAT"	Workspace including terminals must be restored
			Send some data back and forth	Data must be sent back and forth
			Use previously predefined commands	Commands must be usable to send data back and forth
			Use command recents	Commands must be usable to send data back and forth
			Use file recents	Files must be usable to send data back and forth
		Workspace	"File > Workspace > Close"	Workspace must be closed without exceptions

		.yat	Create 2 interconnected TCP/IP AutoSocket terminals	Terminals must get interconnected
			Save terminals manually	Files must get created
			"File > Workspace > Close"	Workspace must be closed without exceptions
			"File > Open"	First terminal must be opened
			"File > Recent"	Second terminal must be opened
		.yat	Save workspace manually	File must get created
			Exit
		Command line	Double-click one of the terminal .yat	YAT and terminal must be opened
			Double-click the workspace .yaw	YAT and terminals must be opened

		About	"Help > About"	Check year
		Release Notes	"Help > Release Notes"	Check year