## 0. Overview
A YAT release is done in 8 steps:
		Step		Duration	of Step	in Total
		1.	Regression Testing		13:30	13:30
		2.	Preparation		01:40	15:10
		3.	Final Testing		01:30	16:40
		4.	Build		00:40	17:20
		5.	Installation Testing		00:40	17:55
		6.	Packaging		00:40	17:55
		7.	Upload		01:20	19:15
		8.	Finalization		03:45	22:30

The YAT story:
	Date		Designation				YAT	MKY	ALAZ	NUnit	netrtf.		LU.xml	RU.xml	.yac	.yacp	.yacps	.yat	.yaw		SVN		Remarks
	2020-0x-xx	:	YAT 2.2.0				2.2.0	1.0.28	3.5.24	1.0.22	0.9.25		1.7.0	1.2.1	1.0.2	1.0.2	1.0.2	1.7.1	1.2.3		2600		No longer implementing twice
	2019-10-04	:	YAT 2.1.0				2.1.0	1.0.27	3.5.23	1.0.21	0.9.24		1.7.0	1.2.0	1.0.2	1.0.2	1.0.2	1.7.0	1.2.3		2553		Version of 3rd party assemblies also incremented twice to prevent potential version conflicts at those who have tested the preliminary versions.
	2018-04-13	:	YAT 2.0 Final				2.0.0	1.0.25	3.5.21	1.0.19	0.9.22		1.6.0	1.1.0	(1.0.2)	(1.0.2)	(1.0.2)	1.6.0	1.2.3		1919		Version of 3rd party assemblies also incremented twice to prevent potential version conflicts at those who have tested the preliminary versions.
	2018-01-12	:	YAT 2.0 Epsilon				1.99.90	1.0.23	3.5.19	1.0.18	0.9.20		1.5.3	1.0.0	(1.0.2)	(1.0.2)	(1.0.2)	1.5.3	1.2.2		1815		Version of 3rd party assemblies also incremented twice to prevent potential version conflicts at those who have tested the preliminary versions.
	2017-10-15	:	YAT 2.0 Delta				1.99.80	1.0.21	3.5.17	1.0.17	0.9.18		1.5.2		(1.0.2)	(1.0.2)	(1.0.2)	1.5.2	1.2.1		1603		Version of 3rd party assemblies also incremented twice to prevent potential version conflicts at those who have tested the preliminary versions.
	2017-07-04	:	YAT 2.0 Gamma 3				1.99.70	1.0.19	3.5.15	1.0.16	0.9.16		1.5.1		(1.0.2)	(1.0.2)	(1.0.2)	1.5.1	1.2.1		1410
	2016-09-30	:	YAT 2.0 Gamma 2''				1.99.52	1.0.17	3.5.14	1.0.14	0.9.15		1.5.0		(1.0.2)	(1.0.2)	(1.0.2)	1.5.0	1.2.1		1190		No longer testing settings; settings equal 1.99.50.
	2016-09-17	:	YAT 2.0 Gamma 2'				1.99.51	1.0.16	3.5.13	1.0.13	0.9.14		1.5.0		(1.0.2)	(1.0.2)	(1.0.2)	1.5.0	1.2.1		1162		No longer testing settings; settings equal 1.99.50.
	2016-09-16	:	YAT 2.0 Gamma 2				1.99.50	1.0.15	3.5.12	1.0.12	0.9.13		1.5.0		(1.0.2)	(1.0.2)	(1.0.2)	1.5.0	1.2.1		1159		Issue with FileVersionsTest.TerminalSettingsCase07 (bugs #232 and #246 "Issues with [Alternate]TolerantXmlSerializer").
	2015-06-13	:	YAT 2.0 Gamma 1''				1.99.34	1.0.13	3.5.11	1.0.10			1.4.1		(1.0.2)	(1.0.2)	(1.0.2)	1.4.1	1.2.0		799
	2015-06-07	:	YAT 2.0 Gamma 1'				1.99.33	1.0.12	3.5.10	1.0.9			1.4.0		(1.0.2)	(1.0.2)	(1.0.2)	1.4.0	1.2.0		778		No longer testing settings; settings equal 1.99.32.
	2015-06-01	:	YAT 2.0 Gamma 1				1.99.32	1.0.11	3.5.9	1.0.8			1.4.0		(1.0.2)	(1.0.2)	(1.0.2)	1.4.0	1.2.0		769
	2013-02-02	:	YAT 2.0 Beta 4 Candidate 2				1.99.30	1.0.9	3.5.7	1.0.6			1.3.1		(1.0.1)	(1.0.1)	(1.0.1)	1.3.1	1.1.1		626
	2011-12-05	:	YAT 2.0 Beta 4 Candidate 1				1.99.28	1.0.7	3.5.5	1.0.4			1.3.0		(1.0.1)	(1.0.1)	(1.0.1)	1.3.0	1.1.0		502
	2011-04-25	:	YAT 2.0 Beta 3 Candidate 4				1.99.26	1.0.5	3.5.3	1.0.2			1.2.4		(1.0.1)	(1.0.1)	(1.0.1)	1.2.9	1.0.0		419
	2010-11-28	:	YAT 2.0 Beta 3 Candidate 3				1.99.25	1.0.4	3.5.2	1.0.1			1.2.4		(1.0.1)	(1.0.1)	(1.0.1)	1.2.9	1.0.0		385
	2010-11-11	:	YAT 2.0 Beta 3 Candidate 2				1.99.24	1.0.4	3.5.2	1.0.1			1.2.4		(1.0.1)	(1.0.1)	(1.0.1)	1.2.8	1.0.0		369
	2009-09-10	:	YAT 2.0 Beta 3 Candidate 1'				1.99.23	1.0.1	3.5.0				1.2.4		(1.0.0)	(1.0.0)	(1.0.0)	1.2.7	1.0.0		251		No longer testing settings; version has been outdated.
	2009-09-08	:	YAT 2.0 Beta 3 Candidate 1				1.99.22	1.0.1	3.5.0				1.2.3		(1.0.0)	(1.0.0)	(1.0.0)	1.2.6	1.0.0		247		No longer testing settings; version has been outdated.
	2008-07-18	:	YAT 2.0 Beta 2 Candidate 4				1.99.20	1.0.0	1.2.0				1.2.3					1.2.5	1.0.0		201		No longer testing settings; version has been outdated.
	2008-04-01	:	YAT 2.0 Beta 2 Candidate 3				1.99.19					1.2.2					1.2.4	1.0.0		136		No longer testing settings; version has been outdated.
	2008-03-17	:	YAT 2.0 Beta 2 Candidate 2				1.99.18					1.2.2					1.2.3	1.0.0		122		No longer testing settings; version has been outdated.
	2008-02-11	:	YAT 2.0 Beta 2 Candidate 1				1.99.17					1.2.2					1.2.2	1.0.0		105		No longer testing settings; version has been outdated.
	2007-08-30	:	YAT 2.0 Beta 2 Preliminary				1.99.13					1.2.1					1.2.1	1.0.0		(45)		No longer testing settings; version has been outdated.
	2007-04-15	:	YAT 2.0 Beta 1				1.99.12					1.2.0					1.2.0			9		No longer testing settings; version has been outdated.
	2007-02-25	:	YAT 2.0 Alpha 3				1.99.8					1.1.2					1.1.2					No longer testing settings; version has been outdated.
	2007-02-07	:	YAT 2.0 Alpha 2				1.99.3					1.1.1					1.1.1					No longer testing settings; version has been outdated.
	2007-01-23	:	YAT 2.0 Alpha 1				1.99.0					1.1.0					1.1.0					No longer testing settings; version has been outdated.
	2003-10-31	:	XTerm232				1.0.2					1.0.1					1.0.1					No longer testing settings; version has been outdated.
	2003-10-30	:	XTerm232				1.0.1					1.0.1					1.0.1					No longer testing settings; version has been outdated.
	2003-10-14	:	XTerm232				1.0.0					1.0.0					1.0.0					No longer testing settings; version has been outdated.

## 1. Regression Testing
				Duration	Step		Total

1.				Regression Testing		00:00	13:30	00:00	13:30

	1.1.			Run coding style checks		00:30		00:30
		1.1.1.		Use StyleCop on 'Debug Test'.
				> "Visual Studio > Tools > Run StyleCop (Rescan All)".

				Note: Rescan just takes a few seconds, but expect quite some time for fixes.

	1.2.			Run assembly checks		01:00		01:30
		1.2.1.		Ensure to select 'YAT.Test' as the 'StartUp' project.

				Note: 'YAT' and 'YATConsole' don't have dependencies to the test projects, thus those would not get built!

		1.2.2.		Build 'Debug Test' using ‘Build Solution’ / [F6]. (Explicitly building ‘YAT.Test’ would not build the .exe projects!)

		1.2.3.		Use FxCop 'MKY.Debug' on 'Debug Test'.
				> Open and verify "\MKY\MKY.Debug.FxCop".

				48 expected warnings:
				CA1002 : DoNotExposeGenericLists @ 9 locations.
				CA2214 : DoNotCallOverridableMethodsInConstructors @ 39 locations.

		1.2.4.		Use FxCop 'NUnit.Debug' on 'Debug Test'.
				> Open and verify "\NUnit\NUnit.Debug.FxCop".

		1.2.5.		Use FxCop 'YAT.Debug' on 'Debug Test'.
				> Open and verify "\YAT\YAT.Debug.FxCop".

				234 expected errors/warnings:
				CA1002 : DoNotExposeGenericLists @ 108 locations.
				CA2214 : DoNotCallOverridableMethodsInConstructors @ 126 locations.

				Note: Rescan just takes a few seconds, but expect quite some time for fixes.

	1.3.			Run automated tests		06:00		07:30
		1.3.1.		Ensure that test environment is fully ready (VSPE, loopbacks, MT-SICS,…).

		1.3.2.		Ensure to select 'YAT.Test' as the 'StartUp' project.

				Note: 'YAT' and 'YATConsole' don't have dependencies to the test projects, thus those would not get built with 'YAT'!

		1.3.3.		Build 'Debug Test' using ‘Build Solution’ / [F6]. (Explicitly building ‘YAT.Test’ would not build the .exe projects!)

		1.3.4.		Use NUnit on 'Debug Test'.
				> "Visual Studio > Tools > NUnit" (Alt+N).
				> Categories = Select and exclude all longer than a minute (but keep 1 minute because some tests just take this long).
				> "Project > Configurations > Debug" ('Debug' @ regression + 'Release' @ final).

				List of test assemblies, for manual ticking:
				> MKY.Test (0'12'')
				> MKY.IO.Ports.Test (2'10'' but see issue below)
				> MKY.IO.Serial.SerialPort.Test (0'00'')
				> MKY.IO.Serial.Socket.Test (4'00'')
				> MKY.IO.Serial.Usb.Test (0'04'')
				> MKY.IO.Usb.Test (0'20'' but see issue below)
				> MKY.Net.Test (0'00'')
				> NUnit (0'00'')
				> YAT.Controller.Test (0'20'')
				> YAT.Domain.Test (6'10'' but see issue below)
				> YAT.Model.Test
				> Clear (0'05'' but see issue below)
				> Command (0'00'')
				> Connection (1'30'' but see issue below)
				> FileHandling (0'20'')
				> Settings (0'00'' but see issue below)
				> Start (0'01'')
				> Stress (0'00'' but see issue below)
				> Transmission
				> MTSicsDevice (1'10'' but see issue below)
				> OneWay (3'20'' but see issues below)
				> Repeating (5'30'' but see issue below)
				> TwoWay (0'30'' but see issue below)
				> YAT.Settings.Test (0'15'')
				> YAT.Test (0'00'')
				> YAT.View.Test (0'30'')

				Known issues:
				MKY.IO.Ports.Test.SerialPort.ConnectionTest.TestDisconnectReconnect...() fail when running in sequence with previous tests, but pass when running as single test. / => For failed tests: Close NUnit, reconfigure USB Hubs, then run first failed test again, then redo for second failed test. / => Don't forget to close and reconfigure after the last test. / (Note that test has successfully completed on release configuration when releasing 1.99.90 on 2018-01-12 :-) / (Note that test has also successfully completed on release configuration when releasing 2.0.0 on 2018-04-06 :-) / (But test has only passed sequentially when releasing 2.1.0 on 2019-10-02… Simply increasing timeout didn't help. Additional 3 sec until revision #2502 cannot be the solution either…)
				MKY.IO.Usb.Test.ConnectionTest is not yet implemented => Assert.Ignore() => yellow bar.
				YAT.Domain.Test.Terminal.KeywordsSerialPortTest.SerialPortLoopbackPair_COM11_COM12() fail because MCT does not support automatic hardware flow control (bug #354 "Automatic hardware flow control is not supported by MCT").
				YAT.Domain.Test.TextTerminal.EolTest.TestByteSequence sometimes fail => Simply run the failed tests again.
				YAT.Model.Test.ClearTest sometimes fail => Simply run the failed tests again.
				YAT.Model.Test.Connection.DisconnectTest on 'IPv6Loopback' => Assert.Ignore() => yellow bar (FR #372).
				YAT.Model.Test.SettingsTest doesn't work yet => Assert.Ignore() => yellow bar.
				YAT.Model.Test.StressTest is not yet implemented => Assert.Ignore() => yellow bar.
				YAT.Model.Test.Transmission.MTSicsDeviceTest sometimes fails => Simply run the failed tests again.
				YAT.Model.Test.Transmission.*.IPLoopbacks on 'SpecificIPv4/6Interface' => Assert.Ignore() => yellow bar => Install/config of "TAP-Win32 Adapter" is required.

				Note: If everything works fine (rarely the case…), run takes around 1 hour, but expect quite some time for fixes.

	1.4.			Run manual tests		06:00		13:30
		1.4.1.		Ensure to select 'YAT' as the 'StartUp' project.

		1.4.2.		According to manual test cases in "\YAT\_Doc.Project\5 - Test\YAT – Test.ods" using 'Release' configuration but still 'Start Debugging [F5]' to handle issues.

				Scopes that haven't changed at all since last release may be skipped.

				List of test sections, for manual ticking:
				> MKY.IO.Serial.SerialPort
				> MKY.IO.Serial.Socket
				> TCP/IP
				> UDP/IP
				> MKY.IO.Serial.Usb
				> YAT.Domain.Terminal
				> YAT.Model.Main
				> YAT.Model.Terminal
				> YAT.View
				> YAT.View.Forms.Main
				> YAT.View.Forms.Terminal
				> YAT.View.Forms.Settings
				> YAT.Log
				> YAT.Info
				(Installation not yet, will be done in 5.)

## 2. Preparation
				Duration	Step		Total

2.				Preparation		00:00	01:40	13:30	15:10

	2.1.			Set versions		00:15		13:45
		2.1.1.		Ensure that product version in ALAZ.Version is different than at last release.
				> Versions must differ to ensure proper installation/update! / > Additional increment makes sense… / …if source code gets used by other software. / …if preliminary test version got distributed.
		2.1.2.		Ensure that product version in MKY.Version is different than at last release.
				> Same reason as above.
		2.1.3.		Ensure that product version in netrtfwriter\RtfWriter\Properties\AssemblyInfo.cs is different than at last release.
				> Same reason as above.
		2.1.4.		Ensure that product version in NUnit.Version is different than at last release.
				> Additional increment makes little sense as NUnit is not distributed.
		2.1.5.		Ensure that product version in YAT.Version is different than at last release.
				> Same reason as above.
		2.1.6.		Set product version in MKY file headers *.* throughout "\Trunk\MKY" (348 occurrences, incl. 4 of port workaround analysis).
				> Also remove 'Development', e.g. '// MKY Version 1.0.27'.
		2.1.7.		Set product version in NUnit file headers *.* throughout "\Trunk\NUnit" (5 occurrences).
				> Also remove 'Development', e.g. '// NUnit Version 1.0.21', if apparent.
		2.1.8.		Set product version in YAT file headers *.* throughout "\Trunk\YAT" (253 occurrences).
				> Also remove 'Development', e.g. '// YAT Version 2.1.0'.
		2.1.9.		Set product version in all other file headers (*.cs throughout \Trunk).
				> Search for all previous versions, e.g. '2.0.0' and '2.0.1' and replace them as required (former settings are OK). / > Includes this.label_Version.Text = "Version 2.0.0"; in WelcomeScreen.Designer.cs
		2.1.10.		Set ProductBuildDesignation in "YAT.Application.ApplicationEx".
		2.1.11.		Set ProductVerisonStabilityIndication in "YAT.Application.ApplicationEx".
		2.1.12.		Fill versions into 'The YAT story' in '0. Overview'.
		2.1.13.		Commit changes to SVN.
				> Check the property status of each file (except those of 3rd party assemblies).

	2.2.			Set installation version		00:05		13:50
		2.2.1.		Set product title in "YAT.Setup.x86".
		2.2.2.		Set product version in "YAT.Setup.x86".
		2.2.3.		Set product title in "YAT.Setup.x64".
		2.2.4.		Set product version in "YAT.Setup.x64".
		2.2.5.		Commit changes to SVN.

	2.3.			Update settings defaults and schema in "YAT\!-Settings\!-Current"		00:30		14:20
		2.3.1.		Ensure to select 'YAT.Test' as the 'StartUp' project.

				Note: 'YAT' and 'YATConsole' don't have dependencies to the test projects, thus those would not get built with 'YAT'!

		2.3.2.		Create files using NUnit on 'Debug Test'.
				> Build ‘Debug Test’ using ‘Build Solution’ / [F6]. (Explicitly building ‘YAT.Test’ would not build the .exe projects!)
				> "Visual Studio > Tools > NUnit" (Alt+N).
				> YAT.Settings.Test.SettingsFilesArchiver.
				Note that explicit tests are only runable if no include/exclude filter is active!
		2.3.3.		Diff *Default.xml.
		2.3.4.		Increase hard-coded settings versions if required.
		2.3.5.		Fill settings versions into '0. Overview'.
		2.3.6.		If any version has changed, create files again.
		2.3.7.		Diff and verify *Default.xml in detail.
				> Restore the <SettingsName> tag to YAT (result of NUnit).
				> Manually set the <ProductVersion> tag to the YAT version (result of NUnit).
				> LocalUser: Restore the <Paths> tags to YAT (result of NUnit).
				> Terminal: Restore the <Log\Root> tags to YAT (result of NUnit).
		2.3.8.		Also diff and verify *Schema.xsd.

	2.4.			Add new settings defaults and schema to settings archive		00:05		14:25:00
		2.4.1.		Archive *Default.xml from "\YAT\!-Settings\!-Current" to "\<New Version>".
		2.4.2.		Archive *Schema.xsd from "\YAT\!-Settings\!-Current" to "\<New Version>".
		2.4.3.		Commit changes to SVN.

	2.5.			Upgrade settings in settings archive "YAT\!-Settings\!-Current"		00:30		14:55:00
		2.5.1.		Prepare upgrade:
				> Delete all ‘YAT Local Settings’ folders in "C:\Users\<User>\AppData\Local\YAT\YAT".
				(ensure that window size is defaulted)
				> Delete all ‘YAT Roaming Settings’ folders in "C:\Users\<User>\AppData\Roaming\YAT\YAT".
				(just to ensure clean state)
				> Copy all terminal and workspace files of previous version to "\!-Current".
				(ensure that "\!-Current" will contain exact clones of the previous version)
				> Diff changes and revert/commit as required.
				> Connect all test devices.
				(needed with some of the files)
		2.5.2.		Select 'YAT' as the 'StartUp' project.
		2.5.3.		Select 'Release' configuration.
		2.5.4.		Perform upgrade:
				> Run YAT not moving or resizing window.
				> Open each old .yat or .yaw settings file in "YAT\!-Settings\!-Current".
				> For .yat, explicitly save settings:
				> File > Save [Ctrl+S].
				> For .yaw, explicitly save all settings:
				> File > Save All Terminals [Ctrl+Shift+A].
				> File > Workspace > Save Workspace [Ctrl+Shift+W].
				(Note on ‘09’ / ‘10’: No issue that some of the 6 terminals are not fully drawn.)
				> Close file(s) again.
				> For .yat:
				> File > Close [Ctrl+F4].
				(Note: Not 'Knigge' to display this standard shortcut in menu.)
				> For .yaw:
				> File > Workspace > Close.
		2.5.5.		Diff and verify the new settings.

	2.6.			Add new settings to settings archive		00:10		15:05:00
		2.6.1.		Archive the upgraded files in "YAT\!-Settings\<New Version>".
		2.6.2.		Add new settings to "YAT.Settings.Model.Test.SettingsFilesProvider".
		2.6.3.		Add new settings to "YAT.Settings.Model.Test.FileVersionsTest".

	2.7.			Rebuild and commit		00:05		15:10:00
		2.7.1.		Select 'YAT.Test' as the 'StartUp' project.
		2.7.2.		Build 'Debug Test' (ensure no build errors).
		2.7.3.		Commit changes to SVN.

## 3. Final Testing
				Duration	Step		Total

3.				Final Testing		00:00	01:30:00	15:10	16:40

	3.1.			Re-Run coding style checks		00:10		15:20
		3.1.1.		Use StyleCop on 'Debug Test'.
				> "Visual Studio > Tools > Run StyleCop (Rescan All)".

				Note: Rescan just takes a few seconds, and there should be not many findings anymore.

	3.2.			Re-Run assembly checks		00:10		15:30
		3.2.1.		Ensure to select 'YAT.Test' as the 'StartUp' project.

				Note: 'YAT' and 'YATConsole' don't have dependencies to the test projects, thus those would not get built!

		3.2.2.		Build 'Debug Test' using ‘Build Solution’ / [F6]. (Explicitly building ‘YAT.Test’ would not build the .exe projects!)

		3.2.3.		Use FxCop 'MKY.Debug' on 'Debug Test'.
				> Open and verify "\MKY\MKY.Debug.FxCop".

				48 expected warnings:
				CA1002 : DoNotExposeGenericLists @ 9 locations.
				CA2214 : DoNotCallOverridableMethodsInConstructors @ 39 locations.

		3.2.4.		Use FxCop 'NUnit.Debug' on 'Debug Test'.
				> Open and verify "\NUnit\NUnit.Debug.FxCop".

		3.2.5.		Use FxCop 'YAT.Debug' on 'Debug Test'.
				> Open and verify "\YAT\YAT.Debug.FxCop".

				234 expected errors/warnings:
				CA1002 : DoNotExposeGenericLists @ 108 locations.
				CA2214 : DoNotCallOverridableMethodsInConstructors @ 126 locations.

				Note: Rescan just takes a few seconds, and there should be not many findings anymore.

	3.3.			Re-run automated tests		01:00		16:30
		3.3.1.		Ensure that test environment is fully ready (VSPE, loopbacks, MT-SICS,…).

		3.3.2.		Ensure to select 'YAT.Test' as the 'StartUp' project.

				Note: 'YAT' and 'YATConsole' don't have dependencies to the test projects, thus those would not get built with 'YAT'!

		3.3.3.		Build 'Release Test' using ‘Build Solution’ / [F6]. (Explicitly building ‘YAT.Test’ would not build the .exe projects!)

		3.3.4.		Use NUnit on 'Release Test'.
				> "Visual Studio > Tools > NUnit" (Alt+N).
				> Categories = Select and exclude all longer than a minute (but keep 1 minute because some tests just take this long).
				> "Project > Configurations > Release" (Debug @ Regression + Release @ Final).

				List of test assemblies, for manual ticking:
				> MKY.Test (0'12'')
				> MKY.IO.Ports.Test (2'10'' but see issue below)
				> MKY.IO.Serial.SerialPort.Test (0'00'')
				> MKY.IO.Serial.Socket.Test (4'00'')
				> MKY.IO.Serial.Usb.Test (0'04'')
				> MKY.IO.Usb.Test (0'20'' but see issue below)
				> MKY.Net.Test (0'00'')
				> NUnit (0'00'')
				> YAT.Controller.Test (0'20'')
				> YAT.Domain.Test (6'10'' but see issue below)
				> YAT.Model.Test
				> Clear (0'05'' but see issue below)
				> Command (0'00'')
				> Connection (1'30'' but see issue below)
				> FileHandling (0'20'')
				> Settings (0'00'' but see issue below)
				> Start (0'01'')
				> Stress (0'00'' but see issue below)
				> Transmission
				> MTSicsDevice (1'10'' but see issue below)
				> OneWay (3'20'' but see issues below)
				> Repeating (5'30'' but see issue below)
				> TwoWay (0'30'' but see issue below)
				> YAT.Settings.Test (0'15'')
				> YAT.Test (0'00'')
				> YAT.View.Test (0'30'')

				Known issues:
				MKY.IO.Ports.Test.SerialPort.ConnectionTest.TestDisconnectReconnect...() fail when running in sequence with previous tests, but pass when running as single test. / => For failed tests: Close NUnit, reconfigure USB Hubs, then run first failed test again, then redo for second failed test. / => Don't forget to close and reconfigure after the last test. / (Note that test has successfully completed on release configuration when releasing 1.99.90 on 2018-01-12 :-) / (Note that test has also successfully completed on release configuration when releasing 2.0.0 on 2018-04-06 :-) / (But test has only passed sequentially when releasing 2.1.0 on 2019-10-02… Simply increasing timeout didn't help. Additional 3 sec until revision #2502 cannot be the solution either…)
				MKY.IO.Usb.Test.ConnectionTest is not yet implemented => Assert.Ignore() => yellow bar.
				YAT.Domain.Test.Terminal.KeywordsSerialPortTest.SerialPortLoopbackPair_COM11_COM12() fail because MCT does not support automatic hardware flow control (bug #354 "Automatic hardware flow control is not supported by MCT").
				YAT.Domain.Test.TextTerminal.EolTest.TestByteSequence sometimes fail => Simply run the failed tests again.
				YAT.Model.Test.ClearTest sometimes fail => Simply run the failed tests again.
				YAT.Model.Test.Connection.DisconnectTest on 'IPv6Loopback' => Assert.Ignore() => yellow bar (FR #372).
				YAT.Model.Test.SettingsTest doesn't work yet => Assert.Ignore() => yellow bar.
				YAT.Model.Test.StressTest is not yet implemented => Assert.Ignore() => yellow bar.
				YAT.Model.Test.Transmission.MTSicsDeviceTest sometimes fails => Simply run the failed tests again.
				YAT.Model.Test.Transmission.*.IPLoopbacks on 'IPv6Loopback' => Assert.Ignore() => yellow bar (FR #372).
				YAT.Model.Test.Transmission.*.IPLoopbacks on 'SpecificIPv4/6Interface' => Assert.Ignore() => yellow bar => Install/config of "TAP-Win32 Adapter" is required.

				Note: If everything works fine (rarely the case…), run takes around 1 hour, and there should be no more findings.

	3.4.			Check and commit		00:10		16:40:00
		3.4.1.		Ensure no debug left-overs by globally searching for "Trace.Write".
				> Match case.
				> No match whole word.

				252 occurrences totally expected, 10 as listed below, others only in test projects.
				> 2 occurrences expected in Diagnostics.
				> 6 occurrences expected in Drawing.
				> 2 occurrences expected in Serializer.

		3.4.2.		Ensure no debug left-overs by globally searching for "Debug.Write".
				> Match case.
				> No match whole word.

				156 occurrences totally expected:
				> 1 occurrence expected in ALAZ.
				> Several in ArgsHandler, Configuration, Diagnostics, EnvironmentEx, EventHelper,…
				> Several more in Usb, Hid, Terminal, Workspace, SendFile, SendText,…

		3.4.3.		Ensure no debug left-overs by globally searching for "Debugger.Break".
				> Match case.

				11 occurrences totally expected:
				> 4 occurrences expected in EventHelper.
				> 7 occurrences expected related to SplitContainerHelper.

		3.4.4.		Commit changes to SVN

## 4. Build
				Duration	Step		Total

4.				Build		00:00	00:40	16:40	17:20

	4.1.			Finalize release notes		00:10		16:50
		4.1.1.		Check whether release notes are complete.
		4.1.2.		Check whether limitations still apply.
		4.1.3.		Update the road map if necessary.
		4.1.4.		Spell check the release notes in word.
		4.1.5.		Clone release notes to those limited to 64 KB.
				> Check number of bytes, remove additional releases if number of lines exceeds 64k.

	4.2.			Prepare package directory		00:10		17:00
		4.2.1.		Check and update year of "!-ReadMe.txt" in the offline archive "\YAT\Releases and Checkpoints".
				> e.g. "2003-2019 Matthias Kläy" *.txt throughout "\Template"
		4.2.2.		Create a new directory based on the template.
		4.2.3.		Copy the release notes to all 6 package directories.
		4.2.4.		Also copy those limited to 64 KB to the distribution root and rename to "YAT Release Notes - ReadMe" (hyphen, no dash !!).
				> SourceForge requires the file to contain 'readme' in the name.

				Note: The distribution packages will be packed in a further step.

	4.3.			Build packages		00:20		17:20
		4.3.1.		Check 'YAT.Setup.x86|x64' prerequisites for 'Setup'.
				> Optimize for speed.
		4.3.2.		Check 'YAT.Setup.x86|x64' prerequisites for 'Setup with Prerequisites'.
				> Optimize for size.
		4.3.3.		Build > Batch Build > Clean all configurations for all target platforms.
				> Reduces the risk of mistakenly taking the wrong assemblies.
				> Check the intermediate folders of "\YAT\YAT\bin".
		4.3.4.		Build 'YAT' for 'x86'.
				> Ensure to start build at the beginning of a minute (in order to have same timestamp on all artifacts, all 3 builds take about 40 seconds).
				> Build "Release" configuration for "x86" using ‘Build Solution’ / [F6]. / (Separated from "Setup" and "Setup with Prerequisites" because both two packages shall contain the same binaries.)
				> Build "Setup" configuration for "x86" using ‘Build Solution’ / [F6].
				> Build "Setup with Prerequisites" configuration for "x86" using ‘Build Solution’ / [F6].
		4.3.5.		Build 'YAT' for 'x64'.
				> Ensure to start build at the beginning of a minute (in order to have same timestamp on all artifacts, all 3 builds take about 40 seconds).
				> Build "Release" configuration for "x64" using ‘Build Solution’ / [F6]. / (Separated from "Setup" and "Setup with Prerequisites" because both two packages shall contain the same binaries.)
				> Build "Setup" configuration for "x64" using ‘Build Solution’ / [F6].
				> Build "Setup with Prerequisites" configuration for "x64" using ‘Build Solution’ / [F6].

## 5. Installation Testing
				Duration	Step		Total

5.				Installation Testing		00:00	00:40	17:20	17:55

	5.1.			Preparation		00:05		17:25
		5.1.1.		Close Visual Studio.
				> Needed to ensure that YAT doesn't detect already running "YAT.vshost.exe" on startup.
		5.1.2.		Ensure that previous Local User Settings are available.
				> Use previous installed version and create 2 interconnected serial COM port terminals.
		5.1.3.		Ensure that previous Roaming User Settings are available.
		5.1.4.		Ensure that no current Local User Settings are already available.
		5.1.5.		Ensure that no current Roaming User Settings are already available.

	5.2.			Installation		00:05		17:30
		5.2.1.		Install YAT.

	5.3.			Run manual after-installation tests		00:30		17:55
		5.3.1.		Run according to manual after-installation test cases.

## 6. Packaging
				Duration	Step		Total

6.				Packaging		00:00	00:30	17:55	18:25

	6.1.			Commit and tag YAT		00:15		18:10
		6.1.1.		Commit any modifications to the subversion repository.
		6.1.2.		Tag/checkpoint the project:
				> SVN > Repo-browser.
				> Select 'trunk' in tree-view.
				> Copy to...
				> New name e.g. "<...>/tags/yat-2-1-0".
				> Message e.g. "YAT 2.1.0".
				> Wait for completion.
				> Select 'tags' in tree-view.
				> Check new tag (Refresh if not visible yet).
		6.1.3.		Fill the tag's SVN revision into 'The YAT story' in '0. Overview'.

	6.2.			Pack YAT		00:15		18:25
		6.2.1.		Update the 6 folders in "<Offline\Releases>\Distribution".
				> Copy packages from "Setup" projects.
				> Assemble binaries:
				> Open C:\Program Files\YAT and count the number of binaries:
				> 2 .exe
				> 25 .dll
				> Copy "YAT.exe" and "*.dll".
				> "\YAT\bin\Release" (AnyCPU) => x64.
				> "\YAT\bin\x86\Release" => x86.
				> Copy "YATConsole.exe" from that project.
				> Copy the 4 "DejaVuSansMono" fonts from "<Trunk>\YAT\!-Fonts\DejaVu\ttf" to "DejaVo Fonts".
				> The 4 "DejaVuSansMono" files are sufficient.
				> Copy "DejaVu Info" from installed C:\Program Files\YAT.
				> Copy "netrtfwriter Info" from installed C:\Program Files\YAT.
				> Run x64 YATConsole.exe as sanity check.
		6.2.2.		Zip the 6 distribution files.
				> Zip within folders, i.e. shall not contain the folder again, then move to parent.
		6.2.3.		Name the 6 distribution files.
				> "YAT-2.1.0_x64_(64-bit).zip".
				> "YAT-2.1.0_x64_(64-bit)_with_.NET_runtime.zip".
				> "YAT-2.1.0_x86_(32-bit).zip".
				> "YAT-2.1.0_x86_(32-bit)_with_.NET_runtime.zip".
				> "YAT-2.1.0_x64_(64-bit)_binaries_only.zip".
				> "YAT-2.1.0_x86_(32-bit)_binaries_only.zip".
				(Binaries last corresponding to order of package folders.)
		6.2.4.		Compare size of packages against last release (plausibility check).

				Note:
				Bugs #318 and #323 suggested to only distribute .msi for easier use.
				However, IE10+ by default does not allow to download (SHA1) .msi !!!
				New FR#274 “Find a way to distribute as .msi only” created.

## 7. Upload
				Duration	Step		Total

7.				Upload		00:00	01:20	17:55	19:15

	7.1.			Update statistics		00:20		18:15
		7.1.1.		Update "\YAT\!-Doc.SourceForge\".

	7.2.			Prepare upload		00:10		18:25
		7.2.1.		Log in as 'y-a-terminal'.
				> Ensure that new folder as well as files are "owned" by neutral user
		7.2.2.		Go to 'SourceForge > YAT > Files'.
		7.2.3.		Add archive folder (e.g. "Version 2.1.0").
		7.2.4.		Move current to archive using FileZilla.
				> Explicitly fill-in "sftp://frs.sourceforge.net | y-a-terminal | PW+OTP | 22".
				> PW is dedicated!
				> "/home/pfs/project/y-a-terminal".
				> Use tree view to open the intended archive folder.
				> Then drag and drop files to that folder.
				> Sequentially move for proper sequence !!!
				> Intended order:
				> RelNotes – x86 bin – x86.NET – x86 – x64 bin – x64.NET – x64.
				> Don't care about '+' symbol, files will get moved anyway.
				> Exit FileZilla, it is not used anymore.
		7.2.5.		Check that archived RelNotes are still excluded from statistics.

	7.3.			Add release		00:30		18:55
		7.3.1.		Upload distributions using the web interface.
				> Sequentially upload for proper sequence !!!
				> Intended order:
				> RelNotes
				> Check whether content of file limited to 64 KB is completely displayed.
				> x86 bin – x86.NET – x86 – x64 bin – x64.NET – x64.
				> Upload takes 20-30 minutes (for ~475 MB).
		7.3.2.		Tick default platform download on normal x64 distribution.
		7.3.3.		Exclude RelNotes from statistics.
		7.3.4.		Also replace RelNotes in archive main folder.
		7.3.5.		Also exclude RelNotes in archive main folder from statistics.

	7.4.			Check release and release notes		00:10		19:05
		7.4.1.		Reload YAT web page.
				> It takes a moment until the uploaded files are ready for download.
		7.4.2.		Download default file with Firefox.
		7.4.3.		Download all files with Firefox.
		7.4.4.		Download all files with Internet Explorer.
		7.4.5.		Download all files with Edge.
				> Verifies digital signature issues…
		7.4.6.		Verify contents of .msi / .zip.
				> At least open the ReadMe or RelNotes.
				> Extract x64 binaries to workspace and execute both .exe.
				> Extract x64 with runtime to temporary folder and execute setup.
				> Error message that app already installed.

	7.5.			Feature request and bug trackers		00:10		19:15
		7.5.1.		Check that items that are covered by this release have been closed.
				> OK if closed with 'y-a-terminal' account.

## 8. Finalization
				Duration	Step		Total

8.				Finalization		00:00	03:45:00	19:15	22:30

	8.1.			Send email to the YAT mailing list (Attention: Mail delay up to 60 min !!!)		00:30		19:45
		8.1.1.		Write email based on earlier mailings.
		8.1.2.		> Make sure that links are updated completely, i.e. link text and link itself.
				> Make sure the correct release notes are used.
		8.1.3.		Check spelling.
		8.1.4.		Send as "y-a-terminal@users.sourceforge.net".
		8.1.5.		Send to "y-a-terminal-users@lists.sourceforge.net".
		8.1.6.		Send encoded in Unicode.
				> Thunderbird: [Options > Encoding > Unicode]
		8.1.7.		Send as Text+HTML.
				> Thunderbird: [Options > Format > Text+HTML]
		8.1.8.		Send :-)
		8.1.9.		Save email in offline archive "\Distribution".
		8.1.10.		Accept email as moderator in mailman.
				> May take up to 60 min until possible.
				> Mail may also be delayed up to 60 min.

	8.2.			Submit news		00:15		20:00
		8.2.1.		[Develop > News > New Post]
				Title:
				"YAT 2.1.0"
				Text:
				"<Intro of release mail>"

	8.3.			Cleanup		00:15		20:15:00
		8.3.1.		Log out from SourceForge as 'y-a-terminal' and log in as 'maettu_this' again.
		8.3.2.		Send thanks mails.
				> People who are waiting for release / had dropbox access / gave feedback (YAT, MT, HFU,…).
		8.3.3.		Clean up preliminaries in dropbox.
		8.3.4.		Remove people from dropbox.
				> Also send mail to the office to do the same there.
		8.3.5.		Commit any modifications during the release process to the subversion repository.

	8.4.			Upgrade tools		01:00		21:00:00
		8.4.1.		Check for updates of Visual Studio and extensions.
				> In case of update, install everything including extensions.
		8.4.2.		Check for updates of all "\Tools\! - Tools and Versions.txt".
		8.4.3.		Also check for updates of TortoiseGIT.

	8.5.			Recreate and verify working copy		00:15		20:30:00
		8.5.1.		Rename the existing working copy to "Trunk_<New Date>".
		8.5.2.		Remove existing backups "Trunk_<Old Date>".
		8.5.3.		Create a new folder "Trunk".
		8.5.4.		Check the head revision out into "Trunk".
				> Make sure that only "...\code\trunk\" is checked out, not the whole repository.
		8.5.5.		Open the YAT solution.
		8.5.6.		Set 'YAT.Test' as the active startup project.
		8.5.7.		Fold all folders/projects.
		8.5.8.		Build 'Debug Test' to ensure that all files got committed from former working copy.
		8.5.9.		If VS/VSI got upgraded:
				> Set 'YAT' as the active startup configuration.
				> Build 'Setup with Prerequisites' to ensure that VSI properly builds.
		8.5.10.		Set 'YAT' as the active startup project.
		8.5.11.		Set 'Debug' as the active solution configuration.

	8.6.			Archive		00:15		21:15:00
		8.6.1.		Export the original working copy to a temporary folder (e.g. "D:\Temp\YAT\Archive").
				> Use 'SVN > Export…'.
				(Note this is the archive, not a backup, that is "Trunk_<New Date>".)
		8.6.2.		Pack the copy into a properly named zip.
		8.6.3.		Sanity check the size of the zip.
		8.6.4.		Move the zip to offline archive "<Version>\Working Copy".

	8.7.			Backup		01:00		22:15:00
		8.7.1.		Commit any modifications during the upgrade/recreate process to the subversion repository.
		8.7.2.		Manually backup onto offline disk.
				> Backup onto NAS is done automatically.

	8.8.			Update and verify working copy => Wait for a few days in case of a severe issue		00:15		22:30:00
		8.8.1.		Increment product version in ALAZ.Version.
		8.8.2.		Increment product version in MKY.Version.
		8.8.3.		Increment product version in netrtfwriter\RtfWriter\Properties\AssemblyInfo.cs.
		8.8.4.		Increment product version in NUnit.Version.
		8.8.5.		Increment product version in YAT.Version.
		8.8.6.		Set product version in MKY file headers *.* throughout "\Trunk\MKY" (348 occurrences, incl. 4 of port workaround analysis).
				> Append 'Development', e.g. '// MKY Version 1.0.28 Development'.
		8.8.7.		Set product version in NUnit file headers *.* throughout "\Trunk\NUnit" (5 occurrences).
				> Append 'Development', e.g. '// NUnit Version 1.0.22 Development'.
		8.8.8.		Set product version in YAT file headers *.* throughout "\Trunk\YAT" (253 occurrences).
				> Append 'Development', e.g. '// YAT Version 2.3.90 Development'.
		8.8.9.		Set stability indication in "YAT.Application.ApplicationEx".
				> Activate 'Development' to clearly indicate non-release state.
		8.8.10.		Add a new section to the release notes.
				> Copy limitations and known issues from last release.
		8.8.11.		Verify that the solution still properly builds and runs.