## 0. Overview
A YAT release is done in 8 steps:
				Duration	Step	Total
		1.	Regression Testing		07:00	07:00
		2.	Preparation		02:10	09:10
		3.	Final Testing		04:45	13:55
		4.	Build		00:30	14:25
		5.	Installation Testing		00:40	15:05
		6.	Packaging		00:40	15:05
		7.	Upload		00:50	15:55
		8.	Finalization		02:10	17:45

The YAT story:
					YAT	MKY	ALAZ	NUnit		LU.xml	.yat	.yaw		SVN
	2013-02-02	:	YAT 2.0 Beta 4 Candidate 2				1.99.30	1.0.9	3.5.7	1.0.6		1.3.1	1.3.1	1.1.1		626
	2011-12-05	:	YAT 2.0 Beta 4 Candidate 1				1.99.28	1.0.7	3.5.5	1.0.4		1.3.0	1.3.0	1.1.0		502
	2011-04-25	:	YAT 2.0 Beta 3 Candidate 4				1.99.26	1.0.5	3.5.3	1.0.2		1.2.4	1.2.9	1.0.0		419
	2010-11-28	:	YAT 2.0 Beta 3 Candidate 3				1.99.25	1.0.4	3.5.2	1.0.1		1.2.4	1.2.9	1.0.0		385
	2010-11-11	:	YAT 2.0 Beta 3 Candidate 2				1.99.24	1.0.4	3.5.2	1.0.1		1.2.4	1.2.8	1.0.0		369
	2009-09-10	:	YAT 2.0 Beta 3 Candidate 1				1.99.23	1.0.1	3.5.0			1.2.4	1.2.7	1.0.0		251
	2009-09-08	:	YAT 2.0 Beta 3 Candidate 1				1.99.22	1.0.1	3.5.0			1.2.3	1.2.6	1.0.0		247
	2008-07-18	:	YAT 2.0 Beta 2 Candidate 4				1.99.20	1.0.0	1.2.0			1.2.3	1.2.5	1.0.0		201
	2008-04-01	:	YAT 2.0 Beta 2 Candidate 3				1.99.19					1.2.2	1.2.4	1.0.0		136
	2008-03-17	:	YAT 2.0 Beta 2 Candidate 2				1.99.18					1.2.2	1.2.3	1.0.0		122
	2008-02-11	:	YAT 2.0 Beta 2 Candidate 1				1.99.17					1.2.2	1.2.2	1.0.0		105
	2007-08-30	:	YAT 2.0 Beta 2 Preliminary				1.99.13					1.2.1	1.2.1	1.0.0		(45)
	2007-04-15	:	YAT 2.0 Beta 1				1.99.12					1.2.0	1.2.0			9
	2007-02-25	:	YAT 2.0 Alpha 3				1.99.8					1.1.2	1.1.2
	2007-02-07	:	YAT 2.0 Alpha 2				1.99.3					1.1.1	1.1.1
	2007-01-23	:	YAT 2.0 Alpha 1				1.99.0					1.1.0	1.1.0
	2003-10-31	:	XTerm232				1.0.2					1.0.1	1.0.1
	2003-10-30	:	XTerm232				1.0.1					1.0.1	1.0.1
	2003-10-14	:	XTerm232				1.0.0					1.0.0	1.0.0

## 1. Regression Testing
				Duration	Step		Total

1.				Regression Testing		00:00	07:00	00:00	07:00

	1.1.			Run coding style checks		00:30		00:30
		1.1.1.		Use StyleCop on 'Debug Test'
				> "Visual Studio > Tools > Run StyleCop (Rescan All)"

				2 expected warnings:
				SA1203 : CSharp.Ordering @ YAT.Model.Settings.SendCommandSettings.cs
				SA1409 : CSharp.Maintainability @ YAT.Model.Terminal.cs

				Note: Rescan takes less than a minute, but expect some time for fixes

	1.2.			Run assembly checks		00:30		01:00
		1.2.1.		Use FxCop 'MKY.Debug' on 'Debug Test'
				> Open and verify "\MKY\MKY.Debug.FxCop"

				50 expected warnings:
				CA1805 : DoNotInitializeUnnecessarily @ 4 locations
				CA1811 : AvoidUncalledPrivateCode @ 4 locations
				CA2213 : DisposableFieldsShouldBeDisposed @ 16 locations
				CA2214 : DoNotCallOverridableMethodsInConstructors @ 26 locations

		1.2.2.		Use FxCop 'NUnit.Debug' on 'Debug Test'
				> Open and verify "\NUnit\NUnit.Debug.FxCop"

		1.2.3.		Use FxCop 'YAT.Debug' on 'Debug Test'
				> Open and verify "\YAT\YAT.Debug.FxCop"

				152 expected errors/warnings:
				CA1002 : DoNotExposeGenericLists @ 36 locations
				CA1044 : PropertiesShouldNotBeWriteOnly @ 17 locations
				CA1601 : DoNotUseTimersThatPreventPowerStateChanges @ 2 locations
				CA1804 : RemoveUnusedLocals @ 1 location
				CA1819 : PropertiesShouldNotReturnArrays @ 1 location
				CA2214 : DoNotCallOverridableMethodsInConstructors @ 96 locations

				Note: Rescan takes less than a minute, but expect some time for fixes

	1.3.			Run automated tests		06:00		07:00
		1.3.1.		Configure NUnit test categories
				> "Visual Studio > Tools > NUnit"
				> "Categories = Select and exclude 10'/60'/infinite/interactive"

		1.3.2.		Use NUnit on 'Debug Test'
				> "Visual Studio > Tools > NUnit"
				> "Project > Configurations > Debug"

				12 expected errors:
				YAT.Model.Test.OneWayTransmissionTest::ClearCommand @ Ipv4/IPv6
				YAT.Settings.Test.FileVersionsTest::TC1/2 @ 1.99.13/17/18/19

				Note: Run takes around 20 minutes, but expect quite some time for fixes

## 2. Preparation
				Duration	Step		Total

2.				Preparation		00:00	02:10	07:00	09:10

	2.1.			Set versions		00:20		07:20
		2.1.1.		Increment product version in ALAZ.Version
		2.1.2.		Increment product version in MKY.Version
		2.1.3.		Increment product version in NUnit.Version
		2.1.4.		Increment product version in YAT.Version
				> All versions must be incremented to later ensure proper installation!
		2.1.5.		Set product name post fix in "YAT.Utilities.ApplicationInfo"
				> Remove 'Development'
		2.1.6.		Set product version in MKY file headers
				> Also remove 'Development', e.g. '// MKY Version 1.0.9'
		2.1.7.		Set product version in NUnit file headers
				> Also remove 'Development', e.g. '// NUnit Version 1.0.6'
		2.1.8.		Set product version in YAT file headers
				> Also remove 'Development', e.g. '// YAT 2.0 Beta 4 Candidate 1 Version 1.99.30'
		2.1.9.		Fill date and versions into 'The YAT story' in '0. Overview'

	2.2.			Set installation version		00:05		07:25
		2.2.1.		Set product title in "YAT.Setup"
		2.2.2.		Set product version in "YAT.Setup"

	2.3.			Update settings defaults and schema in "YAT\!-Settings\!-Current"		00:30		07:55
		2.3.1.		Create files using NUnit on 'Debug Test'
				> "Visual Studio > Tools > NUnit"
				> YAT.Settings.Test.SettingsFilesArchiver
		2.3.2.		Manually modify the product version tag to the YAT version (result of NUnit)
		2.3.3.		Diff and verify the files in "YAT\!-Settings\!-Current"
		2.3.4.		Fill settings versions into 'The YAT story' in '0. Overview'

	2.4.			Add new settings defaults and schema to settings archive		00:15		08:10
		2.4.1.		Archive the upgraded files in "YAT\!-Settings\<New Version>"
		2.4.2.		Add new settings to "YAT.Settings.Test.SettingsFilesProvider"
		2.4.3.		Add new settings to "YAT.Settings.Test.FileVersionsTest"

	2.5.			Upgrade settings in settings archive "YAT\!-Settings\!-Current"		00:30		08:40
		2.5.1.		Upgrade settings
				> Run YAT and open old settings
				> Modify settings (use 'View > Show …' to ensure that IO settings are kept)
				> Undo changes
				> Save upgraded but unchanged settings
		2.5.2.		Diff and verify the new settings

	2.6.			Add new settings to settings archive		00:15		08:55
		2.6.1.		Archive the upgraded files in "YAT\!-Settings\<New Version>"
		2.6.2.		Add new settings to "YAT.Settings.Test.SettingsFilesProvider"
		2.6.3.		Add new settings to "YAT.Settings.Test.FileVersionsTest"

	2.7.			Rebuild and commit		00:15		09:10
		2.7.1.		Rebuild 'Debug'
		2.7.2.		Rebuild 'Debug Test'
		2.7.3.		Rebuild 'Release Test'
		2.7.4.		Commit changes to SVN

## 3. Final Testing
				Duration	Step		Total

3.				Final Testing		00:00	04:45	09:10	13:55

	3.1.			Re-Run coding style checks		00:10		09:20
		3.1.1.		Use StyleCop on 'Debug Test'
				> "Visual Studio > Tools > Run StyleCop (Rescan All)"

				2 expected warnings:
				SA1203 : CSharp.Ordering @ YAT.Model.Settings.SendCommandSettings.cs
				SA1409 : CSharp.Maintainability @ YAT.Model.Terminal.cs

				Note: Rescan takes less than a minute, and there should be no more findings

	3.2.			Re-Run assembly checks		00:10		09:30
		3.2.1.		Use FxCop 'MKY.Debug' on 'Debug Test'
				> Open and verify "\MKY\MKY.Debug.FxCop"

				50 expected warnings:
				CA1805 : DoNotInitializeUnnecessarily @ 4 locations
				CA1811 : AvoidUncalledPrivateCode @ 4 locations
				CA2213 : DisposableFieldsShouldBeDisposed @ 16 locations
				CA2214 : DoNotCallOverridableMethodsInConstructors @ 26 locations

		3.2.2.		Use FxCop 'NUnit.Debug' on 'Debug Test'
				> Open and verify "\NUnit\NUnit.Debug.FxCop"

		3.2.3.		Use FxCop 'YAT.Debug' on 'Debug Test'
				> Open and verify "\YAT\YAT.Debug.FxCop"

				152 expected errors/warnings:
				CA1002 : DoNotExposeGenericLists @ 36 locations
				CA1044 : PropertiesShouldNotBeWriteOnly @ 17 locations
				CA1601 : DoNotUseTimersThatPreventPowerStateChanges @ 2 locations
				CA1804 : RemoveUnusedLocals @ 1 location
				CA1819 : PropertiesShouldNotReturnArrays @ 1 location
				CA2214 : DoNotCallOverridableMethodsInConstructors @ 96 locations

				Note: Rescan takes less than a minute, and there should be no more findings

	3.3.			Run automated tests		00:30		10:00
		3.3.1.		Configure NUnit test categories
				> "Visual Studio > Tools > NUnit"
				> "Categories = Select and exclude 10'/60'/infinite/interactive"

		3.3.2.		Use NUnit on 'Debug Test'
				> "Visual Studio > Tools > NUnit"
				> "Project > Configurations > Debug"

				12 expected errors:
				YAT.Model.Test.OneWayTransmissionTest::ClearCommand @ Ipv4/IPv6
				YAT.Settings.Test.FileVersionsTest::TC1/2 @ 1.99.13/17/18/19

				Note: Run takes around 20 minutes, and there should be no more findings

	3.4.			Disconnect all devices, restart computer, re-run automated tests		00:45		10:45
		3.4.1.		Re-run 3.3.2. above
		3.4.2.		Reconnect devices

	3.5.			Run interactive tests		00:10		10:55
		3.5.1.		Configure NUnit test categories
				> "Visual Studio > Tools > NUnit"
				> "Categories = Select and include interactive only"

		3.5.2.		Use NUnit on 'Debug Test'
				> "Visual Studio > Tools > NUnit"
				> "Project > Configurations > Debug"
		3.5.3.		Use NUnit on 'Release Test'
				> "Visual Studio > Tools > NUnit"
				> "Project > Configurations > Release"

	3.6.			Run manual tests		02:30		13:25
		3.6.1.		According to manual test cases in "\YAT\_Doc.Project\5 - Test\YAT - Test.ods"

	3.7.			Re-run automated tests and commit		00:30		13:55
		3.7.1.		Use NUnit on 'Release Test' to ensure that modifications didn't re-introduce any bugs
				> "Visual Studio > Tools > NUnit"
				> "Project > Configurations > Release"

				12 expected errors:
				YAT.Model.Test.OneWayTransmissionTest::ClearCommand @ Ipv4/IPv6
				YAT.Settings.Test.FileVersionsTest::TC1/2 @ 1.99.13/17/18/19

				Note: Run takes around 20 minutes, and there should be no more findings

		3.7.2.		Commit changes to SVN

## 4. Build
				Duration	Step		Total

4.				Build		00:00	00:30	13:55	14:25

	4.1.			Finalize release notes		00:00		13:55
		4.1.1.		Add them cumulatively to "\!-Doc.User\YAT Release Notes.txt"
		4.1.2.		Check whether release notes are complete
		4.1.3.		Check whether limitations still apply

	4.2.			Prepare package directory		00:10		14:05
		4.2.1.		Add a new directory to the offline archive "\YAT\Releases and Checkpoints"
		4.2.2.		Check and update year of "!-ReadMe.txt" in the release package directories
		4.2.3.		Add the release notes to the release package directories
		4.2.4.		Copy and rename the release notes to "YAT Release Notes - ReadMe.txt"
				> SourceForge requires the file to contain 'readme' in the name

				Note: The distribution packages will be packed in a further step

	4.3.			Re-Build YAT		00:20		14:25
		4.3.1.		Check "YAT.Setup" prerequisites for "Release"
				> Optimize for speed
		4.3.2.		Check "YAT.Setup" prerequisites for "Release with Prerequisites"
				> Optimize for size
		4.3.3.		Re-Build "Release" configuration
				> Re-build to ensure that all assemblies have the same time stamp
		4.3.4.		Build "Release with Prerequisites" configuration
				> No need to re-build since re-build has just been done

## 5. Installation Testing
				Duration	Step		Total

5.				Installation Testing		00:00	00:40	14:25	15:05

	5.1.			Installation		00:10		14:35
		5.1.1.		Close Visual Studio
				> Needed to ensure that YAT doesn't detect already running "YAT.vshost.exe" on startup
		5.1.2.		Install YAT

	5.2.			Run manual after-installation tests		00:30		15:05
		5.2.1.		Run according to manual after-installation test cases

## 6. Packaging
				Duration	Step		Total

6.				Packaging		00:00	00:35	15:05	15:40

	6.1.			Feature request and bug trackers		00:05		15:10
		6.1.1.		Check that items that are covered by this release have been closed

	6.2.			Commit and tag YAT		00:15		15:25
		6.2.1.		Commit any modifications to the subversion repository
				> Message e.g. "YAT 2.0 Beta 4 Candidate 2 Version 1.99.30"
		6.2.2.		Tag/checkpoint the project
				> SVN > Repo Browser
				> Select 'trunk'
				> Copy to...
				> New name e.g. "<...>/tags/yat-1-99-30-beta-4-candidate-2"
				> Message e.g. "YAT 2.0 Beta 4 Candidate 2 Version 1.99.30"
				> Select 'tags'
				> Check tag
		6.2.3.		Fill SVN revision into 'The YAT story' in '0. Overview'

	6.3.			Pack YAT		00:15		15:40
		6.3.1.		Update "\Distribution\Release"
		6.3.2.		Update "\Distribution\Release With Prerequisites"
		6.3.3.		Create the two according .zip files

## 7. Upload
				Duration	Step		Total

7.				Upload		00:00	00:50	15:05	15:55

	7.1.			Prepare upload to SourceForge		00:10		15:15
		7.1.1.		Log in as 'y-a-terminal'
		7.1.2.		Go to 'SourceForge > Files'
		7.1.3.		Add release folder (e.g. "Version 1.99.30 - YAT 2.0 Beta 4 Candidate 2")

				HowTo:
				<https://sourceforge.net/apps/trac/sourceforge/wiki/Release%20files%20for%20download

	7.2.			Add release		00:30		15:45
		7.2.1.		Upload distributions using the web interface
				> 'Release' takes approx. 2 minutes (for 6 MB)
				> 'Release With Prerequisites' takes approx. 60 minutes (for 200 MB)
		7.2.2.		Tick default platform download on normal distribution
		7.2.3.		Upload release notes to the release folder
		7.2.4.		Upload release notes to the parent folder
		7.2.5.		Upload release notes to the root folder

	7.3.			Check release and release notes		00:10		15:55
		7.3.1.		Reload YAT web page
				> It takes several minutes until the uploaded files are ready for download
		7.3.2.		Download release and verify contents of .zip
		7.3.3.		Take a look at the release notes

## 8. Finalization
				Duration	Step		Total

8.				Finalization		00:00	02:10	15:55	17:45

	8.1.			Submit news		00:15		16:10
		8.1.1.		Go to 'Develop > News'
		8.1.2.		Add news
				Title:
				"YAT 2.0 Beta 4 Candidate 2 Version 1.99.30"
				Text:
				"<Intro of release mail>"

				HowTo:
				<https://sourceforge.net/apps/trac/sourceforge/wiki/News>

	8.2.			Send e-mail to the YAT mailing list		00:15		16:25
		8.2.1.		Check/update mailing list
		8.2.2.		Write e-mail based on earlier mailings
				> Make sure that links are updated completely, i.e. link text and link below
				> Make sure the correct release notes are used
		8.2.3.		Send as "y-a-terminal@users.sourceforge.net"
		8.2.4.		Send to "y-a-terminal-users@lists.sourceforge.net"
		8.2.5.		Send as text and HTML formatted
				> Thunderbird: Options > Format > Text+HTML
		8.2.6.		Save e-mail in offline archive "\Distribution"
		8.2.7.		Accept e-mail as moderator in mailman if needed

	8.3.			Commit		00:05		16:30
		8.3.1.		Commit any modifications during the release process to the subversion repository

	8.4.			Recreate working copy		00:15		16:45
		8.4.1.		Rename the existing working copy to "Trunk_<New Date>" (e.g. _2013-02-02)
		8.4.2.		Remove existing backups "Trunk_<Old Date>"
		8.4.3.		Check for updates of TortoiseSVN and AnkhSVN
		8.4.4.		Create a new folder "Trunk"
		8.4.5.		Check the head revision out into "Trunk"

	8.5.			Archive		00:15		17:00
		8.5.1.		Export the new working copy to offline archive "<Version>\Working Copy"
				> Use 'SVN > Export...'
		8.5.2.		Pack the copy into a properly named zip file

	8.6.			Update and verify working copy		00:15		17:15
		8.6.1.		Open the YAT solution
		8.6.2.		Fold all projects
		8.6.3.		Set 'YAT' as the active startup project
		8.6.4.		Increment product version in ALAZ.Version
		8.6.5.		Increment product version in MKY.Version
		8.6.6.		Increment product version in NUnit.Version
		8.6.7.		Increment product version in YAT.Version
				All version must be incremented to later ensure proper installation!
		8.6.8.		Set product name post fix in "YAT.Utilities.ApplicationInfo"
				> Add 'Development' to clearly state that files are non-released revisions
		8.6.9.		Set product version in MKY file headers
				> Add 'Development', e.g. '// MKY Development Version 1.0.7'
		8.6.10.		Set product version in NUnit file headers
				> Add 'Development', e.g. '// NUnit Development Version 1.0.4'
		8.6.11.		Set product version in YAT file headers
				> Add 'Development', e.g. '// YAT 2.0 Beta 4 Candidate 1 Development Version 1.99.28'
		8.6.12.		Add a new section to the release notes
				> Copy limitations and known issues from last release
		8.6.13.		Verify that the solution still properly builds and runs

	8.7.			Update statistics		00:15		17:30
		8.7.1.		Update "\YAT\!-Doc.SourceForge\"

	8.8.			Commit		00:05		17:35
		8.8.1.		Commit modifications to the subversion repository

	8.9.			Backup PC		00:30		17:45
		8.9.1.		Offline archive
		8.9.2.		Sandboxes