## 0. Overview
A YAT release is done in 10 steps:
		Step		Duration	of Step	in Total
		1.	Regression Testing		26:00	26:00
		2.	Documentation		00:10	26:10
		3.	Preparation		01:55	28:05
		4.	Final Testing		01:30	29:35
		5.	Build		00:40	30:15
		6.	Installation Testing		00:40	30:50
		7.	Packaging		00:40	30:50
		8.	Upload		01:50	32:40
		9.	Finalization		03:30	35:40
		10.	Aftermath		00:15	35:55

The YAT story:
	Date		Designation		x86 Build	x64 Build	YAT	MKY	ALAZ	NUnitEx	netrtf.		LU.xml	RU.xml	.yac	.yacp	.yacps	.yat	.yaw		SVN		.NET	WinInst		Remarks
	2021-05-xx	:	YAT 2.4.1		17951	18005	2.4.1	1.0.30	3.5.26	1.0.23	0.9.27		1.8.0	1.3.0	1.0.2	1.0.2	1.0.2	1.8.0	1.2.3		3672		4.8	4.5
	2021-01-29	:	YAT 2.4.0		17951	18005	2.4.0	1.0.29	3.5.25	1.0.22	0.9.26		1.8.0	1.3.0	1.0.2	1.0.2	1.0.2	1.8.0	1.2.3		3672		4.8	4.5		Version of non-YAT assemblies incremented twice to prevent potential version conflicts at those who have tested the preliminary versions.
	2019-10-04	:	YAT 2.1.0				2.1.0	1.0.27	3.5.23	1.0.21	0.9.24		1.7.0	1.2.0	1.0.2	1.0.2	1.0.2	1.7.0	1.2.3		2553		3.5 SP 1	4.5		Last version with execution support for WinXP …vent potential version conflicts at...
	2018-04-13	:	YAT 2.0 Final				2.0.0	1.0.25	3.5.21	1.0.19	0.9.22		1.6.0	1.1.0	(1.0.2)	(1.0.2)	(1.0.2)	1.6.0	1.2.3		1919		3.5 SP 1	4.5		Version of non-YAT assemblies incremented twice to prevent potential version conflicts at those who have tested the preliminary versions.
	2018-01-12	:	YAT 2.0 Epsilon				1.99.90	1.0.23	3.5.19	1.0.18	0.9.20		1.5.3	1.0.0	(1.0.2)	(1.0.2)	(1.0.2)	1.5.3	1.2.2		1815		3.5 SP 1	4.5		Version of non-YAT assemblies incremented twice to prevent potential version conflicts at those who have tested the preliminary versions.
	2017-10-15	:	YAT 2.0 Delta				1.99.80	1.0.21	3.5.17	1.0.17	0.9.18		1.5.2		(1.0.2)	(1.0.2)	(1.0.2)	1.5.2	1.2.1		1603		3.5 SP 1	4.5		Version of non-YAT assemblies incremented twice to prevent potential version conflicts at those who have tested the preliminary versions.
	2017-07-04	:	YAT 2.0 Gamma 3				1.99.70	1.0.19	3.5.15	1.0.16	0.9.16		1.5.1		(1.0.2)	(1.0.2)	(1.0.2)	1.5.1	1.2.1		1410		3.5 SP 1	4.5
	2016-09-30	:	YAT 2.0 Gamma 2''				1.99.52	1.0.17	3.5.14	1.0.14	0.9.15		1.5.0		(1.0.2)	(1.0.2)	(1.0.2)	1.5.0	1.2.1		1190		3.5 SP 1	4.5		No longer testing settings; settings equal 1.99.50.
	2016-09-17	:	YAT 2.0 Gamma 2'				1.99.51	1.0.16	3.5.13	1.0.13	0.9.14		1.5.0		(1.0.2)	(1.0.2)	(1.0.2)	1.5.0	1.2.1		1162		3.5 SP 1	4.5		No longer testing settings; settings equal 1.99.50.
	2016-09-16	:	YAT 2.0 Gamma 2				1.99.50	1.0.15	3.5.12	1.0.12	0.9.13		1.5.0		(1.0.2)	(1.0.2)	(1.0.2)	1.5.0	1.2.1		1159		3.5 SP 1	4.5		Issue with FileVersionsTest.TerminalSettingsCase07 (bugs #232 and #246 "Issues with [Alternate]TolerantXmlSerializer").
	2015-06-13	:	YAT 2.0 Gamma 1''				1.99.34	1.0.13	3.5.11	1.0.10			1.4.1		(1.0.2)	(1.0.2)	(1.0.2)	1.4.1	1.2.0		799		3.5 SP 1	4.5
	2015-06-07	:	YAT 2.0 Gamma 1'				1.99.33	1.0.12	3.5.10	1.0.9			1.4.0		(1.0.2)	(1.0.2)	(1.0.2)	1.4.0	1.2.0		778		3.5 SP 1	4.5		No longer testing settings; settings equal 1.99.32.
	2015-06-01	:	YAT 2.0 Gamma 1				1.99.32	1.0.11	3.5.9	1.0.8			1.4.0		(1.0.2)	(1.0.2)	(1.0.2)	1.4.0	1.2.0		769		3.5 SP 1	4.5
	2013-02-02	:	YAT 2.0 Beta 4 Candidate 2				1.99.30	1.0.9	3.5.7	1.0.6			1.3.1		(1.0.1)	(1.0.1)	(1.0.1)	1.3.1	1.1.1		626		3.5 SP 1	3.1		Last version with installer support for WinXP
	2011-12-05	:	YAT 2.0 Beta 4 Candidate 1				1.99.28	1.0.7	3.5.5	1.0.4			1.3.0		(1.0.1)	(1.0.1)	(1.0.1)	1.3.0	1.1.0		502		3.5 SP 1	3.1
	2011-04-25	:	YAT 2.0 Beta 3 Candidate 4				1.99.26	1.0.5	3.5.3	1.0.2			1.2.4		(1.0.1)	(1.0.1)	(1.0.1)	1.2.9	1.0.0		419		3.5 SP 1	3.1
	2010-11-28	:	YAT 2.0 Beta 3 Candidate 3				1.99.25	1.0.4	3.5.2	1.0.1			1.2.4		(1.0.1)	(1.0.1)	(1.0.1)	1.2.9	1.0.0		385		3.5 SP 1	3.1
	2010-11-11	:	YAT 2.0 Beta 3 Candidate 2				1.99.24	1.0.4	3.5.2	1.0.1			1.2.4		(1.0.1)	(1.0.1)	(1.0.1)	1.2.8	1.0.0		369		3.5 SP 1	3.1
	2009-09-10	:	YAT 2.0 Beta 3 Candidate 1'				1.99.23	1.0.1	3.5.0				1.2.4		(1.0.0)	(1.0.0)	(1.0.0)	1.2.7	1.0.0		251		3.5 SP 1	3.1		No longer testing settings; version has been outdated.
	2009-09-08	:	YAT 2.0 Beta 3 Candidate 1				1.99.22	1.0.1	3.5.0				1.2.3		(1.0.0)	(1.0.0)	(1.0.0)	1.2.6	1.0.0		247		3.5 SP 1	3.1		No longer testing settings; version has been outdated.
	2008-07-18	:	YAT 2.0 Beta 2 Candidate 4				1.99.20	1.0.0	1.2.0				1.2.3					1.2.5	1.0.0		201		2.0	3.1		No longer testing settings; version has been outdated.
	2008-04-01	:	YAT 2.0 Beta 2 Candidate 3				1.99.19					1.2.2					1.2.4	1.0.0		136		2.0	3.1		No longer testing settings; version has been outdated.
	2008-03-17	:	YAT 2.0 Beta 2 Candidate 2				1.99.18					1.2.2					1.2.3	1.0.0		122		2.0	3.1		No longer testing settings; version has been outdated.
	2008-02-11	:	YAT 2.0 Beta 2 Candidate 1				1.99.17					1.2.2					1.2.2	1.0.0		105		2.0	3.1		No longer testing settings; version has been outdated.
	2007-08-30	:	YAT 2.0 Beta 2 Preliminary				1.99.13					1.2.1					1.2.1	1.0.0		(45)		2.0	3.1		No longer testing settings; version has been outdated.
	2007-04-15	:	YAT 2.0 Beta 1				1.99.12					1.2.0					1.2.0			9		2.0	3.1		No longer testing settings; version has been outdated.
	2007-02-25	:	YAT 2.0 Alpha 3				1.99.8					1.1.2					1.1.2					2.0	3.1		No longer testing settings; version has been outdated.
	2007-02-07	:	YAT 2.0 Alpha 2				1.99.3					1.1.1					1.1.1					2.0	3.1		No longer testing settings; version has been outdated.
	2007-01-23	:	YAT 2.0 Alpha 1				1.99.0					1.1.0					1.1.0					2.0	3.1		No longer testing settings; version has been outdated.
	2003-10-31	:	XTerm232				1.0.2					1.0.1					1.0.1					1.1			No longer testing settings; version has been outdated.
	2003-10-30	:	XTerm232				1.0.1					1.0.1					1.0.1					1.1			No longer testing settings; version has been outdated.
	2003-10-14	:	XTerm232				1.0.0					1.0.0					1.0.0					1.1			No longer testing settings; version has been outdated.

## 1. Regression Testing
				Duration	Step		Total

1.				Regression Testing		00:00	26:00	00:00	26:00

	1.1.			Run coding style checks		01:00		01:00
		1.1.1.		Use StyleCop on 'Debug Test'.
				> "Visual Studio > Tools > Run StyleCop (Rescan All)".

				Note: Rescan just takes a few seconds, but expect quite some time for fixes.

	1.2.			Run assembly checks		01:00		02:00
		1.2.1.		Ensure to select 'YAT.Test' as the 'StartUp' project.
				Note: 'YAT' and 'YATConsole' don't have dependencies to the test projects, thus those would not get built.

		1.2.2.		Build 'Debug Test' using ‘Build Solution’ / [F6]. (Explicitly building ‘YAT.Test’ would not build the .exe projects!)

		1.2.3.		Use FxCop 'MKY.Debug' on 'Debug Test'.
				> Open and verify "\MKY\MKY.Debug.FxCop".

				45 expected warnings:
				CA1002 : DoNotExposeGenericLists @ 9 locations.
				CA2214 : DoNotCallOverridableMethodsInConstructors @ 36 locations.

		1.2.4.		Use FxCop 'NUnit.Debug' on 'Debug Test'.
				> Open and verify "\NUnit\NUnit.Debug.FxCop".

		1.2.5.		Use FxCop 'YAT.Debug' on 'Debug Test'.
				> Open and verify "\YAT\YAT.Debug.FxCop".

				227 expected errors/warnings:
				CA1002 : DoNotExposeGenericLists @ 97 locations.
				CA2214 : DoNotCallOverridableMethodsInConstructors @ 130 locations.

				Note: Analysis just take a few seconds, but expect quite some time for fixes.
				But: FxCop is no longer capable to deal with YAT, as there now are references to .NET 4.0! FR#231!

	1.3.			Run automated tests		04:00		06:00
		1.3.1.		Ensure that test environment is fully ready (VSPE, hardware, MT-SICS,…).		Duration doesn't include time for major fixes.

				Attention: Time-out calibration (for whatever reason) no longer fits MKY machine => use MT machine.

		1.3.2.		Ensure to select 'YAT.Test' as the 'StartUp' project.
				Note: 'YAT' and 'YATConsole' don't have dependencies to the test projects, thus those would not get built with 'YAT'.

		1.3.3.		Build 'Debug Test' using ‘Build Solution’ / [F6]. (Explicitly building ‘YAT.Test’ would not build the .exe projects!)

		1.3.4.		Use NUnit on 'Debug Test'.
				> "Visual Studio > Tools > NUnit" (Alt+N).
				> Categories = Select and exclude all longer than a minute (but keep 1 minute because some tests just take this long).
				> "Project > Configurations > Debug" ('Debug' @ regression + 'Release' @ final).

				List of test assemblies, for manual ticking:
				> MKY.Test (0' 25'')
				> MKY.IO.Ports.Test (2' 00'')
				> MKY.IO.Serial.SerialPort.Test (0' 00'')
				> MKY.IO.Serial.Socket.Test (4' 40'')
				> MKY.IO.Serial.Usb.Test (0' 15'')
				> MKY.IO.Usb.Test (0' 30'' but see issue below)
				> MKY.Net.Test (0' 00'')
				> NUnit (0' 00'')
				> YAT.Application.Test (0' 60'' including interaction)
				> YAT.Domain.Test
				> BinaryTerminal (0' 00'')
				> Parser (0' 02'')
				> Terminal (1h 20' !! where SendTest takes 1h 20')
				> TextTerminal (18' 00'')
				> YAT.Model.Test
				> Clear (0' 05'')
				> Command (0' 00'')
				> Connection (1' 45'')
				> FileHandling (0' 20'')
				> Launch (0' 03'')
				> LineExceeded (0' 04'')
				> Stress (0' 00'' but see issue below)
				> Transmission (18' 00'')
				> MTSicsDevice (5' 30'')
				> OneWay (5' 30'')
				> Repeating (6' 30'')
				> TwoWay (0' 30'')
				> YAT.Settings.Test (0' 15'')
				> YAT.Test (0' 00'' (test config generator only, no real tests))
				> YAT.View.Test (0' 45'')

				Known issues:
				MKY.IO.Usb.Test.ConnectionTest is not yet implemented => Assert.Ignore() => yellow bar.
				YAT.Model.Test.StressTest is not yet implemented => Assert.Ignore() => yellow bar.

				In case a test fails, simply try again.

				Note: Run takes around two hours, but expect some time for instabilities and fix of minor issues

	1.4.			Perform manual tests		20:00		26:00:00
		1.4.1.		Ensure to select 'YAT' as the 'StartUp' project.		Duration doesn't include time for major fixes.

		1.4.2.		According to manual test cases in "\YAT\_Doc.Project\5 - Test\YAT – Test.ods" using 'Release' configuration but still 'Start Debugging [F5]' to handle issues.

				Scopes that haven't changed at all since last release may be skipped.

				List of test sections, for manual ticking:
				> MKY.IO.Serial.SerialPort (1h 30')
				> MKY.IO.Serial.Socket (45')
				> TCP/IP (15')
				> UDP/IP (30')
				> MKY.IO.Serial.Usb (30')
				> YAT.Domain.Terminal (2h)
				> YAT.Model.Main (15')
				> YAT.Model.Terminal (2h)
				> YAT.View (to be redone => N/A)
				> YAT.View.Forms.Main (15')
				> YAT.View.Forms.Terminal (1h 30')
				> YAT.View.Forms.Settings (45')
				> YAT.Log (15')
				> YAT.Info (15')
				(Installation not yet, will be done in 5.)

				Note: Performing takes around ten hours, but expect some time for instabilities and fix of minor issues

## 2. Documentation
				Duration	Step		Total

2.				Documentation		00:00	00:10	26:00	26:10

	2.1.			Quick Reference		00:10		26:10
		2.1.1.		Update [YAT Quick Reference] if needed

## 3. Preparation
				Duration	Step		Total

3.				Preparation		00:00	01:55	26:10	28:05

	3.1.			Set versions		00:30		26:40
		3.1.1.		Ensure that product version in ALAZ.Version is different than at last release.
				> Versions must differ to ensure proper installation/update! / > Additional increment makes sense… / …if source code gets used by other software. / …if preliminary test version got distributed.
		3.1.2.		Ensure that product version in MKY.Version is different than at last release.
				> Same reason as above.
		3.1.3.		Ensure that product version in netrtfwriter\RtfWriter\Properties\AssemblyInfo.cs is different than at last release.
				> Same reason as above.
		3.1.4.		Ensure that product version in NunitEx.Version is different than at last release.
				> Additional increment makes little sense as NUnit is not distributed.
				( Note that OxyPlot is based on assemblies and thus doesn't need to be modified. )
		3.1.5.		Ensure that product version in YAT.Version is different than at last release.
				> Same reason as above.
		3.1.6.		Set product version in MKY file headers *.* throughout "\Trunk\MKY" (385 occurrences, incl. 4 of port workaround analysis).
				> Also remove 'Development', if apparent, e.g. '// MKY Version 1.0.30'.
		3.1.7.		Set product version in NUnitEx file headers *.* throughout "\Trunk\NUnitEx" (11 occurrences).
				> Also remove 'Development', if apparent, e.g. '// NUnitEx Version 1.0.23'.
		3.1.8.		Set product version in YAT file headers *.* throughout "\Trunk\YAT" (310 occurrences).
				> Also remove 'Development', if apparent, e.g. '// YAT Version 2.4.1'.
		3.1.9.		Set product version in all other file headers (*.cs throughout \Trunk).
				> Search for all previous versions, e.g. '2.4.0' and '2.4.1' and replace them as required: / > Includes file header of Template.cs / ( FileVersionsTest.cs is OK. ) / ( SettingsFilesProvider.cs is OK. )
		3.1.10.		Set ProductBuildDesignation in "YAT.ApplicationBase.ApplicationEx".
		3.1.11.		Set ProductVersionStabilityIndication in "YAT.ApplicationBase.ApplicationEx".
		3.1.12.		Fill versions into 'The YAT story' in '0. Overview'.
		3.1.13.		Commit changes to SVN.
				> Check the SVN property status of each file

	3.2.			Set installation version		00:05		26:45
		3.2.1.		Set product title in "YAT.Setup.x86".
		3.2.2.		Set product version in "YAT.Setup.x86".
		3.2.3.		Set product title in "YAT.Setup.x64".
		3.2.4.		Set product version in "YAT.Setup.x64".
		3.2.5.		Commit changes to SVN.

	3.3.			Update settings defaults and schema in "YAT\!-Settings\!-Current"		00:30		27:15
		3.3.1.		Ensure to select 'YAT.Test' as the 'StartUp' project.

				Note: 'YAT' and 'YATConsole' don't have dependencies to the test projects, thus those would not get built with 'YAT'.

		3.3.2.		Create files using NUnit on 'Debug Test'.
				> Build ‘Debug Test’ using ‘Build Solution’ / [F6]. (Explicitly building ‘YAT.Test’ would not build the .exe projects.)
				> "Visual Studio > Tools > NUnit" (Alt+N).
				> YAT.Settings.Test.SettingsFilesArchiver.
				Note that explicit tests are only runable if no include/exclude filter is active!
		3.3.3.		Quick-Diff "\!-Settings\!-Current\*Default.xml".
		3.3.4.		Increase hard-coded settings versions if required.
		3.3.5.		Fill settings versions into '0. Overview'.
		3.3.6.		If any version has changed, create files again.
		3.3.7.		Detail-Diff the files.
				> Restore the <SettingsName> tag to YAT (result of NUnit).
				(Only applies to LU/RU that must use YAT vs. YATConsole, while the other settings use 'CommonName'.)
				> Manually set the <ProductVersion> tag to the YAT version (result of NUnit).
				> LocalUser: Restore the <Paths> tags to YAT (result of NUnit).
				> Terminal: Restore the <Log\Root> tags to YAT (result of NUnit).
		3.3.8.		Also diff and verify *Schema.xsd.

	3.4.			Add new settings defaults and schema to settings archive		00:05		03:20:00
		3.4.1.		Archive *Default.xml from "\YAT\!-Settings\!-Current" to "\<New Version>".
		3.4.2.		Archive *Schema.xsd from "\YAT\!-Settings\!-Current" to "\<New Version>".
		3.4.3.		Commit changes to SVN.

	3.5.			Upgrade settings in settings archive "YAT\!-Settings\!-Current"		00:30		03:50:00
		3.5.1.		Prepare upgrade:
				> Delete all ‘YAT Local Settings’ folders in "C:\Users\<User>\AppData\Local\YAT\YAT".
				(ensure that window size is defaulted)
				(and cleans up intermediate development/preliminary/beta versions)
				> Delete all ‘YAT Roaming Settings’ folders in "C:\Users\<User>\AppData\Roaming\YAT\YAT".
				(just to ensure clean state)
				> Copy all terminal and workspace files of previous version to "\!-Current".
				(ensure that "\!-Current" will contain exact clones of the previous version)
				(should be so anyway, diff will tell)
				> In case of any diff, revert/commit as required.
				> Connect all test devices.
				(needed with some of the files)
		3.5.2.		Select 'YAT' as the 'StartUp' project.
		3.5.3.		Select 'Release' configuration.
		3.5.4.		Perform upgrade:
				> Run YAT not moving or resizing window.
				> [Ctrl+O] to open each old .yat or .yaw settings file in "YAT\!-Settings\!-Current".
				> For .yat, explicitly save settings:
				> File > Save [Ctrl+S].
				> For .yaw, explicitly save all settings:
				> File > Save All Terminals [Ctrl+Shift+A].
				(Note: "Terminal saved" may not be visible due to too long I/O status text.)
				> File > Workspace > Save Workspace [Ctrl+Shift+W].
				(Note on ‘09’ / ‘10’: No issue that some of the 6 terminals are not fully drawn.)
				> Close file(s) again.
				> For .yat:
				> File > Close [Ctrl+F4].
				(Note: Not 'Knigge' to display this standard shortcut in menu, therefore not there.)
				> For .yaw:
				> File > Workspace > Close.
		3.5.5.		Diff and verify the new settings.
				(Note: For workspaces with more than 2 terminals, the second terminal will have
				Location = <X>390</X> in .yaw and .yat. The root cause is unknown. Considered acceptable.)

	3.6.			Add new settings to settings archive		00:10		04:00:00
		3.6.1.		Archive the upgraded files in "YAT\!-Settings\<New Version>".
		3.6.2.		Add new settings to "YAT.Settings.Model.Test.SettingsFilesProvider" like previous version.
		3.6.3.		Add new settings to "YAT.Settings.Model.Test.FileVersionsTest" region "Tests".

	3.7.			Rebuild and commit		00:05		28:05:00
		3.7.1.		Select 'YAT.Test' as the 'StartUp' project.
		3.7.2.		Build 'Debug Test' (ensure no build errors).
		3.7.3.		Commit changes to SVN.

## 4. Final Testing
				Duration	Step		Total

4.				Final Testing		00:00	01:30:00	28:05	29:35

	4.1.			Re-Run coding style checks		00:10		28:15
		4.1.1.		Use StyleCop on 'Debug Test'.
				> "Visual Studio > Tools > Run StyleCop (Rescan All)".

				Note: Rescan just takes a few seconds, and there should not be many findings anymore.

	4.2.			Re-Run assembly checks		00:10		28:25
		4.2.1.		Ensure to select 'YAT.Test' as the 'StartUp' project.
				Note: 'YAT' and 'YATConsole' don't have dependencies to the test projects, thus those would not get built.

		4.2.2.		Build 'Debug Test' using ‘Build Solution’ / [F6]. (Explicitly building ‘YAT.Test’ would not build the .exe projects!)

		4.2.3.		Use FxCop 'MKY.Debug' on 'Debug Test'.
				> Open and verify "\MKY\MKY.Debug.FxCop".

				45 expected warnings:
				CA1002 : DoNotExposeGenericLists @ 9 locations.
				CA2214 : DoNotCallOverridableMethodsInConstructors @ 36 locations.

		4.2.4.		Use FxCop 'NUnit.Debug' on 'Debug Test'.
				> Open and verify "\NUnit\NUnit.Debug.FxCop".

		4.2.5.		Use FxCop 'YAT.Debug' on 'Debug Test'.
				> Open and verify "\YAT\YAT.Debug.FxCop".

				227 expected errors/warnings:
				CA1002 : DoNotExposeGenericLists @ 97 locations.
				CA2214 : DoNotCallOverridableMethodsInConstructors @ 130 locations.

				Note: Analysis just take a few seconds, and there should not be many findings anymore.
				But: FxCop is no longer capable to deal with YAT, as there now are references to .NET 4.0! FR#231!

	4.3.			Re-run automated tests		01:00		29:25
		4.3.1.		Ensure that test environment is fully ready (VSPE, hardware, MT-SICS,…).

				Attention: Time-out calibration (for whatever reason) no longer fits MKY machine => use MT machine.

		4.3.2.		Ensure to select 'YAT.Test' as the 'StartUp' project.
				Note: 'YAT' and 'YATConsole' don't have dependencies to the test projects, thus those would not get built with 'YAT'.

		4.3.3.		Build 'Release Test' using ‘Build Solution’ / [F6]. (Explicitly building ‘YAT.Test’ would not build the .exe projects!)

		4.3.4.		Use NUnit on 'Release Test'.
				> "Visual Studio > Tools > NUnit" (Alt+N).
				> Categories = Select and exclude all longer than a minute (but keep 1 minute because some tests just take this long).
				> "Project > Configurations > Release" (Debug @ Regression + Release @ Final).

				List of test assemblies, for manual ticking:
				> MKY.Test (0' 25'')
				> MKY.IO.Ports.Test (2' 00'')
				> MKY.IO.Serial.SerialPort.Test (0' 00'')
				> MKY.IO.Serial.Socket.Test (4' 40'')
				> MKY.IO.Serial.Usb.Test (0' 15'')
				> MKY.IO.Usb.Test (0' 30'' but see issue below)
				> MKY.Net.Test (0' 00'')
				> NUnit (0' 00'')
				> YAT.Application.Test (0' 60'' including interaction)
				> YAT.Domain.Test
				> BinaryTerminal (0' 00'')
				> Parser (0' 02'')
				> Terminal (1h 20' !! where SendTest takes 1h 20')
				> TextTerminal (18' 00'')
				> YAT.Model.Test
				> Clear (0' 05'')
				> Command (0' 00'')
				> Connection (1' 45'')
				> FileHandling (0' 20'')
				> Launch (0' 03'')
				> LineExceeded (0' 04'')
				> Stress (0' 00'' but see issue below)
				> Transmission (18' 00'')
				> MTSicsDevice (5' 30'')
				> OneWay (5' 30'')
				> Repeating (6' 30'')
				> TwoWay (0' 30'')
				> YAT.Settings.Test (0' 15'')
				> YAT.Test (0' 00'' (test config generator only, no real tests))
				> YAT.View.Test (0' 45'')

				Known issues:
				MKY.IO.Usb.Test.ConnectionTest is not yet implemented => Assert.Ignore() => yellow bar.
				YAT.Model.Test.StressTest is not yet implemented => Assert.Ignore() => yellow bar.

				In case a test fails, simply try again.

				Note: Run takes around two hours, and there should be no findings anymore.

	4.4.			Check and commit		00:10		29:35
		4.4.1.		Ensure no debug left-overs by globally searching for "PENDING".
				> Match case.
				> No match whole word.

		4.4.2.		Ensure no debug left-overs by globally searching for "!!!".
				> Case doesn't matter.
				> No match whole word.

				28 occurrences totally expected:
				> 27 occurrences expected in Template.cs.
				> 1 occurrence expected in Main.cs.

		4.4.3.		Ensure no debug left-overs by globally searching for "Trace.Write".
				> Match case.
				> No match whole word.

				332 occurrences totally expected, 10 as listed below, others only in test projects.
				> 2 occurrences expected in Diagnostics\TraceWrapper.cs.
				> 6 occurrences expected in Drawing\DrawingEx.cs.
				> 2 occurrences expected in Serializer.TolerantXmlSerializer.cs.

		4.4.4.		Ensure no debug left-overs by globally searching for "Debug.Write".
				> Match case.
				> No match whole word.

				156 occurrences totally expected:
				> 1 occurrence expected in ALAZ.
				> Several in ArgsHandler, Configuration, Diagnostics, EnvironmentEx, EventHelper,…
				> Several more in Usb, Hid, Terminal, Workspace, SendFile, SendText,…

		4.4.5.		Ensure no debug left-overs by globally searching for "Debugger.Break".
				> Match case.

				20 occurrences totally expected:
				> 4 occurrences expected in EventHelper.
				> 7 occurrences expected related to SplitContainerHelper.
				> 9 occurrences expected related to On...Request() handlers.

		4.4.6.		Ensure no debug left-overs by globally searching for "^\s*#define DEBUG".
				> Match Regex.

		4.4.7.		Commit changes to SVN.

## 5. Build
				Duration	Step		Total

5.				Build		00:00	00:40	29:35	30:15

	5.1.			Finalize release notes		00:10		29:45
		5.1.1.		Check whether release notes are complete.
		5.1.2.		Check whether limitations still apply.
		5.1.3.		Update the road map if necessary.
		5.1.4.		Spell check the release notes in word.
		5.1.5.		Clone release notes to those limited to 64 KB.
				> Check number of bytes, remove additional releases if number of lines exceeds 64k.
		5.1.6.		Commit changes to SVN.

	5.2.			Prepare package directory		00:10		29:55
		5.2.1.		Check whether ReadMe's are up-to-date
				> \YAT\!-Doc.Project\6 - Release\Distribution Template\Setup.x64
				> \YAT\!-Doc.Project\6 - Release\Distribution Template\x64 Binaries
		5.2.2.		Clone ReadMe's using 'Clone.x64.ReadMe.cmd'.
		5.2.3.		Copy the release notes to the package directories using 'CopyRelNotes.cmd'.
				> SourceForge requires the file to contain 'readme' in the name.
		5.2.4.		Copy the supplements to the package directories using 'CopySupplements.cmd'.
				> Named 'Supplements' to be located after 'R'.
		5.2.5.		Commit changes to SVN.

				Note: The distribution directory will be filled in a further step.

	5.3.			Build packages		00:20		30:15
		5.3.1.		Check 'YAT.Setup.x86|x64' prerequisites for 'Setup'.
				> Optimize for speed.
		5.3.2.		Check 'YAT.Setup.x86|x64' prerequisites for 'Setup with Prerequisites'.
				> Optimize for size.
		5.3.3.		Build > Batch Build > Clean all configurations for all target platforms.
				> Reduces the risk of mistakenly taking the wrong assemblies.
				> Check the intermediate folders of "\YAT\YAT\bin".
		5.3.4.		Build [YAT] for 'x86'.
				> Ensure to start build at the beginning of a minute (in order to have same timestamp on all artifacts, all 3 builds take about 40 seconds).
				> Build [Release] for [x86] using 'Build Solution' / [F6].
				(Separated from "Setup" and "Setup with Prerequisites" because both two packages shall contain the same binaries.)
				> Build [Setup] for [x86] using 'Build Solution' / [F6].
				> Build [Setup with Prerequisites] for [x86] using 'Build Solution' / [F6].
		5.3.5.		Build [YAT] for 'Any CPU' => 'x64'.
				> Ensure to start build at the beginning of a minute (in order to have same timestamp on all artifacts, all 3 builds take about 40 seconds).
				> Build [Release] for [Any CPU] using 'Build Solution' / [F6].
				(Separated from "Setup" and "Setup with Prerequisites" because both two packages shall contain the same binaries.)
				> Build [Setup] for [Any CPU] using 'Build Solution' / [F6].
				> Build [Setup with Prerequisites] for [Any CPU] using 'Build Solution' / [F6].

				Notes on 'x86' and 'x64'/'Any CPU':
				> 'x86' is a dedicated 'x86' build for providing compatibility with WinCE/EC (e.g. FixiFoxi).
				> 'x64' targets 64-bit systems and will get installed to "C:\Program Files\".
				But 'Any CPU' builds are used to allow direct use from MSIL projects (e.g. Scripting or PowerShell).
				See bug #507 for a concrete error message when attempting to use an 'x64' build from PowerShell.
				Consequence is an inconsistency in the solution configuration, where 'x64' uses 'Any CPU' for 'Setup' and 'Setup with…'.
				But this is acceptable, given that the use of 'Any CPU' is best practise also for other libraries, e.g. CS-Script or OxyPlot.
				Still, the 'x64' configurations are kept in case of ever requiring it (makes little sense to remove now).

				Notes on prerequisites:
				> The prerequisites require the download and copy of 'ndp48-x86-x64-allos-enu.exe' to:
				C:\Program Files (x86)\Microsoft Visual Studio 14.0\SDK\Bootstrapper\Packages\DotNetFX48
				> The prerequisites result in three WARNINGs:
				"Xml validation did not pass for item 'Microsoft .NET Framework 4.8 (x86 and x64)'…"
				"Xml Validation error in file 'C:\Program Files (x86)\Microsoft Visual Studio 14.0\SDK\…"
				"The value of the 'PublicKey' attribute in 'Microsoft .NET Framework 4.8 (x86 and x64)'"
				These WARNINGs are considered acceptable and can be ignored.

## 6. Installation Testing
				Duration	Step		Total

6.				Installation Testing		00:00	00:40	30:15	30:50

	6.1.			Preparation		00:05		30:20
		6.1.1.		Close Visual Studio.
				> Needed to ensure that YAT doesn't detect already running "YAT.vshost.exe" on startup.
		6.1.2.		Ensure that no current Local User Settings are already available.
		6.1.3.		Ensure that no current Roaming User Settings are already available.
		6.1.4.		Ensure that previous Local/Roaming User Settings are available.
				> Use previous installed version and create 2 interconnected serial COM port terminals.

	6.2.			Installation		00:05		30:25
		6.2.1.		Install YAT.

	6.3.			Run manual after-installation tests		00:30		30:50
		6.3.1.		Run according to manual after-installation test cases.

## 7. Packaging
				Duration	Step		Total

7.				Packaging		00:00	00:40	30:50	31:30

	7.1.			Commit and tag YAT		00:10		31:00
		7.1.1.		Commit any modifications to the subversion repository.
		7.1.2.		Tag/checkpoint the project:
				> SVN > Repo-browser.
				> Select 'trunk' in tree-view.
				> Copy to...
				> New name e.g. "<...>/tags/yat-2-4-0".
				> Message e.g. "YAT 2.4.0".
				> Wait for completion, just takes a few seconds.
				> Prepare release mail in the meantime.
				> Select 'tags' in tree-view.
				> Check new tag (Refresh if not visible yet).
		7.1.3.		Fill the tag's SVN revision into 'The YAT story' in '0. Overview'.

				Notes:
				> Technically the build should be done based on the tag.
				However, for being able to perform installation testing, tagging is done after build.
				> At the release of YAT 2.4.0, the TortoiseSVN Repo Browser crashed on tagging.
				> Using AnhkSVN has worked fine

	7.2.			Pack YAT		00:30		31:30
		7.2.1.		Create a new folder in "<Offline\Releases>" based on the template.
		7.2.2.		Fill-in "\Distribution" based on "\YAT\!-Doc.Project\6 - Release\Distribution Template".
		7.2.3.		Update the 6 folders in "\Distribution":
				> Copy packages from "Setup" projects.
				> Assemble "Binaries":
				> Open C:\Program Files\YAT and count the number of binaries:
				> 26 .dll
				> 2 .exe
				> 2 .exe.config
				> Copy "YAT.exe", "*.dll" and "YAT.exe.config":
				> "\YAT\bin\Release" => Any CPU => x64.
				(See [5. Build] for background.)
				> "\YAT\bin\x86\Release" => x86.
				> Copy "YATConsole.exe" and "YATConsole.exe.confg" from that project.
				> Copy "DejaVu Info" from installed C:\Program Files\YAT.
				> Copy "netrtfwriter Info" from installed C:\Program Files\YAT.
				> Copy "OxyPlot Info" from installed C:\Program Files\YAT.
		7.2.4.		Run sanity checks:
				> x64 YAT.exe
				> Open [Help >About…] and fill the build into 'The YAT story' in '0. Overview'.
				> x86 YATConsole.exe
				> Open [Help >About…] and fill the build into 'The YAT story' in '0. Overview'.
		7.2.5.		Zip the 6 distribution files.
				> Zip within folders, i.e. shall not contain the folder again, then move to parent.
		7.2.6.		Name the 6 distribution files.
				> "YAT-2.4.0_x64_(64-bit).zip".
				> "YAT-2.4.0_x64_(64-bit)_with_.NET_runtime.zip".
				(Named x64 even though it is using 'Any CPU' builds for not confusing the users.)
				(Also, x64 clearly indicates the target, as well as "C:\Program Files\".)
				> "YAT-2.4.0_x86_(32-bit).zip".
				> "YAT-2.4.0_x86_(32-bit)_with_.NET_runtime.zip".
				> "YAT-2.4.0_x64_(64-bit)_binaries_only.zip".
				> "YAT-2.4.0_x86_(32-bit)_binaries_only.zip".
				(Binaries last corresponding to order of package folders.)
		7.2.7.		Compare size of packages against last release (plausibility check).

				Note:
				Bugs #318 and #323 suggested to only distribute .msi for easier use.
				However, IE10+ by default does not allow to download (SHA1) .msi !!!
				New FR#274 “Find a way to distribute as .msi only” created.

## 8. Upload
				Duration	Step		Total

8.				Upload		00:00	01:50	30:50	32:40

	8.1.			Update statistics		00:20		31:10
		8.1.1.		Update "\YAT\!-Doc.SourceForge\Statistics.ods".
				Note: More than 10 min if statistics is completely updated.

	8.2.			Prepare upload		00:10		31:20
		8.2.1.		Log in as 'y-a-terminal'.
				> Ensure that new folder as well as files are "owned" by neutral user
		8.2.2.		Go to 'SourceForge > YAT > Files'.
		8.2.3.		Add archive folder (e.g. "Version 2.1.0").
		8.2.4.		Move current to archive using FileZilla.
				> Explicitly fill-in "sftp://frs.sourceforge.net | y-a-terminal | PW+OTP | 22".
				> PW is dedicated!
				> "/home/pfs/project/y-a-terminal".
				> Use tree view to open the intended archive folder.
				> Then drag and drop files to that folder.
				> Sequentially move for proper sequence !!!
				> Intended order:
				> RelNotes – x86 bin – x86.NET – x86 – x64 bin – x64.NET – x64.
				> Don't care about '+' symbol, files will get moved anyway.
				> Exit FileZilla, it is not used anymore.
		8.2.5.		Exclude archived RelNotes from statistics.

	8.3.			Add release		01:00		32:20
		8.3.1.		Upload distributions using the web interface.
				> Sequentially upload for proper sequence !!!
				> Intended order:
				> RelNotes
				> Check whether content of file limited to 64 KB is completely displayed.
				> x86 bin – x86.NET – x86 – x64 bin – x64.NET – x64.
				> Large uploads take 20-30 minutes (for ~140 MB).
		8.3.2.		Tick default platform download on normal x64 distribution.
		8.3.3.		Exclude RelNotes from statistics.
		8.3.4.		Also replace RelNotes in archive main folder.
		8.3.5.		Also exclude RelNotes in archive main folder from statistics.

	8.4.			Check release and release notes		00:10		32:30
		8.4.1.		Reload YAT web page.
				> It takes a moment until the uploaded files are ready for download.
		8.4.2.		Download default file with Firefox.
		8.4.3.		Download all files with Firefox.
		8.4.4.		Download all files with Edge.
				> Verifies digital signature issues…
		8.4.5.		Verify contents of .msi / .zip.
				> At least open the ReadMe or RelNotes.
				> Extract x64 binaries to workspace and execute both .exe.
				> Extract x64 with runtime to temporary folder and execute setup.
				> Error message that app already installed.

	8.5.			Feature request and bug trackers		00:10		32:40
		8.5.1.		Check that items that are covered by this release have been closed.
				> OK if closed with 'y-a-terminal' account.

## 9. Finalization
				Duration	Step		Total

9.				Finalization		00:00	03:30	32:40	35:40

	9.1.			Send email to the YAT mailing list (Attention: Mail delay up to 60 min !!!)		00:30		33:10
		9.1.1.		Write email based on earlier mailings.
		9.1.2.		> Make sure that links are updated completely, i.e. link text and link itself.
				> Make sure the correct release notes are used.
		9.1.3.		Check spelling.
		9.1.4.		Send as "y-a-terminal@users.sourceforge.net".
		9.1.5.		Send to "y-a-terminal-users@lists.sourceforge.net".
		9.1.6.		Send encoded in Unicode.
				> Thunderbird: [Options > Encoding > Unicode]
		9.1.7.		Send as Text+HTML.
				> Thunderbird: [Options > Format > Text+HTML]
		9.1.8.		Send :-)
		9.1.9.		Save email in offline archive "\Distribution".
		9.1.10.		Accept email as moderator in mailman at https://lists.sourceforge.net/lists/admin/y-a-terminal-users
				> Access is described in offline data.
				> May take up to 60 min until possible.
				> Mail may also be delayed up to 60 min.

	9.2.			Submit news		00:15		33:25
		9.2.1.		[Develop > News > New Post]
				Title:
				"YAT 2.4.0"
				Text:
				"<Intro of release mail>"

	9.3.			Cleanup		00:15		09:40:00
		9.3.1.		Log out from SourceForge as 'y-a-terminal' and log in as 'maettu_this' again.
		9.3.2.		Send thanks mails.
				> People who are waiting for release / had dropbox access / gave feedback (YAT, MT, HFU,…).
		9.3.3.		Clean up preliminaries in dropbox.
		9.3.4.		Remove people from dropbox.
				> Also send mail to the office to do the same there.
		9.3.5.		Commit any modifications during the release process to the subversion repository.

	9.4.			Upgrade tools		01:00		10:25:00
		9.4.1.		Check for updates of Visual Studio and extensions.
				> In case of update, install everything including extensions.
		9.4.2.		Check for updates of all "\Tools\! - Tools and Versions.txt".
		9.4.3.		Also check for updates of TortoiseGIT.

	9.5.			Recreate and verify working copy		00:15		09:55:00
		9.5.1.		Check the tag revision out into "Tag <Version>".
		9.5.2.		Rename the existing working copy to "Trunk_<New Date>".
				> Intermediate _ ensures proper ordering.
		9.5.3.		Remove existing backups "Trunk_<Old Date>".
		9.5.4.		Create a new folder "Trunk".
		9.5.5.		Check the head revision out into "Trunk".
				> Make sure that only "...\code\trunk\" is checked out, not the whole repository.
		9.5.6.		Open the YAT solution.
		9.5.7.		Set 'YAT.Test' as the active startup project.
		9.5.8.		Fold all folders/projects.
		9.5.9.		Build 'Debug Test' to ensure that all files got committed from former working copy.
		9.5.10.		If VS/VSI got upgraded:
				> Set 'YAT' as the active startup configuration.
				> Build 'Setup with Prerequisites' to ensure that VSI properly builds.
		9.5.11.		Set 'YAT' as the active startup project.
		9.5.12.		Set 'Debug' as the active solution configuration.

	9.6.			Archive		00:15		10:40:00
		9.6.1.		Export the original working copy to a temporary folder (e.g. "D:\Temp\YAT\Archive").
				> Use 'SVN > Export…'.
				(Note this is the archive, not a backup, that is "Trunk_<New Date>".)
		9.6.2.		Pack the copy into a properly named zip.
		9.6.3.		Sanity check the size of the zip.
		9.6.4.		Move the zip to offline archive "<Version>\Working Copy".

	9.7.			Backup		01:00		11:40:00
		9.7.1.		Commit any modifications during the upgrade/recreate process to the subversion repository.
		9.7.2.		Backup the trackers to the offline archive.
		9.7.3.		Manually backup onto offline disk.
				> Backup onto NAS is done automatically.

## 10. Aftermath
				Duration	Step		Total

10.				Aftermath		00:00	00:15	35:40	35:55

	10.1.			Update and verify working copy => Wait for a few days in case of a severe issue		00:15		11:55:00
		10.1.1.		Increment product version in ALAZ.Version.
		10.1.2.		Increment product version in MKY.Version.
		10.1.3.		Increment product version in netrtfwriter\RtfWriter\Properties\AssemblyInfo.cs.
		10.1.4.		Increment product version in NUnit.Version.
		10.1.5.		Increment product version in YAT.Version.
		10.1.6.		Set product version in MKY file headers *.* throughout "\Trunk\MKY" (385 occurrences, incl. 4 of port workaround analysis).
				> Append 'Development', e.g. '// MKY Version 1.0.28 Development'.
		10.1.7.		Set product version in NUnitEx file headers *.* throughout "\Trunk\NUnitEx" (11 occurrences).
				> Append 'Development', e.g. '// NunitEx Version 1.0.22 Development'.
		10.1.8.		Set product version in YAT file headers *.* throughout "\Trunk\YAT" (310 occurrences).
				> Append 'Development', e.g. '// YAT Version 2.3.90 Development'.
		10.1.9.		Set stability indication in "YAT.Application.Base.ApplicationEx".
				> Activate 'Development' to clearly indicate non-release state.
		10.1.10.		Add a new section to the release notes.
				> Copy limitations and known issues from last release.
		10.1.11.		Verify that the solution still properly builds and runs.