## 0. Overview
A YAT release is done in 8 steps:
				Duration	Step	Total
		1.	Regression Testing		09:00	09:00
		2.	Preparation		02:10	11:10
		3.	Final Testing		04:50	16:00
		4.	Build		00:30	16:30
		5.	Installation Testing		00:40	17:10
		6.	Packaging		00:40	17:10
		7.	Upload		01:00	18:10
		8.	Finalization		02:10	20:00

The YAT story:
					YAT	MKY	ALAZ	NUnit	netrtfwr.		LU.xml	.yat	.yaw		SVN
		:	YAT 2.0 Gamma 2				1.99.50	1.0.15	3.5.12	1.0.12	0.9.13		1.4.1	1.4.1	1.2.0
	2015-06-13	:	YAT 2.0 Gamma 1''				1.99.34	1.0.13	3.5.11	1.0.10			1.4.1	1.4.1	1.2.0		799
	2015-06-07	:	YAT 2.0 Gamma 1'				1.99.33	1.0.12	3.5.10	1.0.9			1.4.0	1.4.0	1.2.0		778
	2015-06-01	:	YAT 2.0 Gamma 1				1.99.32	1.0.11	3.5.9	1.0.8			1.4.0	1.4.0	1.2.0		769
	2013-02-02	:	YAT 2.0 Beta 4 Candidate 2				1.99.30	1.0.9	3.5.7	1.0.6			1.3.1	1.3.1	1.1.1		626
	2011-12-05	:	YAT 2.0 Beta 4 Candidate 1				1.99.28	1.0.7	3.5.5	1.0.4			1.3.0	1.3.0	1.1.0		502
	2011-04-25	:	YAT 2.0 Beta 3 Candidate 4				1.99.26	1.0.5	3.5.3	1.0.2			1.2.4	1.2.9	1.0.0		419
	2010-11-28	:	YAT 2.0 Beta 3 Candidate 3				1.99.25	1.0.4	3.5.2	1.0.1			1.2.4	1.2.9	1.0.0		385
	2010-11-11	:	YAT 2.0 Beta 3 Candidate 2				1.99.24	1.0.4	3.5.2	1.0.1			1.2.4	1.2.8	1.0.0		369
	2009-09-10	:	YAT 2.0 Beta 3 Candidate 1				1.99.23	1.0.1	3.5.0				1.2.4	1.2.7	1.0.0		251
	2009-09-08	:	YAT 2.0 Beta 3 Candidate 1				1.99.22	1.0.1	3.5.0				1.2.3	1.2.6	1.0.0		247
	2008-07-18	:	YAT 2.0 Beta 2 Candidate 4				1.99.20	1.0.0	1.2.0				1.2.3	1.2.5	1.0.0		201
	2008-04-01	:	YAT 2.0 Beta 2 Candidate 3				1.99.19					1.2.2	1.2.4	1.0.0		136
	2008-03-17	:	YAT 2.0 Beta 2 Candidate 2				1.99.18					1.2.2	1.2.3	1.0.0		122
	2008-02-11	:	YAT 2.0 Beta 2 Candidate 1				1.99.17					1.2.2	1.2.2	1.0.0		105
	2007-08-30	:	YAT 2.0 Beta 2 Preliminary				1.99.13					1.2.1	1.2.1	1.0.0		(45)
	2007-04-15	:	YAT 2.0 Beta 1				1.99.12					1.2.0	1.2.0			9
	2007-02-25	:	YAT 2.0 Alpha 3				1.99.8					1.1.2	1.1.2
	2007-02-07	:	YAT 2.0 Alpha 2				1.99.3					1.1.1	1.1.1
	2007-01-23	:	YAT 2.0 Alpha 1				1.99.0					1.1.0	1.1.0
	2003-10-31	:	XTerm232				1.0.2					1.0.1	1.0.1
	2003-10-30	:	XTerm232				1.0.1					1.0.1	1.0.1
	2003-10-14	:	XTerm232				1.0.0					1.0.0	1.0.0

## 1. Regression Testing
				Duration	Step		Total

1.				Regression Testing		00:00	09:00	00:00	09:00

	1.1.			Run coding style checks		01:00		01:00
		1.1.1.		Use StyleCop on 'Debug Test'
				> "Visual Studio > Tools > Run StyleCop (Rescan All)"

				1 expected warning:
				SA1409 : CSharp.Maintainability @ YAT.Model.Terminal.cs

				Note: Rescan just takes a few seconds, but expect quite some time for fixes

	1.2.			Run assembly checks		02:00		03:00
		1.2.1.		Use FxCop 'MKY.Debug' on 'Debug Test'
				> Open and verify "\MKY\MKY.Debug.FxCop"

				26 expected warnings:
				CA2214 : DoNotCallOverridableMethodsInConstructors @ 26 locations

		1.2.2.		Use FxCop 'NUnit.Debug' on 'Debug Test'
				> Open and verify "\NUnit\NUnit.Debug.FxCop"

		1.2.3.		Use FxCop 'YAT.Debug' on 'Debug Test'
				> Open and verify "\YAT\YAT.Debug.FxCop"

				135 expected errors/warnings:
				CA1002 : DoNotExposeGenericLists @ 52 locations
				CA2214 : DoNotCallOverridableMethodsInConstructors @ 83 locations

				Note: Rescan just takes a few seconds, but expect quite some time for fixes

	1.3.			Run automated tests		06:00		09:00
		1.3.1.		Ensure to select 'YAT.Test' as the 'StartUp' project

				Note: 'YAT' or 'YATConsole' don't have dependencies to the test projects, thus they will not get built!

		1.3.2.		Configure NUnit test categories
				> "Visual Studio > Tools > NUnit" (Alt+N)
				> Categories = Select and exclude "Interactive" and all longer than 2 minutes

		1.3.3.		Use NUnit on 'Debug Test'
				> "Visual Studio > Tools > NUnit" (Alt+N)
				> "Project > Configurations > Debug"

				Expected errors/warnings:
				YAT.Gui.Test.StressTest.TestTransmissionDisplay fails automatically, successfully passes when manually started ?!?
				YAT.Model.Test.<Various> fail for 'OnSpecificIPv4/6Interface', install/config of "TAP-Win32 Adapter" is required
				YAT.Model.Test.Repeating.Perform.<Any>02/10TwoWay fail
				YAT.Settings.Test.FileVersionsTest.V1.99.13/17/18/19[01|02] fail (bugs #232 and #246 "Issues with [Alternate]TolerantXmlSerializer")

				Note: Run takes around 20 minutes, but expect quite some time for fixes

## 2. Preparation
				Duration	Step		Total

2.				Preparation		00:00	02:10	09:00	11:10

	2.1.			Set versions		00:20		09:20
		2.1.1.		Ensure that product version in ALAZ.Version is different than at last release
		2.1.2.		Ensure that product version in netrtfwriter AssemblyInfo is different than at last release
				> Increment makes little sense as there is are no version tags in file header
		2.1.3.		Increment product version in MKY.Version
		2.1.4.		Increment product version in NUnit.Version
		2.1.5.		Increment product version in YAT.Version
				> Versions must be incremented to ensure proper installation/update!
		2.1.6.		Set product name post fix in "YAT.Utilities.ApplicationInfo"
				> Remove 'Development'
		2.1.7.		Set product version in MKY file headers
				> Also remove 'Development', e.g. '// MKY Version 1.0.12'
		2.1.8.		Set product version in NUnit file headers
				> Also remove 'Development', e.g. '// NUnit Version 1.0.9'
		2.1.9.		Set product version in YAT file headers
				> Also remove 'Development', e.g. '// YAT 2.0 Gamma 1 Version 1.99.33'
		2.1.10.		Commit changes to SVN
				> Check the property status of each file
				> Ensure not to commit modified settings file(s)
		2.1.11.		Fill date and versions into 'The YAT story' in '0. Overview'

	2.2.			Set installation version		00:05		09:25
		2.2.1.		Set product title in "YAT.Setup.x86"
		2.2.2.		Set product version in "YAT.Setup.x86"
		2.2.3.		Set product title in "YAT.Setup.x64"
		2.2.4.		Set product version in "YAT.Setup.x64"

	2.3.			Update settings defaults and schema in "YAT\!-Settings\!-Current"		00:30		09:55
		2.3.1.		Update settings versions if required
		2.3.2.		Fill settings versions into '0. Overview'
		2.3.3.		Create files using NUnit on 'Debug Test'
				> Build "Debug Test"
				> "Visual Studio > Tools > NUnit" (Alt+N)
				> YAT.Settings.Test.SettingsFilesArchiver
				(Note that explicit tests are only enableable if no include/exclude filter is active)
		2.3.4.		Diff and verify the files in "YAT\!-Settings\!-Current"
				> Manually modify the product version tag to the YAT version (result of NUnit)

	2.4.			Add new settings defaults and schema to settings archive		00:15		10:10
		2.4.1.		Archive the upgraded files in "YAT\!-Settings\<New Version>"

	2.5.			Upgrade settings in settings archive "YAT\!-Settings\!-Current"		00:30		10:40
		2.5.1.		Upgrade settings
				> Copy default settings to the "YAT Local Settings" to ensure that window size is defaulted
				> Ensure that "YAT\!-Settings\!-Current" contains exact clones of the previous version
				> Run YAT and open old settings
				> Modify settings
				> For terminals, change radix to ensure that IO settings are kept
				> For workspaces, change tile to ensure that terminal settings are kept
				> Undo changes
				> Save upgraded but unchanged settings
		2.5.2.		Diff and verify the new settings

	2.6.			Add new settings to settings archive		00:15		10:55
		2.6.1.		Archive the upgraded files in "YAT\!-Settings\<New Version>"
		2.6.2.		Add new settings to "YAT.Settings.Test.SettingsFilesProvider"
		2.6.3.		Add new settings to "YAT.Settings.Test.FileVersionsTest"

	2.7.			Rebuild and commit		00:15		11:10
		2.7.1.		Rebuild 'Debug Test'
		2.7.2.		Commit changes to SVN

## 3. Final Testing
				Duration	Step		Total

3.				Final Testing		00:00	04:50	11:10	16:00

	3.1.			Re-Run coding style checks		00:10		11:20
		3.1.1.		Use StyleCop on 'Debug Test'
				> "Visual Studio > Tools > Run StyleCop (Rescan All)"

				1 expected warning:
				SA1409 : CSharp.Maintainability @ YAT.Model.Terminal.cs

				Note: Rescan just takes a few seconds, and there should be no more findings

	3.2.			Re-Run assembly checks		00:10		11:30
		3.2.1.		Use FxCop 'MKY.Debug' on 'Debug Test'
				> Open and verify "\MKY\MKY.Debug.FxCop"

				26 expected warnings:
				CA2214 : DoNotCallOverridableMethodsInConstructors @ 26 locations

		3.2.2.		Use FxCop 'NUnit.Debug' on 'Debug Test'
				> Open and verify "\NUnit\NUnit.Debug.FxCop"

		3.2.3.		Use FxCop 'YAT.Debug' on 'Debug Test'
				> Open and verify "\YAT\YAT.Debug.FxCop"

				135 expected errors/warnings:
				CA1002 : DoNotExposeGenericLists @ 52 locations
				CA2214 : DoNotCallOverridableMethodsInConstructors @ 83 locations

				Note: Rescan just takes a few seconds, and there should be no more findings

	3.3.			Run automated tests		00:30		12:00
		3.3.1.		Ensure to select 'YAT.Test' as the 'StartUp' project

				Note: 'YAT' or 'YATConsole' don't have dependencies to the test projects, thus they will not get built!

		3.3.2.		Configure NUnit test categories
				> "Visual Studio > Tools > NUnit" (Alt+N)
				> Categories = Select and exclude "Interactive" and all longer than 2 minutes

		3.3.3.		Use NUnit on 'Debug Test'
				> "Visual Studio > Tools > NUnit" (Alt+N)
				> "Project > Configurations > Debug"

				Expected errors/warnings:
				YAT.Gui.Test.StressTest.TestTransmissionDisplay fails automatically, successfully passes when manually started ?!?
				YAT.Model.Test.<Various> fail for 'OnSpecificIPv4/6Interface', install/config of "TAP-Win32 Adapter" is required
				YAT.Model.Test.Repeating.Perform.<Any>02/10TwoWay fail
				YAT.Settings.Test.FileVersionsTest.V1.99.13/17/18/19[01|02] fail (bugs #232 and #246 "Issues with [Alternate]TolerantXmlSerializer")

				Note: Run takes around 20 minutes, and there should be no more findings

	3.4.			Disconnect all devices, restart computer, re-run automated tests		00:45		12:45
		3.4.1.		Re-run 3.3.3. above
		3.4.2.		Reconnect devices

	3.5.			Run interactive tests		00:10		12:55
		3.5.1.		Configure NUnit test categories
				> "Visual Studio > Tools > NUnit" (Alt+N)
				> Categories = Select and include "Interactive" only

		3.5.2.		Use NUnit on 'Debug Test'
				> "Visual Studio > Tools > NUnit" (Alt+N)
				> "Project > Configurations > Debug"
		3.5.3.		Use NUnit on 'Release Test'
				> "Visual Studio > Tools > NUnit" (Alt+N)
				> "Project > Configurations > Release"

	3.6.			Run manual tests		02:30		15:25
		3.6.1.		According to manual test cases in "\YAT\_Doc.Project\5 - Test\YAT - Test.ods"

	3.7.			Re-run automated tests		00:25		15:50
		3.7.1.		Use NUnit on 'Release Test' to ensure that modifications didn't re-introduce any bugs
				> "Visual Studio > Tools > NUnit" (Alt+N)
				> "Project > Configurations > Release"
				> Categories = Select and exclude "Interactive" and all longer than 2 minutes

				Note: Run takes around 20 minutes, and there should be no more findings

	3.8.			Check and commit		00:10		16:00
		3.8.1.		Ensure no debug left-overs by globally searching for "System.Diagnostics.Debug.Write"
				> Match case
				> No match whole word

				45 occurrences totally expected in ArgsHandler, Usb, Hid,...

		3.8.2.		Commit changes to SVN
				> Ensure not to commit modified settings file(s)

## 4. Build
				Duration	Step		Total

4.				Build		00:00	00:30	16:00	16:30

	4.1.			Finalize release notes		00:00		16:00
		4.1.1.		Add them cumulatively to "\!-Doc.User\YAT Release Notes.txt"
		4.1.2.		Check whether release notes are complete
		4.1.3.		Check whether limitations still apply
		4.1.4.		Update the road map if necessary

	4.2.			Prepare package directory		00:10		16:10
		4.2.1.		Add a new directory to the offline archive "\YAT\Releases and Checkpoints"
		4.2.2.		Check and update year of "!-ReadMe.txt" in the release package directories
		4.2.3.		Copy the release notes to all package directories
		4.2.4.		Also copy them to the distribution root and rename to "YAT Release Notes - ReadMe.txt"
				> SourceForge requires the file to contain 'readme' in the name

				Note: The distribution packages will be packed in a further step

	4.3.			Re-Build YAT		00:20		16:30
		4.3.1.		Check "YAT.Setup.x86|x64" prerequisites for "Release"
				> Optimize for speed
		4.3.2.		Check "YAT.Setup.x86|x64" prerequisites for "Release with Prerequisites"
				> Optimize for size
		4.3.3.		Clean ALL configuration for ALL target platforms
				> Reduces the risk of mistakenly taking the wrong assemblies
				> Check the intermediate folders of "\YAT\YAT\bin"
		4.3.4.		Build "Release" configuration for "x86"
				> Build "Setup" configuration for "x86"
				> Build "Setup with Prerequisites" configuration for "x86"
		4.3.5.		Clean "Release" configuration for "x86"
				> Reduces the risk of mistakenly taking the wrong assemblies
		4.3.6.		Build "Release" configuration for "AnyCPU" (reason see FR#229)
				> Build "Setup" configuration for "AnyCPU"
				> Build "Setup with Prerequisites" configuration for "AnyCPU"
		4.3.7.		Clean "Release" configuration for "AnyCPU"
				> Reduces the risk of mistakenly taking the wrong assemblies

## 5. Installation Testing
				Duration	Step		Total

5.				Installation Testing		00:00	00:40	16:30	17:10

	5.1.			Installation		00:10		16:40
		5.1.1.		Close Visual Studio
				> Needed to ensure that YAT doesn't detect already running "YAT.vshost.exe" on startup
		5.1.2.		Install YAT

	5.2.			Run manual after-installation tests		00:30		17:10
		5.2.1.		Run according to manual after-installation test cases

## 6. Packaging
				Duration	Step		Total

6.				Packaging		00:00	00:30	17:10	17:40

	6.1.			Commit and tag YAT		00:15		17:25
		6.1.1.		Commit any modifications to the subversion repository
				> Message e.g. "YAT 2.0 Gamma 1 Version 1.99.32"
		6.1.2.		Tag/checkpoint the project
				> SVN > Repo-browser
				> Select 'trunk' in tree-view
				> Copy to...
				> New name e.g. "<...>/tags/yat-1-99-32-gamma-1"
				> Message e.g. "YAT 2.0 Gamma 1 Version 1.99.32"
				> Select 'tags'
				> Check tag
		6.1.3.		Fill SVN revision into 'The YAT story' in '0. Overview'

	6.2.			Pack YAT		00:15		17:40
		6.2.1.		Update the 4 folders in "<Offline\Releases>\Distribution"
		6.2.2.		Create the 4 according distribution files
				> "YAT-2.0_Gamma-1_Version-1.99.32_x64_(64-bit).msi"
				> "YAT-2.0_Gamma-1_Version-1.99.32_x64_(64-bit)_with_.NET_runtime.zip"
				> "YAT-2.0_Gamma-1_Version-1.99.32_x86_(32-bit).msi"
				> "YAT-2.0_Gamma-1_Version-1.99.32_x86_(32-bit)_with_.NET_runtime.zip"

				Note: The compact packages are distributed .msi for easier use (input of bugs #318 and #323)

## 7. Upload
				Duration	Step		Total

7.				Upload		00:00	01:00	17:10	18:10

	7.1.			Prepare upload to SourceForge		00:10		17:20
		7.1.1.		Log in as 'y-a-terminal'
		7.1.2.		Go to 'SourceForge > YAT > Files > YAT 2.0'
		7.1.3.		Add release folder (e.g. "Version 1.99.32 - YAT 2.0 Gamma 1")

				HowTo:
				<https://sourceforge.net/apps/trac/sourceforge/wiki/Release%20files%20for%20download>

	7.2.			Add release		00:30		17:50
		7.2.1.		Upload distributions using the web interface
				> Intended order: x86.NET – x64.NET – x86 – x64
				> Manually upload for proper sequence !!!
				> All 4 distributions together take approx. 15 minutes (for ~450 MB)
		7.2.2.		Tick default platform download on normal x64 distribution
		7.2.3.		Upload release notes to the release folder
		7.2.4.		Upload release notes to the parent folder
		7.2.5.		Upload release notes to the root folder

	7.3.			Check release and release notes		00:10		18:00
		7.3.1.		Reload YAT web page
				> It takes a moment until the uploaded files are ready for download
		7.3.2.		Download all files
		7.3.3.		Verify contents of .msi / .zip
				> At least open the ReadMe or RelNotes

	7.4.			Feature request and bug trackers		00:10		18:10
		7.4.1.		Check that items that are covered by this release have been closed

## 8. Finalization
				Duration	Step		Total

8.				Finalization		00:00	02:10	18:10	20:00

	8.1.			Submit news		00:15		18:25
		8.1.1.		Go to 'Develop > News'
		8.1.2.		Add news
				Title:
				"YAT 2.0 Gamma 1 Version 1.99.32"
				Text:
				"<Intro of release mail>"

				HowTo:
				<https://sourceforge.net/apps/trac/sourceforge/wiki/News>

	8.2.			Send e-mail to the YAT mailing list (Attention: Mail delay up to 60 min !!!)		00:15		18:40
		8.2.1.		Check/update mailing list
		8.2.2.		Write e-mail based on earlier mailings
				> Make sure that links are updated completely, i.e. link text and link below
				> Make sure the correct release notes are used
		8.2.3.		Send as "y-a-terminal@users.sourceforge.net"
		8.2.4.		Send to "y-a-terminal-users@lists.sourceforge.net"
		8.2.5.		Send encoded in Unicode
				> Thunderbird: Options > Encoding > Unicode
		8.2.6.		Send as Text+HTML
				> Thunderbird: Options > Format > Text+HTML
		8.2.7.		Save e-mail in offline archive "\Distribution"
		8.2.8.		Accept e-mail as moderator in mailman if needed

	8.3.			Commit		00:05		18:45
		8.3.1.		Commit any modifications during the release process to the subversion repository
		8.3.2.		Log out as 'y-a-terminal'

	8.4.			Recreate and verify working copy		00:15		19:00
		8.4.1.		Rename the existing working copy to "Trunk_<New Date>" (e.g. _2013-02-02)
		8.4.2.		Remove existing backups "Trunk_<Old Date>"
		8.4.3.		Check for updates of TortoiseSVN and AnkhSVN
		8.4.4.		Create a new folder "Trunk"
		8.4.5.		Check the head revision out into "Trunk"
		8.4.6.		Open the YAT solution
		8.4.7.		Fold all projects
		8.4.8.		Set 'YAT' as the active startup project
		8.4.9.		Build "Debug Test" and "Release Test" to ensure that all files are committed

	8.5.			Archive		00:15		19:15
		8.5.1.		Export the new working copy to offline archive "<Version>\Working Copy"
				> Use 'SVN > Export...'
		8.5.2.		Pack the copy into a properly named zip file

	8.6.			Update and verify working copy (wait for a few days in case of a severe issue)		00:15		19:30
		8.6.1.		Increment product version in ALAZ.Version
		8.6.2.		Increment product version in netrtfwriter AssemblyInfo
				> All versions must be incremented to ensure proper installation/update!
		8.6.3.		Increment product version in MKY.Version
		8.6.4.		Set product version in MKY file headers
				> Add 'Development', e.g. '// MKY Development Version 1.0.14'
		8.6.5.		Increment product version in NUnit.Version
		8.6.6.		Set product version in NUnit file headers
				> Add 'Development', e.g. '// NUnit Development Version 1.0.11'
		8.6.7.		Increment product version in YAT.Version
		8.6.8.		Set product version in YAT file headers
				> Add 'Development', e.g. '// YAT 2.0 Gamma 2 Development Version 1.99.35'
		8.6.9.		Set product name post fix in "YAT.Utilities.ApplicationInfo"
				> Add 'Development' to clearly state that files are non-released revisions
		8.6.10.		Add a new section to the release notes
				> Copy limitations and known issues from last release
		8.6.11.		Verify that the solution still properly builds and runs

	8.7.			Update statistics		00:15		19:45
		8.7.1.		Update "\YAT\!-Doc.SourceForge\"

	8.8.			Commit		00:05		19:50
		8.8.1.		Commit modifications to the subversion repository

	8.9.			Backup PC		00:30		20:00
		8.9.1.		Offline archive
		8.9.2.		Sandboxes